## Sec-CNC Schedule
2018-09-06
2018-09-20
MACHINE | PART NUMBER | PACKET MADE | Order Qty | QTY Remaining | Routing Cards | RATE PCS/HR | SETUP TIME | TOTAL HRS | TOTAL SHIFTS | MAKE FROM PART NUMBER | ROUGH WGT EA | Finished Weight | Weight Per Bar | MATL/PCS NEEDED | # of Bars Required | DAYS | ORIG STRT DATE | SCH'D START DATE | ORIG DUE DATE | COMMENTS
[22 empty] | CNC Shifts Behind | CNC 2 Weeks
CNC SCHEDULE | [17 empty] | 2018-09-06 |  |  |  | 533 | 902
CNC-Okuma Cadet | C3850001 (1/3) | 620955 | 600 | 0 | 0 | 6 | 0 | 0 | 0 | A02002-0028 | 0.6598 | 0.24672 | 29.31 | 0 | 0 | 0 | 2018-06-01 | 2018-09-06 | 2018-06-10 | job out 9/4 |  | 0 | 0
Shifts | A48001 (1/2) | 620940 | 150 | 85 | 0.073464 | 14 | 0 | 6.0714 | 1 | A02002-0038 | 0.4721 | 0.121 | 54.03 | 40.1285 | 0.74271 | 0.5 | 2018-08-29 | 2018-09-06 | 2018-08-31 | job out 9/6 |  | 1 | 1
2 | FS134(1/2) | 620881 | 900 | 900 | 0.54643 | 12 | 3 | 78 | 10 | A02002-0024 | 0.1962 | 0.085 | 21.54 | 176.58 | 8.1978 | 5 | 2018-08-10 | 2018-09-07 | 2018-08-30 |  |  | 10 | 10
| V1000004 | 620198 | 1500 | 1500 | 2.8071 | 30 | 2 | 52 | 7 | A02002-0056 | 0.8811 | 0.262 | 117.25 | 1321.65 | 11.2721 | 3.5 | 2018-08-01 | 2018-09-14 | 2018-08-20 |  |  | 7 | 7
| G200-12 | 621099 | 1500 | 1500 | 0.40714 | 27 | 2 | 57.5556 | 8 | A02002-0040 | 0.1342 | 0.038 | 59.82 | 201.3 | 3.3651 | 4 | 2018-08-20 | 2018-09-20 | 2018-09-04 |  |  | 8 | 8
| VR1002 | new | 250 | 250 | 1.1518 | 8 | 3.5 | 34.75 | 5 | A02001-0048 | 1.6384 | 0.645 | 78.12 | 409.6 | 5.2432 | 2.5 | 2018-08-02 | 2018-09-26 | 2018-08-21 |  |  | 5 | 5
| MPC40003 | STND | 1500 | 1500 | 2.9357 | 12 | 4.5 | 129.5 | 17 | A02002-0048 | 0.6357 | 0.274 | 86.14 | 953.55 | 11.0698 | 8.5 | 2018-09-01 | 2018-10-01 | 2018-09-24 |  |  |  | 17
| VRGSS12501 (1/3) | 611596 | 50 | 50 | 0.20679 | 60 | 3 | 3.8333 | 1 | A06202-0056 | 1.8283 | 0.579 | 108.5 | 91.415 | 0.84253 | 0.5 | 2018-08-15 | 2018-10-12 | 2018-09-01 |  |  | 1 | 1
| S144S144002(2/2) | 618823 | 2000 | 1508 |  | 32 | 0 | 47.125 | 6 | S144S144002(1/2) | NA |  |  | 1508 |  | 3 | 2018-12-01 | 2018-10-15 | 2018-12-20 | Balance of previous run
| P1212001-10 (1/2) | new | 500 | 500 | 4.9357 | 5 | 2 | 102 | 14 | A02002-0060 | 4.6706 | 1.382 | 134.6 | 2335.3 | 17.3499 | 7 | 2018-08-02 | 2018-10-18 | 2018-08-21 |  |  | 14 | 14
| P1515001-10 (1/2) | new | 50 | 50 | 0.62964 | 19 | 2 | 4.6316 | 1 | A02002-0072 | 6.9704 | 1.763 | 193.82 | 348.52 | 1.7982 | 0.5 | 2018-08-02 | 2018-10-29 | 2018-08-21 |  |  | 1 | 1
2018-10-30
2018-09-06
CNC- Hardinge Cobra | FS135(1/2) | 619961 | 900 | 35 | 0.26305 | 10 | 0 | 3.5 | 0 | A02002-0022 | 0.1491 | 1.0522 | 18.1 | 5.2185 | 0.28831 | 0 | 2018-07-01 | 2018-09-06 | 2018-07-30 | job out 9/5 |  | 0 | 0
Shifts | FS135(2/2) | 619961 | 900 | 900 |  | 12 | 3 | 78 | 10 | FS135(1/2) | NA |  |  | 900 |  | 10 | 2018-07-01 | 2018-09-06 | 2018-07-30 |  |  | 10 | 10
2 | C3850001 (2/3) | 620955 | 600 | 600 |  | 27 | 1.5 | 23.7222 | 3 | C3850001 (1/3) | NA |  |  | 600 |  | 1.5 | 2018-06-01 | 2018-09-20 | 2018-06-10 | From Cadet |  | 3 | 3
| FS134(2/2) | 620881 | 900 | 900 |  | 19 | 2 | 49.3684 | 7 | FS134(1/2) | NA |  |  | 900 |  | 3.5 | 2018-08-10 | 2018-09-24 | 2018-08-30 | From Cadet |  | 7 | 7
| CRV7503(2/2) | 619731 | 1500 | 1500 |  | 22 | 8 | 76.1818 | 10 | CRV7503(1/2) | NA |  |  | 1500 |  | 5 | 2018-09-01 | 2018-09-28 | 2018-09-17 |  |  |  | 10
| FS128 | new | 700 | 700 | 0.0225 | 13 | 3 | 56.8462 | 8 | A02001-0016 | 0.0253 | 0.0045 | 8.68 | 17.71 | 2.0403 | 4 | 2018-09-01 | 2018-10-05 | 2018-09-17 |  |  |  | 8
| A24023 (2/2) | new | 500 | 500 |  | 13 | 4 | 42.4615 | 6 | A24023 (1/2) | NA |  |  | 500 |  | 3 | 2018-07-15 | 2018-10-11 | 2018-08-01 | From T42 |  | 6 | 6
| EH38009 | new | 750 | 750 | 0.14464 | 12 | 8 | 70.5 | 9 | A19101-0016 | 0.0482 | 0.027 | 2.83 | 36.15 | 12.7739 | 4.5 | 2018-08-20 | 2018-10-16 | 2018-09-10 |  |  |  | 9
| EH38023 | new | 750 | 750 | 0.064286 | 12 | 8 | 70.5 | 9 | A05501-0028 | 0.012 | 0.012 | 3.71 | 9 | 2.4259 | 4.5 | 2018-08-20 | 2018-10-23 | 2018-09-10 |  |  |  | 9
| P1212001-10 (2/2) | new | 500 | 500 |  | 12 | 3 | 44.6667 | 6 | P1212001-10 (1/2) | NA |  |  | 500 |  | 3 | 2018-08-02 | 2018-10-30 | 2018-08-21 | From Cadet |  | 6 | 6
| P1515001-10 (2/2) | new | 50 | 50 |  | 19 | 4 | 6.6316 | 1 | P1515001-10 (1/2) | NA |  |  | 50 |  | 0.5 | 2018-08-02 | 2018-11-02 | 2018-08-21 | From Cadet |  | 1 | 1
| 106272-11 | 619555 | 30 | 21 | 0.014775 | 57 | 16 | 16.3684 | 2 | 106273-1 | NA | 0.0985 |  | 21 |  | 1 | 2018-09-15 | 2018-11-05 | 2018-10-01 | Balance of Previous | Need tooling |  | 2
2018-11-06
2018-11-06
2018-09-06
CNC-Hardinge T42 | FT10101 (1/3) | 620958 | 500 | 0 | 0 | 8 | 0 | 0 | 0 | A02002-0032 | 0.727 | 0.307 | 38.29 | 0 | 0 | 0 | 2018-08-15 | 2018-09-06 | 2018-08-28 | job out 9/4 |  | 0 | 0
Shifts | FT10101 (2/3) | 620958 | 500 | 400 |  | 29 | 0 | 13.7931 | 2 | FT10101 (1/3) | NA |  |  | 400 |  | 1 | 2018-08-15 | 2018-09-06 | 2018-08-28 | running 9/6 |  | 2 | 2
2 | CRV7503(1/2) | 619731 | 1500 | 1500 | 0.45643 | 12 | 8 | 133 | 18 | A06201-0036 | 0.354 | 0.0426 | 40.56 | 531 | 13.0917 | 9 | 2018-09-01 | 2018-09-07 | 2018-09-15 |  |  |  | 18
| MPC10002-SS | Sample | 50 | 50 |  | 3 | 16 | 32.6667 | 4 | A06101-0032 | NA |  |  | 50 |  | 2 | 2018-06-26 | 2018-09-20 | 2018-07-26 | Material on racks by S1 | Jeff Van Horn | 4 | 4
| MPC10004-SS | Sample | 50 | 50 |  | 3 | 16 | 32.6667 | 4 | A06101-0032 | NA |  |  | 50 |  | 2 | 2018-06-26 | 2018-09-24 | 2018-07-26 | Material on racks by S1 | Jeff Van Horn | 4 | 4
| 200195 (1/3) | new | 25 | 25 | 0.10321 | 1 | 3 | 28 | 4 | A06501-0048 | 2.4482 | 0.578 | 72.1 | 61.205 | 0.84889 | 2 | 2018-08-07 | 2018-09-26 | 2018-08-27 |  |  | 4 | 4
| 200195 (2/3) | new | 25 | 25 |  | 1 | 12 | 37 | 5 | 200195 (1/3) | NA |  |  | 25 |  | 2.5 | 2018-08-07 | 2018-09-28 | 2018-08-27 |  |  | 5 | 5
| 200195 (3/3) | new | 25 | 25 |  | 1 | 12 | 37 | 5 | 200195 (2/3) | NA |  |  | 25 |  | 2.5 | 2018-08-07 | 2018-10-03 | 2018-08-27 |  |  | 5 | 5
| MPC40001 | 613717 | 1500 | 435 | 0.92593 | 11 | 0 | 39.5455 | 5 | A02001-0042 | 1.2907 | 0.298 | 59.81 | 561.4545 | 9.3873 | 2.5 | 2018-09-01 | 2018-10-08 | 2018-09-10 |  |  |  | 5
| A24023 (1/2) | new | 500 | 500 | 0.47143 | 13 | 4 | 42.4615 | 6 | A02002-0032 | 0.4476 | 0.132 | 38.29 | 223.8 | 5.8449 | 3 | 2018-07-15 | 2018-10-11 | 2018-08-01 |  |  | 6 | 6
| 100700-1(1/3) | new | 50 | 50 | 0 | 4 | 4 | 16.5 | 2 | 100046-999 | NA |  |  | 50 |  | 1 | 2018-08-01 | 2018-10-16 | 2018-08-15 |  |  | 2 | 2
| 100700-1(2/3) | new | 50 | 50 |  | 6 | 4 | 12.3333 | 2 | 100700-1(1/3) | NA |  |  | 50 |  | 1 | 2018-08-01 | 2018-10-17 | 2018-08-15 |  |  | 2 | 2
| 100700-1(3/3) | new | 50 | 50 |  | 6 | 4 | 12.3333 | 2 | 100700-1(2/3) | NA |  |  | 50 |  | 1 | 2018-08-01 | 2018-10-18 | 2018-08-15 |  |  | 2 | 2
| 300322 (1/2) | 618205 | 150 | 150 | 0.055393 | 8 | 4 | 22.75 | 3 | A06153-0016 | 0.1018 | 0.0517 | 10.52 | 15.27 | 1.4515 | 1.5 | 2018-09-04 | 2018-10-19 | 2018-09-24 |  |  |  | 3
| EH38006 | new | 750 | 750 | 0.17625 | 12 | 8 | 70.5 | 9 | A19101-0036 | 0.1385 | 0.0329 | 14.03 | 103.875 | 7.4038 | 4.5 | 2018-08-24 | 2018-10-23 | 2018-09-24 |  |  |  | 9
| VRGSS12501 (2/3) | 611596 | 50 | 50 |  | 16 | 2 | 5.125 | 1 | VRGSS12501(A) | NA |  |  | 50 |  | 0.5 | 2018-08-15 | 2018-10-30 | 2018-09-01 | From Cadet |  | 1 | 1
| A24010 (1/2) | new | 1400 | 1400 | 0.14464 | 22 | 4 | 67.6364 | 9 | A02001-0022 | 0.2352 | 0.0411 | 16.41 | 329.28 | 20.0658 | 4.5 | 2018-09-15 | 2018-10-31 | 2018-10-01 |  |  |  | 9
| EH38025 | new | 750 | 750 | 0.0053571 | 12 | 8 | 70.5 | 9 | A02001-0014 | 0.001 | 0.001 | 6.65 | 0.75 | 0.11278 | 4.5 | 2018-10-01 | 2018-11-07 | 2018-10-29
2018-11-14
2018-09-06
CNC-HAAS H1 | 11-4-C-BLNK | 614198 | 100 | 0 | 0 | 42 | 0 | 0 | 0 | A02071-0056 | 1.6788 | 0.812 | 106.33 | 0 | 0 | 0 | 2018-07-15 | 2018-09-06 | 2018-08-01 | job out |  | 0 | 0
(2" Cap) | 7-3-D-BLNK | 620363 | 1300 | 310 | 1.0241 | 43 | 0 | 7.2093 | 1 | A02071-0052 | 1.3483 | 0.4625 | 91.68 | 417.973 | 4.559 | 0.5 | 2018-08-01 | 2018-09-06 | 2018-08-15 | job out |  | 1 | 1
Shifts | SB2201 (2/3) | 618028 | 2300 | 2300 |  | 27 | 2 | 87.1852 | 12 | SB2201 (1/3) | NA |  |  | 2300 |  | 6 | 2018-08-30 | 2018-09-07 | 2018-09-07 | running 9/6 | Run 500pcs |  | 12
2 | CRV7507 | 616686 | 1300 | 1300 | 0.39557 | 11 | 8 | 126.1818 | 17 | A06201-0064 | 0.9506 | 0.0426 | 128.2 | 1235.78 | 9.6395 | 8.5 | 2018-08-10 | 2018-09-17 | 2018-08-20 |  |  | 17 | 17
| 5-4-C-BLNK | 618535 | 1500 | 1500 | 2.1246 | 27 | 1 | 56.5556 | 8 | A02071-0040 | 0.6361 | 0.1983 | 54.25 | 954.15 | 17.588 | 4 | 2018-09-15 | 2018-09-28 | 2018-09-30 |  |  |  | 8
| 11-4-F-BLNK | new | 400 | 400 | 2.5957 | 34 | 1 | 12.7647 | 2 | A02071-0064 | 2.354 | 0.9085 | 138.88 | 941.6 | 6.78 | 1 | 2018-09-01 | 2018-10-04 | 2018-09-15 |  |  |  | 2
| 4-4-B-BLNK | new | 600 | 600 | 0.83571 | 52 | 1 | 12.5385 | 2 | A02071-0034 | 0.525 | 0.195 | 39.2 | 315 | 8.0357 | 1 | 2018-09-01 | 2018-10-05 | 2018-09-15 |  |  |  | 2
| 502-A-BLNK | new | 2100 | 2100 | 2.7 | 30 | 2 | 72 | 10 | A02071-0034 | 0.5094 | 0.18 | 39.2 | 1069.74 | 27.2893 | 5 | 2018-09-01 | 2018-10-08 | 2018-09-15 |  |  |  | 10
| 7-4-C-BLNK | STND | 1100 | 1100 | 3.0486 | 52 | 1 | 22.1538 | 3 | A02071-0040 | 0.6404 | 0.388 | 54.25 | 704.44 | 12.9851 | 1.5 | 2018-09-02 | 2018-10-15 | 2018-09-16 |  |  |  | 3
2018-10-17
2018-09-06
CNC-HAAS H2 | RCF013 (1/2) | 610991 | 1500 | 0 | 0 | 14 | 0 | 0 | 0 | A02001-0020 | 0.7 | 0.0861 | 13.56 | 0 | 0 | 0 | 2018-06-15 | 2018-09-06 | 2018-07-01 | job out 8/30 |  | 0 | 0
Shifts | RCF013 (2/2) | 610991 | 1500 | 897 |  | 14 | 0 | 64.0714 | 9 | RCF013 (1/2) | NA |  |  | 897 |  | 4.5 | 2018-06-15 | 2018-09-06 | 2018-07-01 | running 8/30 |  | 9 | 9
2 | C10 | new | 500 | 500 | 0.24982 | 42 | 2 | 13.9048 | 2 | A02001-0036 | 0.144 | 0.06995 | 43.94 | 72 | 1.6386 | 1 | 2018-09-01 | 2018-09-13 | 2018-09-10 |  |  |  | 2
| C12 | new | 750 | 750 | 0.37473 | 25 | 1 | 31 | 4 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 93 | 2.1165 | 2 | 2018-09-10 | 2018-09-14 | 2018-09-20 |  |  |  | 4
| C15 | new | 800 | 800 | 0.39971 | 31 | 1 | 26.8065 | 4 | A02001-0036 | 0.144 | 0.06995 | 43.94 | 115.2 | 2.6218 | 2 | 2018-09-10 | 2018-09-18 | 2018-09-20 |  |  |  | 4
| C17 | new | 500 | 500 | 0.24982 | 25 | 1 | 21 | 3 | A02001-0036 | 0.144 | 0.06995 | 43.94 | 72 | 1.6386 | 1.5 | 2018-09-10 | 2018-09-20 | 2018-09-20 |  |  |  | 3
| C20 | new | 300 | 300 | 0.14989 | 25 | 1 | 13 | 2 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 37.2 | 0.84661 | 1 | 2018-09-10 | 2018-09-24 | 2018-09-20 |  |  |  | 2
| C30 | new | 400 | 400 | 0.19986 | 31 | 3 | 15.9032 | 2 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 49.6 | 1.1288 | 1 | 2018-09-10 | 2018-09-25 | 2018-09-20 |  |  |  | 2
| C40 | new | 200 | 200 | 0.092857 | 31 | 2 | 8.4516 | 1 | A02001-0036 | 0.124 | 0.065 | 43.94 | 24.8 | 0.56441 | 0.5 | 2018-09-10 | 2018-09-26 | 2018-09-20 |  |  |  | 1
| C50 | new | 200 | 200 | 0.092857 | 25 | 1 | 9 | 1 | A02001-0036 | 0.124 | 0.065 | 43.94 | 24.8 | 0.56441 | 0.5 | 2018-09-10 | 2018-09-27 | 2018-09-20 |  |  |  | 1
| C6 | new | 150 | 150 | 0.069643 | 31 | 1 | 5.8387 | 1 | A02001-0036 | 0.144 | 0.065 | 43.94 | 21.6 | 0.49158 | 0.5 | 2018-09-10 | 2018-09-28 | 2018-09-20 |  |  |  | 1
| C8 | new | 500 | 500 | 0.23214 | 49 | 1 | 11.2041 | 1 | A02001-0036 | 0.144 | 0.065 | 43.94 | 72 | 1.6386 | 0.5 | 2018-09-10 | 2018-10-01 | 2018-09-20 |  |  |  | 1
| G150-4SS | new | 1300 | 1300 | 1.0029 | 7 | 5 | 190.7143 | 25 | A06201-0048 | 0.3584 | 0.108 | 72.1 | 465.92 | 6.4621 | 12.5 | 2018-10-02 | 2018-10-02 | 2018-10-22
2018-10-19
2018-09-06
CNC-HAAS H3 | CRV7512 | 618335 | 3000 | 0 | 0 | 18 | 0 | 0 | 0 | A06201-0052 | 0.3632 | 0.038 | 84.62 | 0 | 0 | 0 | 2018-06-01 | 2018-09-06 | 2018-06-15 | job out 9/5 |  | 0 | 0
(1-7/8" Cap) | CRV7510(1/2) | 616921 | 1500 | 1450 | 1.3775 | 11 | 0 | 131.8182 | 18 | A06201-0054 | 0.2622 | 0.133 | 91.5 | 380.19 | 4.1551 | 9 | 2018-09-01 | 2018-09-06 | 2018-09-17 | running 9/5 |  |  | 18
Shifts | 106207-1 (1/2) | 621240 | 25 | 25 | 0.16607 | 5 | 3 | 8 | 1 | 106205-999 | NA | 0.93 |  | 25 |  | 0.5 | 2018-08-01 | 2018-09-19 | 2018-08-15 |  |  | 1 | 1
2 | 106207-1 (2/2) | 621240 | 25 | 25 |  | 5 | 1.5 | 6.5 | 1 | 106207-1 (1/2) | NA |  |  | 25 |  | 0.5 | 2018-08-01 | 2018-09-20 | 2018-08-15 |  |  | 1 | 1
| 106205-1 (1/2) | 621795 | 25 | 25 | 0.17304 | 5 | 2.5 | 7.5 | 1 | 106205-999 | NA | 0.969 |  | 25 |  | 0.5 | 2018-08-01 | 2018-09-21 | 2018-08-20 |  |  | 1 | 1
| 106205-1 (2/2) | 621795 | 25 | 25 |  | 5 | 2.5 | 7.5 | 1 | 106205-1 (1/2) | NA |  |  | 25 |  | 0.5 | 2018-08-01 | 2018-09-24 | 2018-08-20 |  |  | 1 | 1
| 106206-1 (1/2) | new | 5 | 5 | 0.030236 | 5 | 2.5 | 3.5 | 0 | 106204-999 | NA | 0.8466 |  | 5 |  | 0 | 2018-08-20 | 2018-09-25 | 2018-08-30 |  |  | 0 | 0
| 106206-1 (2/2) | new | 5 | 5 |  | 5 | 1.5 | 2.5 | 1 | 106206-1 (1/2) | NA |  |  | 5 |  | 0.5 | 2018-08-20 | 2018-09-25 | 2018-08-30 |  |  | 1 | 1
| 106206-3 (1/2) | new | 15 | 15 | 0.086786 | 5 | 2.5 | 5.5 | 1 | 106204-999 | NA | 0.81 |  | 15 |  | 0.5 | 2018-10-01 | 2018-09-26 | 2018-10-22
| 106206-3 (2/2) | new | 15 | 15 |  | 5 | 1.5 | 4.5 | 1 | 106206-3 (1/2) | NA |  |  | 15 |  | 0.5 | 2018-10-01 | 2018-09-27 | 2018-10-20
| 106210-1 | 613188 | 100 | 100 | 0.19879 | 15 | 8 | 14.6667 | 2 | A06201-0020 | 0.368 | 0.2783 | 12.9 | 36.8 | 2.8527 | 1 | 2018-09-01 | 2018-09-28 | 2018-09-17 | From B/S 18 | needs 2nd op CNC |  | 2
| G125-21SS | new | 200 | 200 | 0.048571 | 10 | 3 | 23 | 3 | A06201-0024 | 0.0799 | 0.034 | 18.58 | 15.98 | 0.86006 | 1.5 | 2018-09-04 | 2018-10-01 | 2018-09-24 |  |  |  | 3
| G150-5ASS | new | 1200 | 1200 | 0.85714 | 11 | 4 | 113.0909 | 15 | A06201-0044 | 0.2894 | 0.1 | 60.59 | 347.28 | 5.7316 | 7.5 | 2018-09-10 | 2018-10-03 | 2018-10-01 |  |  |  | 15
2018-10-15
2018-09-06
CNC-HAAS H4 | SF9-2.5-B-BLNK | 617911 | 300 | 0 | 0 | 18 | 0 | 0 | 0 | A02071-0096 | 8.1782 | 2.11 | 312.49 | 0 | 0 | 0 | 2018-08-01 | 2018-09-06 | 2018-08-15 | job out |  | 0 | 0
(2-1/4" Rnd Min) | 11-4-K-BLNK | 619345 | 50 | 0 | 0 | 13 | 0 | 0 | 0 | A02071-0128 | 16.2917 | 5.38 | 555.53 | 0 | 0 | 0 | 2018-08-05 | 2018-09-06 | 2018-08-20 | job out |  | 0 | 0
Shifts | 2203-A-BLNK | 611842 | 50 | 0 | 0 | 3 | 0 | 0 | 0 | A01301-0088 | 6.5365 | 3.2699 | 243 | 0 | 0 | 0 | 2018-06-11 | 2018-09-06 | 2018-06-21 | job out |  | 0 | 0
2 | 2803-A-BLNK | 618297 | 100 | 0 | 0 | 2 | 0 | 0 | 0 | A01301-0112 | 12.9759 | 5.41 | 392.52 | 0 | 0 | 0 | 2018-06-10 | 2018-09-06 | 2018-06-20 | job out |  | 0 | 0
| 9-3-E-BLNK | 619962 | 450 | 450 | 3.4605 | 24 | 0 | 18.75 | 3 | A02071-0076 | 4.3326 | 1.0766 | 195.85 | 1949.67 | 9.9549 | 1.5 | 2018-08-20 | 2018-09-06 | 2018-08-28 | no material |  | 3 | 3
| 11-4-L-BLNK | 619628 | 375 | 375 | 7.5123 | 16 | 2 | 25.4375 | 3 | A02071-0096 | 7.9106 | 2.8046 | 312.49 | 2966.475 | 9.493 | 1.5 | 2018-09-01 | 2018-09-10 | 2018-09-15 |  |  |  | 3
| 707-A-BLNK | 620201 | 400 | 400 | 2.7314 | 21 | 2.5 | 21.5476 | 3 | A02071-0072 | 3.7932 | 0.956 | 175.8 | 1517.28 | 8.6307 | 1.5 | 2018-09-02 | 2018-09-12 | 2018-09-16 |  |  |  | 3
2018-09-14
2018-09-06
CNC-Mori Seki M1 | 9-8-A-BLNK | 616492 | 100 | 0 | 0 | 27 | 0 | 0 | 0 | A02071-0060 | 2.1325 | 0.668 | 122.07 | 0 | 0 | 0 | 2018-07-24 | 2018-09-06 | 2018-08-10 | job out |  | 0 | 0
(2" Cap) | 702-A-BLNK | 618020 | 2000 | 1255 | 2.8874 | 33 | 0 | 38.0303 | 5 | A02071-0040 | 0.8392 | 0.3221 | 54.25 | 1053.196 | 19.4138 | 2.5 | 2018-08-15 | 2018-09-06 | 2018-08-30 | running 8/31 |  | 5 | 5
Shifts | 902-A-BLNK | 619732 | 450 | 450 | 2.4782 | 34 | 0.5 | 13.7353 | 2 | A02071-0056 | 2.1486 | 0.771 | 106.33 | 966.87 | 9.0931 | 1 | 2018-08-15 | 2018-09-11 | 2018-08-30 |  |  | 2 | 2
2 | 11-4-A-BLNK | 620302 | 100 | 100 | 0.71571 | 54 | 1 | 2.8519 | 0 | A02071-0046 | 1.4035 | 1.002 | 71.75 | 140.35 | 1.9561 | 0 | 2018-08-15 | 2018-09-12 | 2018-08-30 |  |  | 0 | 0
| 705-A-BLNK | 620819 | 1400 | 1400 | 3.9 | 34 | 2 | 43.1765 | 6 | A02071-0052 | 1.4109 | 0.39 | 91.68 | 1975.26 | 21.5452 | 3 | 2018-08-01 | 2018-09-12 | 2018-08-15 |  |  | 6 | 6
| PCV10002 (2/2) | 613768 | 4500 | 1500 | 0 | 54 | 0 | 27.7778 | 4 | PCV10002 (1/2) | NA |  |  | 1500 |  | 2 | 2018-09-01 | 2018-09-17 | 2018-09-15 | Balance of previous run |  |  | 4
| 7-4-E-BLNK | 615567 | 1000 | 1000 | 3.8571 | 33 | 1.5 | 31.803 | 4 | A02071-0056 | 1.6703 | 0.54 | 106.33 | 1670.3 | 15.7086 | 2 | 2018-09-01 | 2018-09-19 | 2018-09-15 |  |  |  | 4
2018-09-21
2018-09-21
| PCV10002 (2/2) | new | 4000 | 4000 | 0 | 54 | 16 | 90.0741 | 12 | PCV10002 (1/2) | NA |  |  | 4000 |  |  | 2018-10-01 | 2018-09-21 | 2018-10-15
2018-09-06
CNC--Ganesh | RP1201 | 619449 | 3000 | 2500 | 4.3214 | 22 | 0 | 113.6364 | 15 | A02001-0044 | 0.383 | 0.242 | 65.64 | 957.5 | 14.5871 | 7.5 | 2018-09-01 | 2018-09-06 | 2018-09-15 | running 9/4 |  |  | 15
Shifts | RP1202 | 621213 | 3000 | 3000 | 5.1857 | 23 | 0.5 | 130.9348 | 17 | A02001-0044 | 0.383 | 0.242 | 65.64 | 1149 | 17.5046 | 8.5 | 2018-09-01 | 2018-09-18 | 2018-09-15 |  |  |  | 17
2 | [17 empty] | 2018-10-01
2018-09-06
CNC--Okuma Genos #1 | PCV10001 | 619340 | 1500 | 706 | 6.3036 | 7 | 0 | 100.8571 | 13 | A01001-0073 | 6.48 | 1.25 | 171.4 | 4574.88 | 26.6912 | 6.5 | 2018-07-15 | 2018-09-06 | 2018-07-30 | running 8/21 |  | 13 | 13
Shifts | PCV10001 | 621206 | 1500 | 1500 | 13.3929 | 7 | 0 | 214.2857 | 29 | A01001-0073 | 6.48 | 1.25 | 171.4 | 9720 | 56.7095 | 14.5 | 2018-08-01 | 2018-09-17 | 2018-08-15 |  |  | 29 | 29
2 | [17 empty] | 2018-10-08
2018-09-06
CNC--Okuma Genos #2 | 5-4-9 | 621197 | 3000 | 2108 | 6.0078 | 14 | 0 | 150.5714 | 20 | A02071-0052 | 1.2882 | 0.399 | 91.68 | 2715.5256 | 29.6196 | 10 | 2018-08-01 | 2018-09-06 | 2018-08-15 | running 8/30 |  | 20 | 20
Shifts | 902-19-3/16 | 621883 | 2000 | 2000 | 8.3429 | 14 | 2 | 144.8571 | 19 | A02071-0056 | 2.0283 | 0.584 | 106.33 | 4056.6 | 38.151 | 9.5 | 2018-09-10 | 2018-09-20 | 2018-09-20 |  |  |  | 19
2 | EH38030 | new | 1500 | 1500 | 1.0929 | 12 | 8 | 133 | 18 | A02001-0036 | 0.2171 | 0.102 | 43.94 | 325.65 | 7.4112 | 9 | 2018-09-04 | 2018-10-04 | 2018-09-24 |  |  |  | 18
2018-10-17
2018-09-06
CNC--Okuma LB3000 | FT13801 | 618477 | 3000 | 725 | 0.18612 | 22 | 0 | 32.9545 | 4 | A02002-0018 | 0.2352 | 0.03594 | 12.11 | 170.52 | 14.0809 | 2 | 2018-08-17 | 2018-09-06 | 2018-09-01 | running 8/29 | Material is on A9 | 4 | 4
Shifts | ASC-7 | 620203 | 1100 | 1100 | 1.4929 | 44 | 1 | 26 | 3 | A02071-0032 | 0.6144 | 0.19 | 34.72 | 675.84 | 19.4654 | 1.5 | 2018-09-01 | 2018-09-10 | 2018-09-15 |  |  |  | 3
2 | J-BLNK | 620939 | 750 | 750 | 0.069643 | 49 | 1 | 16.3061 | 2 | A02001-0016 | 0.024 | 0.013 | 8.68 | 18 | 2.0737 | 1 | 2018-08-01 | 2018-09-12 | 2018-08-15 |  |  | 2 | 2
| J1 | 620543 | 1000 | 1000 | 0.092857 | 32 | 1 | 32.25 | 4 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 28.4 | 3.2719 | 2 | 2018-07-15 | 2018-09-13 | 2018-08-01 |  |  | 4 | 4
| J2 | 621232 | 1000 | 1000 | 0.092857 | 31 | 1 | 33.2581 | 4 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 28.4 | 3.2719 | 2 | 2018-07-15 | 2018-09-17 | 2018-08-01 |  |  | 4 | 4
| J4 | 621716 | 1000 | 1000 | 0.092857 | 32 | 1 | 32.25 | 4 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 28.4 | 3.2719 | 2 | 2018-07-15 | 2018-09-19 | 2018-08-01 |  |  | 4 | 4
| J1/4 | new | 1000 | 1000 | 0.092857 | 32 | 1 | 32.25 | 4 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 28.4 | 3.2719 | 2 | 2018-07-15 | 2018-09-21 | 2018-08-01 |  |  | 4 | 4
| J1/2 | new | 500 | 500 | 0.046429 | 32 | 1 | 16.625 | 2 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 14.2 | 1.6359 | 1 | 2018-08-01 | 2018-09-25 | 2018-08-15 |  |  | 2 | 2
| J1/6 | new | 750 | 750 | 0.069643 | 32 | 1 | 24.4375 | 3 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 21.3 | 2.4539 | 1.5 | 2018-08-01 | 2018-09-26 | 2018-08-15 |  |  | 3 | 3
| J2-1/2 | new | 750 | 750 | 0.069643 | 36 | 1 | 21.8333 | 3 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 21.3 | 2.4539 | 1.5 | 2018-08-01 | 2018-09-28 | 2018-08-15 |  |  | 3 | 3
| J3 | new | 750 | 750 | 0.069643 | 32 | 1 | 24.4375 | 3 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 21.3 | 2.4539 | 1.5 | 2018-08-01 | 2018-10-02 | 2018-08-15 |  |  | 3 | 3
| J3/4 | new | 800 | 800 | 0.074286 | 32 | 1 | 26 | 3 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 22.72 | 2.6175 | 1.5 | 2018-08-01 | 2018-10-04 | 2018-08-15 |  |  | 3 | 3
| J5 | new | 750 | 750 | 0.069643 | 32 | 1 | 24.4375 | 3 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 21.3 | 2.4539 | 1.5 | 2018-08-01 | 2018-10-08 | 2018-08-15 |  |  | 3 | 3
| J6 | new | 300 | 300 | 0.027857 | 32 | 1 | 10.375 | 1 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 8.52 | 0.98157 | 0.5 | 2018-08-01 | 2018-10-10 | 2018-08-15 |  |  | 1 | 1
| J8 | new | 300 | 300 | 0.027857 | 64 | 1 | 5.6875 | 1 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 8.52 | 0.98157 | 0.5 | 2018-08-01 | 2018-10-11 | 2018-08-15 |  |  | 1 | 1
| 4-3-5 | Stnd | 5000 | 5000 | 3.5571 | 30 | 1 | 167.6667 | 22 | A02071-0026 | 0.243 | 0.0996 | 22.95 | 1215 | 52.9412 | 11 |  | 2018-10-12
2018-10-29
2018-09-06
CNC--Citizen C1 | 3-3-2 | 620853 | 5000 | 3971 | 0.86511 | 83 | 0 | 47.8434 | 6 | A02071-0020 | 0.091 | 0.0305 | 13.56 | 361.361 | 26.649 | 3 | 2018-08-15 | 2018-09-06 | 2018-08-31 | running 9/5 |  | 6 | 6
Shifts | CRV7505 | 621796 | 1500 | 1500 | 0.085714 | 14 | 8 | 115.1429 | 15 | A06201-0016 | 0.0361 | 0.008 | 8.26 | 54.15 | 6.5557 | 7.5 |  | 2018-09-11
2 | 5-3-3 | 619733 | 2000 | 2000 | 0.43571 | 13 | 3 | 156.8462 | 21 | A02071-0020 | 0.099 | 0.0305 | 13.56 | 198 | 14.6018 | 10.5 | 2018-08-15 | 2018-09-21 | 2018-09-01 |  |  | 21 | 21
| KF120601-12 | new | 1600 | 1600 | 0.99429 | 32 | 1 | 51 | 7 | A02001-0026 | 0.242 | 0.087 | 22.95 | 387.2 | 16.8715 | 3.5 | 2018-08-02 | 2018-10-08 | 2018-08-16 |  |  | 7 | 7
| 4-4-3 | new | 3500 | 3500 | 0.975 | 59 | 0 | 59.322 | 8 | A02071-0026 | 0.22 | 0.039 | 22.95 | 770 | 33.5512 | 4 | 2018-09-01 | 2018-10-12 | 2018-09-15 |  |  |  | 8
| PCV10003 | 610811 | 5000 | 5000 | 1.4286 | 54 | 16 | 108.5926 | 14 | A06101-7314 | 0.0525 | 0.04 | 3.56 | 262.5 | 73.736 | 7 | 2018-08-01 | 2018-10-18 | 2018-08-15 |  |  | 14 | 14
| M4-4-3 | new | 3000 | 3000 | 1.7807 | 57 | 0 | 52.6316 | 7 | A02071-0026 | 0.249 | 0.0831 | 22.95 | 747 | 32.549 | 3.5 |  | 2018-10-29
2018-11-02
2018-09-06
CNC--Citizen C2 | RCF015-13 | 614738 | 7000 | 1473 | 0.010521 | 66 | 0 | 22.3182 | 3 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 2.2095 | 0.65177 | 1.5 | 2018-07-10 | 2018-09-06 | 2018-07-30 | pulling out 9/5 |  | 3 | 3
Mortex Capable | RCF015-24 | 620544 | 500 | 0 | 0.053571 | 66 | 0 | 0 | 0 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 0 | 0 | 0 | 2018-08-10 | 2018-09-10 | 2018-09-01 | job out 9/5 |  | 0 | 0
Shifts | RCF015-19 | 620546 | 1600 | 1600 | 0.053571 | 66 | 0 | 24.2424 | 3 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 2.4 | 0.70796 | 1.5 | 2018-08-10 | 2018-09-10 | 2018-09-01 | running 9/6 |  | 3 | 3
2 | RCF015-10 | 620547 | 2000 | 2000 | 0.010521 | 66 | 4 | 34.303 | 5 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 3 | 0.88496 | 2.5 | 2018-08-10 | 2018-09-12 | 2018-09-01 |  |  | 5 | 5
| RCF015-17 | 620548 | 7500 | 7500 | 0.014286 | 66 | 4 | 117.6364 | 16 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 11.25 | 3.3186 | 8 | 2018-08-10 | 2018-09-17 | 2018-09-01 |  |  | 16 | 16
| 447681 | 612305 | 550 | 550 | 0.055 | 5 | 8 | 118 | 16 | A02001-0016 | 0.0347 | 0.014 | 8.68 | 19.085 | 2.1987 | 8 | 2018-06-01 | 2018-09-27 | 2018-07-22 | engineering to run | per Steve Salmons | 16 | 16
| CY90001 | 618336 | 3000 | 3000 | 2.5264 | 16 | 2 | 189.5 | 25 | A02002-0024 | 0.229 | 0.1179 | 21.54 | 687 | 31.8942 | 12.5 | 2018-08-15 | 2018-10-09 | 2018-09-01 |  |  | 25 | 25
2018-10-26
2018-09-06
CNC--Citizen(A32) C3 | SF403-4-3/16 | 620859 | 1000 | 0 | 0 | 50 | 0 | 0 | 0 | A02071-0028 | 0.2184 | 0.092 | 26.58 | 0 | 0 | 0 | 2018-08-11 | 2018-09-06 | 2018-08-31 | job out 8/28 |  | 0 | 0
1-1/4" Cap | SF403-6-3/16 | 620611 | 1000 | 0 | 0 | 29 | 0 | 0 | 0 | A02071-0028 | 0.2184 | 0.085 | 26.58 | 0 | 0 | 0 | 2018-08-11 | 2018-09-06 | 2018-08-31 | job out 8/30 |  | 0 | 0
2 | G50-10SS | 620549 | 1000 | 1000 | 0.30714 | 15 | 4 | 70.6667 | 9 | A06201-0020 | 0.1334 | 0.043 | 12.9 | 133.4 | 10.3411 | 4.5 | 2018-08-01 | 2018-09-06 | 2018-08-08 | set up 9/5 |  | 9 | 9
| SF403-4-3/16 | 619629 | 4000 | 4000 | 2.6286 | 50 | 1 | 81 | 11 | A02071-0028 | 0.2184 | 0.092 | 26.58 | 873.6 | 32.8668 | 5.5 | 2018-09-01 | 2018-09-13 | 2018-09-15 |  |  |  | 11
| SF403-6-3/16 | 621246 | 3000 | 3000 | 1.8214 | 29 | 1 | 104.4483 | 14 | A02071-0028 | 0.2184 | 0.085 | 26.58 | 655.2 | 24.6501 | 7 | 2018-09-05 | 2018-09-21 | 2018-09-20 |  |  |  | 14
| SF403-2-3/16 | new | 3000 | 3000 | 1.8214 | 62 | 0 | 48.3871 | 6 | A02071-0028 | 0.2814 | 0.085 | 26.58 | 844.2 | 31.7607 | 3 | 2018-09-06 | 2018-10-02 | 2018-09-21 |  |  |  | 6
2018-10-05
2018-09-06
CNC--Miyano 3 Jaw | A48001 (2/2) | 620940 | 150 | 150 |  | 22 | 4 | 10.8182 | 1 | A48001 (1/2) | NA |  |  | 150 |  | 0.5 | 2018-08-29 | 2018-09-06 | 2018-08-31 |  |  | 1 | 1
Shifts | G100-1GSS(1/3) | 616831 | 30 | 30 | 0.75643 | 14 | 2 | 4.1429 | 1 | G100-1GSS-BLNK | NA | 3.53 |  | 30 |  | 0.5 | 2018-05-01 | 2018-09-07 | 2018-05-15 |  |  | 1 | 1
1 | G100-1GSS(2/3) | 616831 | 30 | 30 |  | 14 | 2 | 4.1429 | 1 | G100-1GSS(1/3) | NA |  |  |  |  | 0.5 | 2018-05-01 | 2018-09-10 | 2018-05-15 |  |  | 1 | 1
2018-09-11
2018-09-06
CNC--Miyano 2 Jaw | G100-1GSS(3/3) | 616831 | 30 | 30 |  | 14 | 2 | 4.1429 | 1 | G100-1GSS(2/3) | NA |  |  |  |  | 1 | 2018-05-01 | 2018-09-06 | 2018-05-15 |  |  | 1 | 1
Shifts | [17 empty] | 2018-09-07
1
2018-09-06
HAAS Vertical Mill VF3 | NN38B21(3/3) | 606375 | 7000 | 4133 | 0 | 90 | 0 | 45.9222 | 6 | NN38B21(2/3) | NA |  |  | 4133 |  | 3 |  | 2018-09-06 | 2018-08-20 | running 9/5 | run 750pcs | 6
Shifts | FT10101 (3/3) | 620958 | 500 | 500 |  | 20 | 2 | 27 | 4 | FT10101 (2/3) | NA |  |  | 500 |  | 2 | 2018-08-15 | 2018-09-11 | 2018-08-28 | running 9/6 |  | 4 | 4
2 | IF5050B24(2/2) |  | 1998 | 1998 | 0 | 80 | 0 | 24.975 | 3 | IF5050B24 (1/2) | NA |  |  | 1998 |  | 1.5 | 2018-08-20 | 2018-09-13 | 2018-09-10 |  |  |  | 3
| SB2201 (3/3) | 618028 | 2300 | 2300 |  | 15 | 2 | 155.3333 | 21 | SB2201 (2/3) | NA |  |  | 2300 |  | 10.5 | 2018-10-01 | 2018-09-17 | 2018-10-15 | From H1 | run 500pcs
| SB5001 (2/2) | 617906 | 3500 | 2950 |  | 15 | 0 | 196.6667 | 26 | SB5001 (1/2) | NA |  |  | 2950 |  | 13 | 2018-10-01 | 2018-10-02 | 2018-10-08
| CY12010 (2/2) | 618552 | 2700 | 1155 |  | 40 | 0 | 28.875 | 4 | CY12010 (1/2) | NA |  |  | 1155 |  | 2 | 2018-09-01 | 2018-10-19 | 2018-09-15 |  |  |  | 4
| AP7501(3/3) | new | 3000 | 2119 | 0 | 40 | 0 | 52.975 | 7 | AP7501(3/4) | NA |  |  | 2119 |  | 3.5 | 2018-10-01 | 2018-10-23 | 2018-10-15 | Balance of previous run
| 101467-19(3/3) | 618213 | 3000 | 1700 | 0 | 46 | 0 | 36.9565 | 5 | 101467-19(2/3) | NA |  |  | 1700 |  | 2.5 | 2018-11-01 | 2018-10-29 | 2018-11-05 | Balance of previous run
| 101467-1-LF(3/3) | 618042 | 988 | 100 | 0 | 46 | 16 | 18.1739 | 2 | 101467-1-LF(2/3) | NA |  |  | 100 |  | 1 | 2018-07-10 | 2018-11-01 | 2018-07-20 | Balance of previous run |  | 2 | 2
| RMB013 | new | 100 | 100 | 0.41571 | 48 | 1 | 3.0833 | 0 | RMB001 | NA | 0.582 |  | 100 |  | 0 | 2018-07-01 | 2018-11-02 | 2018-07-30 |  |  | 0 | 0
| C3850001 (3/3) | 620955 | 600 | 600 |  | 23 | 1 | 27.087 | 4 | C3850001 (2/3) | NA |  |  | 600 |  | 2 | 2018-06-01 | 2018-11-02 | 2018-06-10 |  |  | 4 | 4
| SW3301 (2/2) | 618551 | 1500 | 928 | 0 | 15 | 0 | 61.8667 | 8 | SW3301 (1/2) | NA |  |  | 928 |  | 4 | 2018-08-01 | 2018-11-06 | 2018-08-13 |  | . | 8 | 8
| 300322 (2/2) | 618205 | 150 | 150 | 0 | 4 | 2 | 39.5 | 5 | 300322 (1/2) | NA |  |  | 150 |  | 2.5 | 2018-09-04 | 2018-11-12 | 2018-09-24 |  |  |  | 5
| VRGSS12501 (3/3) | 611596 | 50 | 50 |  | 16 | 2 | 5.125 | 1 | VRGSS12501 (2/3) | NA |  |  | 50 |  | 0.5 | 2018-08-15 | 2018-11-15 | 2018-09-01 | From Cobra |  | 1 | 1
| 104856-2 (3/4) | 621125 | 1250 | 1250 |  | 25 | 0.5 | 50.5 | 7 | 104856-2 (2/4) | NA |  |  | 1250 |  | 3.5 | 2018-09-02 | 2018-11-16 | 2018-09-17 | From B/S Ultramatic |  |  | 7
| 102095-2 (3/3) | new | 1100 | 1100 |  | 38 | 3 | 31.9474 | 4 | 102095-2 (2/3) | NA |  |  | 1100 |  | 2 | 2018-10-01 | 2018-11-22 | 2018-10-15 | From B/S Ultramatic
| FT10501(2/2) | 616257 | 3200 | 2800 |  | 24 | 1 | 117.6667 | 16 | FT10501(1/2) | NA |  |  | 2800 |  | 8 | 2018-10-06 | 2018-11-26 | 2018-10-26 | Balance of previous run
| SB7501 (2/2) | 618347 | 1000 | 1000 |  | 15 | 2 | 68.6667 | 9 | SB7501 (1/2) | NA |  |  | 1000 |  | 4.5 | 2018-10-02 | 2018-12-06 | 2018-10-16
| 106215-7 | new | 100 | 100 | 0.094514 | 16 | 2 | 8.25 | 1 | 106215-999 | NA | 0.13232 |  | 100 |  | 0.5 | 2018-09-04 | 2018-12-13 | 2018-09-24 |  |  |  | 1
| 183434 | 611850 | 5700 | 3500 | 0 | 44 | 0 | 79.5455 | 11 | 109784-10 | NA |  |  | 3500 |  | 5.5 | 2018-10-02 | 2018-12-14 | 2018-10-16 | Balance of previous run
2018-09-06
HAAS Vertical Mill VF4 | 2211-2-1/4-0 | 620964 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0 |  | 2 | 2018-08-29 | 2018-09-06 | 2018-09-10 | job out 9/4 |  |  | 0
Shifts | 2211-4-1/4-0 | 620966 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0 |  | 2 | 2018-08-29 | 2018-09-10 | 2018-09-10 | job out 9/4 |  |  | 0
2 | 2211-6-1/4-0 | 620970 | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0 |  | 2 | 2018-08-29 | 2018-09-12 | 2018-09-10 | job out 9/4 |  |  | 0
| 2813-6-1/4-0 | 620973 | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0 |  | 2 | 2018-08-29 | 2018-09-14 | 2018-09-10 | job out 9/5 |  |  | 0
| 2813-8-1/4-0 | 620979 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0 |  | 2 | 2018-08-29 | 2018-09-18 | 2018-09-10 | job out 9/5 |  |  | 0
| 2813-9-1/4-0 | 620982 | 3 | 3 | 0.12552 | 2 | 2 | 3.5 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 3 |  | 2 | 2018-08-29 | 2018-09-20 | 2018-09-10 | job out 9/5\6 |  |  | 0
| 2813-12-1/4-0 | 620984 | 9 | 9 | 0.37657 | 2 | 2 | 6.5 | 1 | 2813-A-BLNK | NA | 5.8577 |  | 9 |  | 2 | 2018-08-29 | 2018-09-24 | 2018-09-10 | running 9/6 |  |  | 1
| S144S144003 (2/2) | 618033 | 3000 | 3000 |  | 5 | 1 | 601 | 80 | S144S144003 (1/2) | NA |  |  | 3000 |  | 2 | 2018-08-01 | 2018-09-26 | 2018-08-16 | From A6 | run 600pcs | 80 | 80
| SW1001 (2/2) | 617663 | 5000 | 1300 | 0 | 15 | 0 | 86.6667 | 12 | SW1001 (1/2) | NA |  |  | 1300 |  | 2 | 2018-08-15 | 2018-09-28 | 2018-08-30 | Balance of previous run |  | 12 | 12
| SW1201 (2/2) | 618041 | 750 | 500 | 0 | 15 | 8 | 41.3333 | 6 | SW1201 (1/2) | NA |  |  | 500 |  | 2 | 2018-07-10 | 2018-10-02 | 2018-07-20 | Balance of previous run |  | 6 | 6
| EH38001 | rework | 500 | 500 | [11 empty] | 2 |  | 2018-10-04
| CRV7510(2/2) | 616921 | 1500 | 1500 |  | 22 | 8 | 76.1818 | 10 | CRV7510(1/2) | NA |  |  | 1500 |  | 2 | 2018-09-01 | 2018-10-08 | 2018-09-15 | From H3 |  |  | 10
2018-10-10
2018-10-10
2018-09-06
CNC--Bridgeport Mill | 42412 (2/2) | 617850 | 11000 | 5400 |  | 54 | 0 | 100 | 13 | 42412(1/2) | NA |  |  | 5400 |  | 6.5 | 2018-08-01 | 2018-09-06 | 2018-08-13 | pullo out |  | 13 | 13
Shifts | 79390 (2/2) | 618023 | 18000 | 9453 |  | 112 | 0 | 84.4018 | 11 | 79390 (1/2) | NA |  |  | 9453 |  | 5.5 | 2018-09-01 | 2018-09-17 | 2018-09-15 | running 8/30 |  |  | 11
2 | 42412 (2/2) | 617850 | 11000 | 5400 |  | 54 | 0 | 100 | 13 | 42412(1/2) | NA |  |  | 5400 |  | 6.5 | 2018-09-01 | 2018-09-25 | 2018-09-15 | Balance of previous run |  |  | 13
| CY11101(2/2) | 616997 | 2086 | 2086 |  | 54 | 1 | 39.6296 | 5 | CY11101(1/2) | NA |  |  | 2086 |  | 2.5 | 2018-11-01 | 2018-10-04 | 2018-12-01
2018-10-09
| 42412 (2/2) | new | 16000 | 16000 |  | 54 | 2 | 298.2963 | 40 | 42412(1/2) | NA |  |  | 16000 |  |  | 2018-10-20 | 2018-10-19 | 2018-10-26
SECONDARY OPS SCHEDULE | [9 empty] | 2018-09-06
MACHINE | PART NUMBER | PACKET MADE | QTY BAL DUE | QTY BAL DUE |  | RATE PCS/HR | SETUP TIME | TOTAL HRS | TOTAL SHIFTS | MAKE FROM PART NUMBER | ROUGH WGT EA |  |  | MATL/PCS NEEDED |  | DAYS | ORIG STRT DATE | SCH'D START DATE | ORIG DUE DATE |  |  | 2nd Op Shifts Behind | 2nd Op 2 Weeks
[18 empty] | 2018-09-06 |  |  |  | 59 | 136
GOSS #1
Shifts
0
[18 empty] | 2018-09-06 |  | job out 8/31
B&S-17 (HAND) | Top Holes | 9-3-D-BLNK | [13 empty] | 2 |  | 2018-09-06
Shifts | RCF007-P | Rework | 2827 | 2827 | [11 empty] | 2 |  | 2018-09-10 |  | waiting on tooling
1 | G125-21SS | Rework | 42 | 42 | [11 empty] | 2 |  | 2018-09-12 |  | job out
Top Holes
2018-09-06
B&S-18 (BAR) | M130 | Sample | 4000 | 0 | [5 empty] | A02001-0026 | [5 empty] | 3 | 2018-08-27 | 2018-09-06 | 2018-08-31 | job out 9/4 |  | 0 | 0
Shifts | 30486A | Sample | 750 | 700 | [5 empty] | A02002-0018 | [6 empty] | 2018-08-28 | 2018-09-11 | 2018-08-31 | running 9/5 |  | 0 | 0
1 | B3222-3 (1/2) | 619633 | 2500 | 2500 | 0.60018 | 13 | 1.5 | 193.8077 | 26 | A02001-0024 | 0.1426 | 0.03361 | 19.53 | 356.5 | 18.254 | 26 | 2018-08-01 | 2018-09-11 | 2018-08-27 |  |  | 26 | 26
| 104856-2 (1/4) | 621125 | 1250 | 1250 | 0.53705 | 120 | 16 | 26.4167 | 4 | A02002-0024 | 0.2116 | 0.06015 | 21.54 | 264.5 | 12.2795 | 4 | 2018-09-02 | 2018-10-17 | 2018-09-17 |  |  |  | 4
| B3451-1 | new | 300 | 300 | 0.077786 | 144 | 16 | 18.0833 | 2 | A02002-0014 | 0.0801 | 0.0363 | 7.33 | 24.03 | 3.2783 | 2 | 2018-09-02 | 2018-10-23 | 2018-09-17 |  |  |  | 2
| G200-8SS (1/2) | new | 1000 | 1000 | 0.81429 | 10 | 3 | 103 | 14 | A06201-0012 | 0.1462 | 0.114 | 4.65 | 146.2 | 31.4409 | 14 | 2018-09-01 | 2018-10-25 | 2018-09-24 |  |  |  | 14
| B3453-1 | 619233 | 2250 | 2250 | 1.5075 | 332 | 16 | 22.7771 | 3 | A02002-0022 | 0.2336 | 0.0938 | 18.1 | 525.6 | 29.0387 | 3 | 2018-10-01 | 2018-11-14 | 2018-10-15
| 102095-2 (1/3) | new | 1100 | 1100 | 0.51071 | 360 | 16 | 19.0556 | 3 | A02002-0024 | 0.1734 | 0.065 | 21.54 | 190.74 | 8.8552 | 3 | 2018-10-01 | 2018-11-19 | 2018-10-15
| A5012 (1/2) | new | 2000 | 2000 | 2.7043 | 96 | 8 | 28.8333 | 4 | A02001-0020 | 0.2536 | 0.1893 | 13.56 | 507.2 | 37.4041 | 4 | 2018-10-01 | 2018-11-22 | 2018-10-15
| G150-8SS (1/2) | new | 2000 | 2000 | 1.3429 | 45 | 4 | 48.4444 | 6 | A06201-0012 | 0.1166 | 0.094 | 4.65 | 233.2 | 50.1505 | 6 | 2018-10-01 | 2018-11-28 | 2018-10-22
| G100-8SS (1/2) | new | 350 | 350 | 0.1375 | 45 | 4 | 11.7778 | 2 | A06201-0010 | 0.0703 | 0.055 | 3.23 | 24.605 | 7.6176 | 2 | 2018-10-01 | 2018-12-06 | 2018-10-22
| 106273-1 | STND | 300 | 300 | 0.21107 | 12 | 8 | 33 | 4 | A06202-0022 | 0.1276 | 0.0985 | 16.7 | 38.28 | 2.2922 | 4 | 2018-10-02 | 2018-12-10 | 2018-10-23
| 106273-2 | STND | 300 | 300 | 0.32571 | 12 | 8 | 33 | 4 | A06202-0028 | 0.2434 | 0.152 | 27.89 | 73.02 | 2.6181 | 4 | 2018-10-03 | 2018-12-14 | 2018-10-24
2018-12-20
2018-12-20
2018-09-06
B&S-#2 Ultramatic w/Lipe | R450-1-8 | 620299 | 2500 | 274 | 1.89 | 96 | 0 | 2.8542 | 0 | A02001-0008 | 0.1205 | 0.12 | 2.17 | 33.017 | 15.2152 | 0 | 2018-08-20 | 2018-09-06 | 2018-08-25 | running 8/24 |  | 0 | 0
Shifts | R450-1-12 | 620364 | 1500 | 1500 | 0 | 96 | 4 | 19.625 | 3 | A02001-0008 | 0.1807 | 0.18052 | 2.17 | 271.05 | 124.9078 | 3 | 2018-09-10 | 2018-09-06 | 2018-10-01 |  |  |  | 3
1 | R431-10 (1/2) | 620671 | 1800 | 1800 | 0 | 96 | 4 | 22.75 | 3 | A02001-0008 | 0.147 | 0.147 | 2.17 | 264.6 | 121.9355 | 3 | 2018-09-10 | 2018-09-11 | 2018-10-01 |  |  |  | 3
| R433-12 | R&D | [15 empty] | 2018-09-14
| R452-12 | R&D
2018-09-06
B&S-#3 Ultramatic | IL20014(2/2) | 618206 | 3000 | 0 |  | 60 | 0 | 0 | 0 | IL20014(1/2) | NA |  |  | 0 |  | 0 | 2018-08-01 | 2018-09-06 | 2018-08-15 | job out 8/30 |  | 0 | 0
Shifts | 106272-2 | 620612 | 50 | 0 | 0 | 57 | 0 | 0 | 0 | 106273-1 | NA | 0.0985 |  | 0 |  | 0 | 2018-09-01 | 2018-09-06 | 2018-09-17 | job out 8/31 |  |  | 0
1 | FC7504 (2/2) | 614311 | 4000 | 2678 |  | 192 | 0 | 13.9479 | 2 | FC7504(1/2) | NA |  |  | 2678 |  | 2 | 2018-09-01 | 2018-09-06 | 2018-09-15 | running 9/4 |  |  | 2
| 104856-2 (2/4) | 621125 | 1250 | 1250 |  | 42 | 18 | 47.7619 | 6 | 104856-2 (1/4) | NA |  |  | 1250 |  | 6 | 2018-09-02 | 2018-09-20 | 2018-09-17 | From B/S 18 |  |  | 6
| 102095-2 (2/3) | new | 1100 | 1100 |  | 131 | 4 | 12.3969 | 2 | 102095-2 (1/3) | NA |  |  | 1100 |  | 2 | 2018-10-01 | 2018-09-28 | 2018-10-15
| B3222-3 (2/2) | 619633 | 2500 | 2500 |  | 64 | 12 | 51.0625 | 7 | B3222-3 (1/2) | NA |  |  | 2500 |  | 7 | 2018-08-01 | 2018-10-02 | 2018-08-27 |  |  | 7 | 7
| G200-8SS (2/2) | new | 1000 | 1000 |  | 10 | 3 | 103 | 14 | G200-8SS (1/2) | NA |  |  | 1000 |  | 14 | 2018-09-01 | 2018-10-11 | 2018-09-24 |  |  |  | 14
| G150-8SS (2/2) | new | 2000 | 2000 |  | 45 | 4 | 48.4444 | 6 | G150-8SS (1/2) | NA |  |  | 2000 |  | 6 | 2018-10-01 | 2018-10-31 | 2018-10-22
| G100-8SS (2/2) | new | 350 | 350 |  | 45 | 4 | 11.7778 | 2 | G100-8SS (1/2) | NA |  |  | 350 |  | 2 | 2018-10-01 | 2018-11-08 | 2018-10-22
| TC6301(2/2) | 620550 | 18000 | 18000 |  | 120 | 4 | 154 | 21 | TC6301(1/2) | NA |  |  | 18000 |  | 21 | 2018-08-20 | 2018-11-12 | 2018-08-27 |  |  | 21 | 21
| M40070(2/2) | 621198 | 12000 | 12000 |  | 249 | 4 | 52.1928 | 7 | M40070(1/2) | NA |  |  | 12000 |  | 7 | 2018-10-01 | 2018-12-11 | 2018-10-15
2018-12-20
|  | . | [15 empty] | 2018-09-06
4 WAY-MS2 #471 | P25031 | 620083 | 2050 | 608 | 0.2901 | 150 | 0 | 4.0533 | 1 | P25031-10 | NA | 0.0668 |  | 608 |  | 1 | 2018-08-10 | 2018-09-06 | 2018-08-30 | running 9/6 |  | 1 | 1
Shifts | [17 empty] | 2018-09-07
1
2018-09-06
4 WAY-MS3 # 472
Shifts
1
2018-09-06
4 WAY-MS4 #473
Shifts
0
2018-09-06
HARDING LATHE-0467 | C3000-3-6 | 617914 | 3000 | 1484 | 0 | 192 | 0 | 7.7292 | 1 | C3000-3-6U | NA |  |  | 1484 |  | 1 | 2018-05-01 | 2018-09-06 | 2018-05-21 | running 9/4 |  | 1 | 1
Shifts | C3000-3-3.4 | 618558 | 150 | 150 | 0.017679 | 192 | 1 | 1.7812 | 0 | C3000-3-3.4U | NA | 0.0165 |  | 150 |  | 0 | 2018-06-01 | 2018-09-07 | 2018-06-18 |  |  | 0 | 0
1 | C3000-3-4.600 (2/2) | 616828 | 150 | 150 |  | 192 | 1 | 1.7812 | 0 | C3000-3-4.600 (1/2) | NA |  |  | 150 |  | 0 | 2018-06-01 | 2018-09-07 | 2018-06-18 |  |  | 0 | 0
2018-09-07
2018-09-06
HARDING LATHE-0466 | C3838005-3 | 619676 | 3000 | 2200 | 0.018621 | 240 | 0 | 9.1667 | 1 | C3838005 | NA | 0.001185 |  | 2200 |  | 1 | 2018-09-01 | 2018-09-06 | 2018-09-17 | ready to run 8/30 |  |  | 1
Shifts | [17 empty] | 2018-09-07
0
2018-09-06
LATHE-0468
Shifts
0
2018-09-06
NOZZLE LATHE | J3 | 621804 | 20 | [6 empty] | J1 | [7 empty] | 2018-09-06 |  | running 9/6
Shifts | JR3/4 | 621805 | 5 | [6 empty] | JR-BLNK | [7 empty] | 2018-09-07
1 | C5A | 621806 | 2 | [6 empty] | CA-BLNK | [7 empty] | 2018-09-11
| C6A | 621807 | 2 | [6 empty] | CA-BLNK | [7 empty] | 2018-09-11
| C8A | 621808 | 2 | [6 empty] | CA-BLNK | [7 empty] | 2018-09-11
| G15A | 621809 | 2 | [6 empty] | GA-BLNK | [7 empty] | 2018-09-11
| JR2 | 621810 | 30 | [6 empty] | JR-BLNK | [7 empty] | 2018-09-11
All w/o's should | ER12 | NON STD | 5 | [6 empty] | ER-BLNK | [7 empty] | 2018-09-12
be made as "NON-STD" | J8 | HOLD | 20 | [6 empty] | J-BLNK | [7 empty] | 2018-09-12
DRILL PRESS-0062 | A5128 (2/2) | 616272 | 2000 | 2000 |  | 240 | 0 | 8.3333 | 1 | A5128 (1/2) | NA | 0.0271 |  | 2000 |  | 1 | 2018-07-01 | #REF! | 2018-07-15 | ready to run 8/30 |  | 1 | 1
(5/8 Roberts Jobs) | [17 empty] | #REF!
Shifts | A5012 (2/2) | new | 2000 | 2000 |  | 240 | 1 | 9.3333 | 1 | A5012 (1/2) | NA |  |  | 2000 |  | 1 | 2018-10-01 | 2018-11-28 | 2018-10-15 | from B/S 18
1
2018-09-06
DRILL PRESS-0063 | R431-10 (2/2) | 620671 | 1800 | 1800 |  | 128 | 0.5 | 14.5625 | 2 | R431-10 (1/2) | NA |  |  | 1800 |  | 2 | 2018-09-10 | 2018-09-06 | 2018-10-01 | from B/S with Lipe |  |  | 2
Shifts | [17 empty] | 2018-09-10
0
2018-09-06
DRILL PRESS-0462 | 104670-1 | 619038 | 3200 | 1397 | 0.33169 | 180 | 0 | 7.7611 | 1 | 104670U-1 | NA | 0.03324 |  | 1397 |  | 1 | 2018-09-01 | 2018-09-06 | 2018-09-15 | ready to run 8/27 |  |  | 1
Shifts | B3056-1 | 619635 | 12000 | 12000 | 0.25063 | 240 | 1 | 51 | 7 | B3056-1U | NA | 0.002924 |  | 12000 |  | 7 | 2018-10-01 | 2018-09-07 | 2018-10-15
0 | [17 empty] | 2018-09-18
2018-09-06
MILL-0469
Shifts
0
2018-09-06
ROLL THREADER-0053 | A4035-1 (2/2) | 619480 | 150 | 0 |  | 192 | 0 | 0 | 0 | A4035-1 (1/2) | NA |  |  | 0 |  | 0 | 2018-08-01 | 2018-09-06 | 2018-08-07 | job out |  | 0 | 0
Shifts | C3000-1-2.4 | 621103 | 350 | 0 | 0 | 192 | 0 | 0 | 0 | C3000-1-2.4U | NA | 0.010088 |  | 0 |  | 0 | 2018-08-30 | 2018-09-06 | 2018-08-30 | job out 8/30 |  | 0 | 0
1 | A5037-1-6 | 619636 | 500 | 500 | 0.19821 | 192 | 0.75 | 3.3542 | 0 | A5037-1-6U | NA | 0.0555 |  | 500 |  | 0 | 2018-09-01 | 2018-09-06 | 2018-09-15 |  |  |  | 0
2018-09-06
2018-09-06
BRIDGEPORT DRILL PRESS-0100 | R1006-2 | 616824 | 15 | 15 |  | 25 | 0 | 0.6 | 0 | R1006-LF | NA |  |  | 15 |  | 0 | 2018-04-30 | 2018-09-06 | 2018-05-15 | job out 8/31 |  | 0 | 0
Shifts | 300341 | 619737 | 50 | 50 | 0.014343 | 4 | 0.4 | 12.9 | 2 | 300340 | NA | 0.04016 |  | 50 |  | 2 | 2018-08-20 | 2018-09-06 | 2018-08-25 |  |  | 2 | 2
1 | 104524-5 | 615571 | 400 | 200 | 0.24571 | 65 | 0 | 3.0769 | 0 | 104524-2-200 | NA | 0.172 |  | 200 |  | 0 | 2018-08-15 | 2018-09-06 | 2018-09-04 | running 9/5 |  | 0 | 0
2018-09-06
CAGE DIE HEAD | R452-16(2/2) | 620365 | 300 | 300 |  | 144 | 0 | 0 | 0 | R452-16(1/2) | NA |  |  | 0 |  | 0 | 2018-09-01 | 2018-09-06 | 2018-09-10 | job out 9/4 |  |  | 0
Shifts
0
`
2018-09-06
CUT SAW-0067 | C3000-1-2.4U | 621108 | 350 | 0 | 0 | 192 | 0 | 0 | 0 | C3000-1-3U | NA | 0.010088 |  | 0 |  | 0 | 2018-08-30 | 2018-09-06 | 2018-08-30 | job out 8/30 |  | 0 | 0
Shifts | R452-16(1/2) | 620365 | 300 | 0 | 0 | 144 | 0 | 2.0833 | 0 | A02001-0012 | 0.54 | 0.052 | 4.88 | 162 | 33.1967 | 0 | 2018-09-01 | 2018-09-06 | 2018-09-10 | job out 8/30 |  |  | 0
0 | [17 empty] | 2018-09-06
2018-09-06
DRILL PRESS TAPPER-0077 | 104676-15 | 619483 | 2500 | 2500 | 0.125 | 192 | 0 | 13.0208 | 2 | 104676U-15 | NA | 0.007 |  | 2500 |  | #DIV/0! | 2018-10-10 | 0 | 2018-11-05 | ready to run 8/28
Shifts
0
2018-09-06
FLOAT TAPPER-0055
(Small Floats)
Shifts
0
2018-09-06
Auto MILL-0469 | SB7515(2/2) | 618560 | 6000 | 4500 |  | 67 | 0.5 | 67.6642 | 9 | SB7515(1/2) | NA |  |  | 4500 |  | 9 | 2018-09-01 | 2018-09-06 | 2018-09-17 | From A3 |  |  | 9
Shifts | LH50011 (2/2) | 612376 | 6000 | 6000 |  | 56 | 2 | 109.1429 | 15 | LH50011 (1/2) | 1 |  |  | 0 |  | 15 | 2018-09-01 | 2018-09-19 | 2018-09-17 | From D6 |  |  | 15
1 | 104856-2 (4/4) | 621125 | 1250 | 1250 |  | 192 | 0.5 | 7.0104 | 1 | 104856-2 (3/4) | NA |  |  | 1250 |  | 1 | 2018-09-02 | 2018-10-10 | 2018-09-17 | From VF3 |  |  | 1
2018-10-11
Color Codes
New Part
Material in House
Material 1 week
Material 2 weeks
Material partial in house
Needs Machine Analysis Completed
Hard Orders
Needs Reviewed
Gross & Scrap Verified- in BOM
Cycle time Verified
Vefication that BOM matches P/N Secondary schedule Only
Citizen | 3-2-3 |  | 0 | 0 | 0 | 77 | 8 | 8 | 1 | A02071-0020 | 0.0956 | 0.0376 | 13.56 | 0 | 0
Citizen | 3-3-2 |  | 0 | 0 | 0 | 83 | 2 | 2 | 0 | A02071-0020 | 0.091 | 0.0305 | 13.56 | 0 | 0
Citizen | 4-3-2 |  | 0 | 0 | 0 | 79 | 2 | 2 | 0 | A02071-0020 | 0.1003 | 0.04355 | 13.56 | 0 | 0 | Family 2
Citizen | 5-3-2 |  | 0 | 0 | 0 | 48 | 1 | 1 | 0 | A02071-0020 | 0.091 | 0.06 | 13.56 | 0 | 0
Citizen | 5-4-2 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0028 | 0.258 | 0.08 | 26.58 | 0 | 0
Citizen | 7-3-2 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0028 | 0.361 | 0.23 | 26.58 | 0 | 0
Citizen | 7-4-2 |  | 0 | 0 | 0 | 46 | 1 | 1 | 0 | A02071-0028 | 0.281 | 0.25 | 26.58 | 0 | 0
Citizen | 3-3-3 |  | 0 | 0 | 0 | 65 | 1.5 | 1.5 | 0 | A02071-0020 | 0.0993 | 0.028 | 13.56 | 0 | 0
Citizen | 4-3-3 |  | 0 | 0 | 0 | 66 | 1 | 1 | 0 | A02071-0020 | 0.1003 | 0.039 | 13.56 | 0 | 0 | Family 2
Citizen | 5-3-3 |  | 0 | 0 | 0 | 13 | 3 | 3 | 0 | A02071-0020 | 0.099 | 0.067 | 13.56 | 0 | 0
Citizen | 5-4-3 |  | 0 | 0 | 0 | 51 | 1 | 1 | 0 | A02071-0028 | 0.528 | 0.104 | 26.58 | 0 | 0
Citizen | 7-3-3 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0028 | 0.313 | 0.24 | 26.58 | 0 | 0
Citizen | 7-4-3 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0028 | 0.3067 | 0.1973 | 26.58 | 0 | 0
Citizen | 3-3-4 |  | 0 | 0 | 0 | 56 | 2 | 2 | 0 | A02071-0022 | 0.1343 | 0.038 | 16.41 | 0 | 0
Citizen | 4-2.5-6 | Non-Stnd | 0 | 0 | 0 | 45 | 1 | 1 | 0 | A02071-0022 | 0.1618 | 0.07 | 16.41 | 0 | 0
Citizen | 4-2.5-8 |  | 0 | 0 | 0 | 45 | 1 | 1 | 0 | A02071-0026 | 0.257 | 0.103 | 22.95 | 0 | 0
Citizen | 4-3-4 |  | 0 | 0 | 0 | 45 | 1 | 1 | 0 | A02071-0026 | 0.243 | 0.079 | 22.95 | 0 | 0 | Family 1
Hass Vertical Mill VF3 | 4-3-5 | Non-Stnd | 0 | 0 | 0 | 45 | 1 | 1 | 0 | 4-3-B-BLNK | NA | 0.0788
Citizen | 4-4-2 |  | 0 | 0 | 0 | 58 | 1 | 1 | 0 | A02071-0026 | 0.239 | 0.0859 | 22.95 | 0 | 0
Citizen | 4-4-3 |  | 0 | 0 | 0 | 59 | 3 | 3 | 0 | A02071-0026 | 0.22 | 0.039 | 22.95 | 0 | 0
Citizen | 4-4-4 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0026 | 0.239 | 0.0726 | 22.95 | 0 | 0
Citizen | 5-3-4 |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0026 | 0.249 | 0.105 | 22.95 | 0 | 0
Citizen | 5-4-4 |  | 0 | 0 | 0 | 37 | 1 | 1 | 0 | A02071-0028 | 0.259 | 0.11 | 26.58 | 0 | 0
Citizen | 7-3-4 |  | 0 | 0 | 0 | 41 | 1 | 1 | 0 | A02071-0028 | 0.361 | 0.23 | 26.58 | 0 | 0
Citizen | 7-4-4 |  | 0 | 0 | 0 | 46 | 2 | 2 | 0 | A02071-0028 | 0.3079 | 0.1913 | 26.58 | 0 | 0
Citizen | 3-3-6 |  | 0 | 0 | 0 | 31 | 4 | 4 | 1 | A02071-0026 | 0.222 | 0.02 | 22.95 | 0 | 0
Citizen | 3-3-8 |  | 0 | 0 | 0 | 31 | 4 | 4 | 1 | A02071-0028 | 0.267 | 0.04 | 26.58 | 0 | 0
Citizen | 4-3-6 |  | 0 | 0 | 0 | 32 | 1.5 | 1.5 | 0 | A02071-0026 | 0.243 | 0.0734 | 22.95 | 0 | 0 | Family 1
Citizen | 5-3-6 |  | 0 | 0 | 0 | 43 | 1 | 1 | 0 | A02071-0026 | 0.249 | 0.0933 | 22.95 | 0 | 0
Citizen | 7-3-6 |  | 0 | 0 | 0 | 34 | 2.5 | 2.5 | 0 | A02071-0028 | 0.36 | 0.23 | 26.58 | 0 | 0
Citizen | 3-3-8 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0028 | 0.267 | 0.071 | 26.58 | 0 | 0
Citizen | 4-3-8 |  | 0 | 0 | 0 | 26 | 2 | 2 | 0 | A02071-0028 | 0.292 | 0.07 | 26.58 | 0 | 0
Citizen | 5-3-8 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0028 | 0.34 | 0.09 | 26.58 | 0 | 0
Cobra | 40051 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | A02002-0028 | 0.2634 | 0.1484 | 29.31 | 0 | 0
Drill Press | 42395 (2/2) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | 42395(1/2) | NA |  |  | 0
Bridgeport CNC | 42412 (2/2) |  | 0 | 0 |  | 54 | 2 | 2 | 0 | 42412(1/2) | NA |  |  | 0
Citizen | 447667 |  | 0 | 0 | 0 | 14 | 8 | 8 | 1 | A06001-0040 | 0.2134 | 0.06 | 50.08 | 0 | 0 |  |  |  |  | 2018
Citizen | 447676 |  | 0 | 0 | 0 | 18 | 8 | 8 | 1 | A19101-0028 | 0.0576 | 0.0376 | 8.485 | 0 | 0 |  |  |  |  | 2018
Citizen | 447681 |  | 0 | 0 | 0 | 5 | 8 | 8 | 1 | A02001-0016 | 0.0347 | 0.014 | 8.68 | 0 | 0 |  |  |  |  | 2018
Bridgeport CNC/VF3 | 79390 (2/2) |  | 0 | 0 |  | 112 | 2 | 2 | 0 | 79390 (1/2) | NA |  |  | 0
Haas Vertical Mill VF3 | 11-8-4 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 11-6-C-BLNK | NA | 0.99 |  | 0
Haas Vertical Mill VF3 | 11-8-5 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 11-6-C-BLNK | NA | 0.99 |  | 0
Haas Vertical Mill VF3 | 11-8-6 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 11-6-C-BLNK | NA | 0.99 |  | 0
Haas Vertical Mill VF3 | 11-8-7 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 11-6-C-BLNK | NA | 0.99 |  | 0
Haas Vertical Mill VF3 | 11-8-8 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 11-6-C-BLNK | NA | 0.99 |  | 0
Haas Vertical Mill VF3 | 109784 | 2016 | 0 | 0 | 0 | 32 | 2 | 2 | 0 | 109784-10 | NA | 0.589 |  | 0 | [5 empty] | 2016
Kingsbury | 109784 | obsolete routing | 0 | 0 | 0 | 50 | 1 | 1 | 0 | 109784-10 | NA | 0.589 |  | 0
Goss#2 | 183434 | obsolete routing | 0 | 0 | 0 | 44 | 2 | 2 | 0 | 109784-10 | NA | 0.565 |  | 0
Haas Vertical Mill VF3 | 183434 | 2016 | 0 | 0 | 0 | 44 | 2 | 2 | 0 | 109784-10 | NA | 0.565 |  | 0 | [5 empty] | 2016
Goss/Kingsbury | 183434 | obsolete routing | 0 | 0 | 0 | 44 | 2 | 2 | 0 | 109784-10 | NA | 0.565 |  | 0
T-42 | 200195 (1/3) |  | 0 | 1 | 0.0041286 | 1 | 3 | 4 | 1 | A06501-0048 | 2.4482 | 0.578 | 72.1 | 2.4482 | 0.033956
T-42 | 200195 (2/3) |  | 0 | 2 |  | 1 | 12 | 14 | 2 | 200195 (1/3) | NA |  |  | 2
T-42 | 200195 (3/3) |  | 0 | 3 |  | 1 | 12 | 15 | 2 | 200195 (2/3) | NA |  |  | 3
T-42 | 300322 (1/2) |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | A06153-0016 | 0.1018 | 0.0517 | 10.52 | 0 | 0
Hass Vertical Mill VF3 | 300322 (2/2) |  | 0 | 0 |  | 4 | 2 | 2 | 0 | 300322 (1/2) | NA |  |  | 0
Bridgeport Drill Press | 300341 | STND | 0 | 0 | 0 | 4 | 0.4 | 0.4 | 0 | 300340 | NA | 0.04016 |  | 0
Bridgeport CNC Mill | 300341 | Non Stnd | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 300340 | NA | 0.04016 |  | 0
Bridgeport Drill Press | 300346 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 300322 | NA | 0.04016 |  | 0
B&S18 | 301104 |  | 0 | 0 | 0 | 214 | 8 | 8 | 1 | A09002-0014 | 0.004 | 0.001 |  | 0
Drill Press | 427178 (2/2) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | 427178 (1/2) | NA |  |  | 0
Citizen | .430-3-2 |  | 0 | 0 | 0 | 55 | 1.5 | 1.5 | 0 | A02071-0024 | 0.185 | 0.0833 | 19.53 | 0 | 0
Citizen | .430-3-3 |  | 0 | 0 | 0 | 60 | 1 | 1 | 0 | A02071-0024 | 0.123 | 0.065 |  | 0
Citizen | .430-3-4 |  | 0 | 0 | 0 | 46 | 1 | 1 | 0 | A02071-0026 | 0.224 | 0.07 |  | 0
Okuma-Genos | .430-3-5 |  | 0 | 0 | 0 | 55 | 1.5 | 1.5 | 0 | A02071-0026 | 0.224 | 0.071 | 22.95 | 0 | 0
Citizen | .430-3-6 |  | 0 | 0 | 0 | 33 | 1 | 1 | 0 | A02071-0026 | 0.322 | 0.0689 |  | 0
Citizen | .430-3-8 |  | 0 | 0 | 0 | 29 | 1 | 1 | 0 | A02071-0028 | 0.292 | 0.0634 |  | 0
Citizen | .430-4-2 |  | 0 | 0 | 0 | 63 | 3 | 3 | 0 | A02071-0024 | 0.1935 | 0.0676 |  | 0
Citizen | .430-4-3 |  | 0 | 0 | 0 | 58 | 1 | 1 | 0 | A02071-0026 | 0.218 | 0.08 | 22.95 | 0 | 0
Citizen | .430-4-4 |  | 0 | 0 | 0 | 50 | 2.5 | 2.5 | 0 | A02071-0026 | 0.222 | 0.07 | 22.95 | 0 | 0
Okuma-Genos | .430-5-3 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0028 | 0.2719 | 0.064 | 26.58 | 0 | 0
H3 | .430-A-BLNK |  | 0 | 0 | 0 | 56 | 1 | 1 | 0 | A02071-0028 | 0.301 | 0.101 |  | 0
Citizen | .430-A-BLNK |  | 0 | 0 | 0 | 90 | 1 | 1 | 0 | A02071-0028 | 0.225 | 0.101 |  | 0
Citizen | .430-B-BLNK |  | 0 | 0 | 0 | 58 | 1 | 1 | 0 | A02071-0026 | 0.224 | 0.094 | 22.95 | 0 | 0
Citizen | .430-C-BLNK |  | 0 | 0 | 0 | 18 | 2 | 2 | 0 | A02071-0028 | 0.301 | 0.097 |  | 0
H3 | .430-E-BLNK |  | 0 | 0 | 0 | 58 | 1 | 1 | 0 | A02071-0026 | 0.218 | 0.08 |  | 0
H3 | .535-3-A-BLNK |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0040 | 0.854 | 0.29 |  | 0
Ganesh CNC | 0010-92-C |  | 0 | 0 | 0 | 18 | 16 | 16 | 2 | A02001-0040 | 1.0617 | 0.585 | 54.25 | 0 | 0
Cobra | 0012-85-C | Backup 2nd op from Hydro | 0 | 0 |  | 18 | 3 | 3 | 0 | 0012-85-C-10 | NA |  |  | 0
Ganesh CNC | 0012-85-C |  | 0 | 0 | 0 | 15 | 16 | 16 | 2 | A02031-0040 | 0.7091 | 0.23145 | 54.25 | 0 | 0
Ganesh CNC | 0014-01-C |  | 0 | 0 | 0 | 11 | 2 | 2 | 0 | A02001-0040 | 0.6479 | 0.24365 | 54.25 | 0 | 0
Ganesh CNC | 0017-89-C |  | 0 | 0 | 0 | 270 | 32 | 32 | 4 | A02031-0040 | 0.7767 | 0.292 | 54.25 | 0 | 0
T-42 | 0042-54-C |  | 0 | 0 | 0 | 8 | 6 | 6 | 1 | A06101-0034 | 0.4655 | 0.22375 | 37.29 | 0 | 0
Citizen | 0042-55-C |  | 0 | 0 | 0 | 9 | 6.5 | 6.5 | 1 | A06101-0013 | 0.1136 | 0.037 | 5.29 | 0 | 0
Citizen | 0042-56-C |  | 0 | 0 | 0 | 14 | 4 | 4 | 1 | A06101-0016 | 0.0579 | 0.0295 | 8.01 | 0 | 0
T-42 | 0042-64-C |  | 0 | 0 | 0 | 14 | 4 | 4 | 1 | A06101-0042 | 0.7356 | 0.226 | 55.2 | 0 | 0
Citizen | 0042-65-C |  | 0 | 0 | 0 | 12 | 6 | 6 | 1 | A06101-0020 | 0.244 | 0.121 | 12.52 | 0 | 0
Citizen | 0042-66-C |  | 0 | 0 | 0 | 30 | 5 | 5 | 1 | A06101-00035 | 0.0168 | 0.0036 | 3.5 | 0 | 0
Cobra | 0042-68-C |  | 0 | 0 | 0 | 16 | 2 | 2 | 0 | A05501-0028 | 0.1289 | 0.0917 | 3.71 | 0 | 0
B&S18 | 0042-69-C |  | 0 | 0 | 0 | 160 | 2 | 2 | 0 | A06101-0008 | 0.0638 | 0.0555 | 2.06 | 0 | 0
Ganesh CNC | 0043-33-C | Backup from Hydro | 0 | 0 | 0 | 16 | 16 | 16 | 2 | A02031-0060 | 1.6401 | 0.369 | 122.07 | 0 | 0
Ganesh CNC | 0043-34-C | Backup from Hydro | 0 | 0 | 0 | 16 | 16 | 16 | 2 | A02031-0040 | 0.953 | 0.472 | 54.25 | 0 | 0
Ganesh CNC | 0045-30-C | Standard | 0 | 0 | 0 | 14 | 16 | 16 | 2 | A02031-0040 | 0.6344 | 0.252 | 54.25 | 0 | 0
T-42 | 0045-30-C | Backup from Hydro | 0 | 0 | 0 | 15 | 2.5 | 2.5 | 0 | 0045-30-C-10 | NA | 0.252 |  | 0
Ganesh CNC | 0045-31-C |  | 0 | 0 | 0 | 12 | 16 | 16 | 2 | A02001-0040 | 0.525 | 0.207 | 54.25 | 0 | 0
Okuma-Genos | 0050-68-C | Standard | 0 | 0 | 0 | 26 | 16 | 16 | 2 | A02001-0040 | 0.3501 | 0.098 | 54.25 | 0 | 0
Ganesh CNC | 0050-68-C | NON STND | 0 | 0 | 0 | 26 | 16 | 16 | 2 | A02001-0040 | 0.3501 | 0.098 | 54.25 | 0 | 0
Okuma-Genos | 9-3-15 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.6703 | 0.516 | 106.33 | 0 | 0
Okuma-Genos | 11-4-15 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0064 | 2.354 | 0.081 | 138.88 | 0 | 0
Drill Press | 42395 (2/2) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | 42395 (1/2) | NA |  |  | 0
Bridgeport CNC | 42412 (2/2) |  | 0 | 0 |  | 54 | 2 | 2 | 0 | 42412 (1/2) | NA |  |  | 0
Okuma-Genos | 7-3-16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.3217 | 0.4925 | 91.68 | 0 | 0
Okuma-Genos | 11-4-16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0064 | 2.354 | 0.807 | 138.88 | 0 | 0
Okuma-Genos | 7-3-17 | Non Stnd | 0 | 0 | 0 | 14 | 1 | 1 | 0 | A02071-0052 | 1.3483 | 0.358 | 91.68 | 0 | 0
Okuma-Genos | 11-4-17 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0072 | 3.6511 | 1.364 | 175.8 | 0 | 0
Okuma-Genos | 7-3-18 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0068 | 2.687 | 0.67 | 156.79 | 0 | 0
Okuma-Genos | 9-3-18 | Non Stnd | 0 | 0 | 0 | 18 | 1 | 1 | 0 | A02071-0056 | 1.5733 | 0.5 | 106.33 | 0 | 0
Okuma-Genos | 9-4-18 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0072 | 3.5376 | 0.094 | 175.8 | 0 | 0
Okuma-Genos | 9-3-19 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0068 | 3.0733 | 0.96 | 156.79 | 0 | 0
Haas Vertical Mill VF4 | 11-4-20 | Non Stnd | 0 | 0 | 0 | 8 | 1 | 1 | 0 | 11-4-G-BLNK | NA | 1.1 |  | 0
Okuma-Genos | 11-4-20 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0072 | 3.6511 | 1.1 | 175.8 | 0 | 0
Okuma-Genos | 9-3-22 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0068 | 3.0733 | 0.774 | 156.79 | 0 | 0
Haas Vertical Mill VF4 | 11-4-25 | Non Stnd | 0 | 0 | 0 | 8 | 1 | 1 | 0 | 11-4-L-BLNK | NA | 1.92 |  | 0
Okuma-Genos | 9-3-26 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.3326 | 1.307 | 195.85 | 0 | 0
Haas Vertical Mill VF4 | 9-3-26 | Non Stnd | 0 | 0 | 0 | 8 | 1 | 1 | 0 | 9-3-E-BLNK | NA | 1.307 |  | 0
Haas Vertical Mill VF4 | 11-4-26 | Non Stnd | 0 | 0 | 0 | 8 | 1 | 1 | 0 | 11-4-L-BLNK | NA | 1.87 |  | 0
Haas Vertical Mill VF4 | 11-4-35 | Non Stnd | 0 | 0 | 0 | 3 | 1.5 | 1.5 | 0 | 11-4-K-BLNK | NA | 5.38 |  | 0
Haas Vertical Mill VF4 | 11-4-36 | Non Stnd | 0 | 0 | 0 | 4 | 1.5 | 1.5 | 0 | 11-4-K-BLNK | NA | 5.38 |  | 0
Bridgeport Drill Press | 300341 | Non Stnd | 0 | 0 |  | 2 | 2 | 2 | 0 | 300340 | NA |  |  | 0
Bridgeport CNC Mill | 300341 | Stnd | 0 | 0 |  | 4 | 0.4 | 0.4 | 0 | 300340 | NA |  |  | 0
Bridgeport Drill Press | 300346 | Non Stnd | 0 | 0 |  | 6 | 1 | 1 | 0 | 300322 | NA |  |  | 0
B&S18 | 301104 |  | 0 | 0 |  | 6 | 1 | 1 | 0 | A09002-0014 | 0.004 |  | 2.39 | 0 | 0
Cobra | 434292 |  | 0 | 0 |  | 16 | 16 | 16 | 2 | A06101-0018 | 0.0486 |  | 10.45 | 0 | 0
T-42 or Cobra | 100046-1(1/3) |  | 0 | 0 | 0 | 6 | 4 | 4 | 1 | 100046-999 | NA | 0.98137 |  | 0
T-42 or Cobra | 100046-1(2/3) |  | 0 | 0 |  | 6 | 4 | 4 | 1 | 100046-1(1/3) | NA |  |  | 0
T-42 | 100046-1(3/3) |  | 0 | 0 |  | 6 | 4 | 4 | 1 | 100046-1(2/3) | NA |  |  | 0
T-42 or Cobra | 100046-2(1/3) |  | 0 | 0 | 0 | 3 | 4 | 4 | 1 | 100046-999 | NA | 0.93 |  | 0
T-42 or Cobra | 100046-2(2/3) |  | 0 | 0 |  | 3 | 2 | 2 | 0 | 100046-2(1/3) | NA |  |  | 0
T-42 | 100046-2(3/3) |  | 0 | 0 |  | 3 | 4 | 4 | 1 | 100046-2(2/3) | NA |  |  | 0
T-42 or Cobra | 100046-3(1/3) |  | 0 | 0 | 0 | 6 | 4 | 4 | 1 | 100046-999 | NA | 0.807 |  | 0
T-42 or Cobra | 100046-3(2/3) |  | 0 | 0 |  | 6 | 3 | 3 | 0 | 100046-3(1/3) | NA |  |  | 0
T-42 | 100046-3(3/3) |  | 0 | 0 |  | 6 | 4 | 4 | 1 | 100046-3(2/3) | NA |  |  | 0
B&S18 | 100048-1 |  | 0 | 0 | 0 | 93 | 16 | 16 | 2 | A02001-0036 | 0.0866 | 0.01875 | 43.94 | 0 | 0
B&S18 | 100048-1-LF |  | 0 | 0 | 0 | 93 | 8 | 8 | 1 | A03001-0036 | 0.0866 | 0.02125 | 48.96 | 0 | 0
B&S18 | 100049-1 |  | 0 | 0 | 0 | 120 | 16 | 16 | 2 | A02001-0016 | 0.1171 | 0.9202 | 8.68 | 0 | 0
B&S18 | 100050-1 |  | 0 | 0 | 0 | 200 | 16 | 16 | 2 | A02001-0028 | 0.0416 | 0.01785 | 26.58 | 0 | 0
B&S18 | 100052-1 |  | 0 | 0 | 0 | 103 | 16 | 16 | 2 | A02001-0036 | 0.737 | 0.3496 | 43.94 | 0 | 0
Okuma-Cadet | 100132-1 |  | 0 | 0 | 0 | 8 | 16 | 16 | 2 | A06201-0028 | 0.4004 | 0.2488 | 25.29 | 0 | 0
B/S 18 | 100147-3(1/2) |  | 0 | 0 | 0 | 90 | 16 | 16 | 2 | A06201-0008 | 0.0124 | 0.003 | 2.06 | 0 | 0
Drill Press | 100147-3(2/2) |  | 0 | 0 |  | 90 | 16 | 16 | 2 | 100147-3(1/2) | 0.0124 |  |  | 0
T-42 or Cobra | 100700-1(1/3) |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 100046-999 | NA | 0.659 |  | 0
T-42 or Cobra | 100700-1(2/3) |  | 0 | 0 |  | 6 | 4 | 4 | 1 | 100700-1(1/3) | NA |  |  | 0
T-42 | 100700-1(3/3) |  | 0 | 0 |  | 6 | 4 | 4 | 1 | 100700-1(2/3) | NA |  |  | 0
B/S 17 | 101467-1 (2/3) |  | 0 | 0 |  | 72 | 16 | 16 | 2 | 101467-1 (1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | 101467-1 (3/3) |  | 0 | 0 |  | 46 | 16 | 16 | 2 | 101467-1 (2/3) | NA |  |  | 0
B/S 17 | 101467-1-LF(2/3) |  | 0 | 0 |  | 72 | 16 | 16 | 2 | 101467-1-LF(1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | 101467-1-LF(3/3) |  | 0 | 0 |  | 46 | 16 | 16 | 2 | 101467-1-LF(2/3) | NA |  |  | 0
B/S 17 | 101467-19(2/3) |  | 0 | 0 |  | 72 | 16 | 16 | 2 | 101467-19(1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | 101467-19(3/3) |  | 0 | 0 |  | 46 | 16 | 16 | 2 | 101467-19(2/3) | NA |  |  | 0
B/S 17 | 101467-19-LF(2/3) |  | 0 | 0 |  | 72 | 16 | 16 | 2 | 101467-19-LF(1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | 101467-19-LF(3/3) |  | 0 | 0 |  | 46 | 16 | 16 | 2 | 101467-19-LF(2/3) | NA |  |  | 0
B/S 17 | 101582-1 (2/3) |  | 0 | 0 |  | 64 | 1 | 1 | 0 | 101582-1 (1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | 101582-1 (3/3) |  | 0 | 0 |  | 103 | 4 | 4 | 1 | 101582-1 (2/3) | NA |  |  | 0
B/S 17 | 101728-1 (2/3) |  | 0 | 0 |  | 131 | 4 | 4 | 1 | 101728-1 (1/3) | NA |  |  | 0
CNC Bridgeport | 101728-1 (3/3) |  | 0 | 0 |  | 54 | 1 | 1 | 0 | 101728-1 (2/3) | NA |  |  | 0
B/S 17 | 101728-1-LF (2/3) |  | 0 | 0 |  | 131 | 4 | 4 | 1 | 101728-1-LF (1/3) | NA |  |  | 0
CNC Bridgeport | 101728-1-LF (3/3) |  | 0 | 0 |  | 36 | 3 | 3 | 0 | 101728-1-LF (2/3) | NA |  |  | 0
B/S 17 | 101728-2 (2/3) |  | 0 | 0 |  | 131 | 4 | 4 | 1 | 101728-2 (1/3) | NA |  |  | 0
CNC Bridgeport | 101728-2 (3/3) |  | 0 | 0 |  | 38 | 3 | 3 | 0 | 101728-2 (2/3) | NA |  |  | 0
CNC Bridgeport | 101728-6 | non stnd | 0 | 0 | 0 | 38 | 3 | 3 | 0 | 101728-1 | NA | 0.1517 |  | 0
B/S 17 | 101729-1 (2/3) |  | 0 | 0 |  | 131 | 4 | 4 | 1 | 101729-1 (1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | 101729-1 (3/3) |  | 0 | 0 |  | 38 | 3 | 3 | 0 | 101729-1 (2/3) | NA |  |  | 0
B&S18 | 102095-2 (1/3) | Standard | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02002-0024 | 0.1734 | 0.065 | 21.54 | 0 | 0
B/S 17 | 102095-2 (2/3) |  | 0 | 0 |  | 131 | 4 | 4 | 1 | 102095-2 (1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | 102095-2 (3/3) |  | 0 | 0 |  | 38 | 3 | 3 | 0 | 102095-2 (2/3) | NA |  |  | 0
B&S18 | 102100-1 | Non Stnd | 0 | 0 | 0 | 152 | 8 | 8 | 1 | A02002-0022 | 0.0282 | 0.00466 | 18.1 | 0 | 0
B&S18 | 102526-1 |  | 0 | 0 |  | 720 | 16 | 16 | 2 | A02001-0005 | 0.0232 | 0.023 | 0.8484 | 0 | 0
T-42 or Cobra | 103147-1 (1/4) |  | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 100046-999 | NA | 0.498 |  | 0
T-42 or Cobra | 103147-1 (2/4) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | 103147-1 (1/4) | NA |  |  | 0
T-42 | 103147-1 (3/4) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | 103147-1 (2/4) | NA |  |  | 0
T-42 | 103147-1 (4/4) |  | 0 | 0 |  | 6 | 4 | 4 | 1 | 103147-1 (4/4) | NA |  |  | 0
Okuma-Cadet | 103148-1 (1/2) |  | 0 | 0 | 0 | 7 | 16 | 16 | 2 | A06201-0028 | 0.2931 | 0.18032 | 25.29 | 0 | 0
Okuma-Cadet | 103148-1 (2/2) |  | 0 | 0 |  | 15 | 16 | 16 | 2 | 103148-1 (1/2) | 0.2931 |  |  | 0
Okuma-Cadet | 103151-1 (1/2) |  | 0 | 0 | 0 | 2 | 3.5 | 3.5 | 0 | A06202-0048 | 1.1566 | 0.1723 | 79.5 | 0 | 0
Okuma-Cadet | 103151-1 (2/2) |  | 0 | 0 |  | 5 | 2 | 2 | 0 | 103151-1 (1/2) | NA |  |  | 0
B&S18 | 103153-1 (1/2) |  | 0 | 0 | 0 | 32 | 8 | 8 | 1 | A06201-0014 | 0.068 | 0.0472 | 6.763 | 0 | 0
B&S Ultramatic #3 | 103153-1 (2/2) |  | 0 | 0 |  | 65 | 5 | 5 | 1 | 103153-1 (1/2) | NA |  |  | 0
Drill Press | 103329-2 |  | 0 | 0 | 0 | 182 | 1 | 1 | 0 | 103329-1 | NA | 0.1152 |  | 0
Bridgeport Drill Press | 104524-5 |  | 0 | 0 | 0 | 65 | 1 | 1 | 0 | 104524-2-200 | NA | 0.172 |  | 0
B&S18 | 104668-1 |  | 0 | 0 | 0 | 128 | 16 | 16 | 2 | A02001-0012 | 0.0384 | 0.01912 | 4.88 | 0 | 0
B&S18 | 104669-1 |  | 0 | 0 | 0 | 180 | 16 | 16 | 2 | A02001-0014 | 0.0367 | 0.01676 | 6.65 | 0 | 0
Drill Press | 104670-1 |  | 0 | 0 | 0 | 180 | 1 | 1 | 0 | 104670U-1 | NA | 0.03324 |  | 0
Tapper | 104676-15 |  | 0 | 0 | 0 | 192 | 0.5 | 0.5 | 0 | 104676U-15 | NA | 0.007 |  | 0
Tapper | 104676-17 |  | 0 | 0 | 0 | 192 | 0.5 | 0.5 | 0 | 104676U-17 | NA | 0.007 |  | 0
B&S18 | 104856-2 (1/4) |  | 0 | 0 | 0 | 120 | 16 | 16 | 2 | A02002-0024 | 0.2116 | 0.06015 | 21.54 | 0 | 0
B&S17 | 104856-2 (2/4) |  | 0 | 0 |  | 42 | 18 | 18 | 2 | 104856-2 (1/4) | NA |  |  | 0
Hass Vertical Mill VF3 | 104856-2 (3/4) |  | 0 | 0 |  | 25 | 0.5 | 0.5 | 0 | 104856-2 (2/4) | NA |  |  | 0
Mill | 104856-2 (4/4) |  | 0 | 0 |  | 25 | 0.5 | 0.5 | 0 | 104856-2 (3/4) | NA |  |  | 0
B&S18 | 105365-1 |  | 0 | 0 | 0 | 96 | 16 | 16 | 2 | A02001-0020 | 0.2636 | 0.1344 | 13.56 | 0 | 0
B&S18 | 105365-1-LF |  | 0 | 0 | 0 | 60 | 16 | 16 | 2 | A03001-0020 | 0.2636 | 0.1344 | 13.56 | 0 | 0
B&S17 | 105950-4 |  | 0 | 0 | 0 | 244 | 16 | 16 | 2 | 105950-2 | NA | 0.017 |  | 0
B&S17 | 106148-1 | Hydromat | 0 | 0 |  | 240 | 4 | 4 | 1 | 106148U-1 | 1 |  |  | 0
Okuma-Cadet | 106203-1 (1/3) |  | 0 | 0 | 0 | 2 | 5 | 5 | 1 | 106203-999 | NA | 1.4065 |  | 0
Okuma-Cadet | 106203-1 (2/3) |  | 0 | 0 |  | 2 | 5 | 5 | 1 | 106203-1 (1/3) | NA |  |  | 0
Okuma-Cadet | 106203-1 (3/3) |  | 0 | 0 |  | 2 | 5 | 5 | 1 | 106203-1 (2/3) | NA |  |  | 0
T-42 or H3 | 106204-1 (1/2) |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 106204-999 | NA | 0.8507 |  | 0
T-42 or H3 | 106204-1 (2/2) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | 106204-1 (1/2) | NA |  |  | 0
T-42 or H3 | 106204-3 (1/2) |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 106204-999 | NA | 0.735 |  | 0
T-42 or H3 | 106204-3 (2/2) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | 106204-3 (1/2) | NA |  |  | 0
T-42 or H3 | 106205-1 (1/2) |  | 0 | 0 | 0 | 5 | 2.5 | 2.5 | 0 | 106205-999 | NA | 0.969 |  | 0
T-42 or H3 | 106205-1 (2/2) |  | 0 | 0 |  | 5 | 2.5 | 2.5 | 1 | 106205-1 (1/2) | NA |  |  | 0
T-42 or H3 | 106206-1 (1/2) |  | 0 | 0 | 0 | 5 | 2.5 | 2.5 | 0 | 106204-999 | NA | 0.8466 |  | 0
T-42 or H3 | 106206-1 (2/2) |  | 0 | 0 |  | 5 | 1.5 | 1.5 | 1 | 106206-1 (1/2) | NA |  |  | 0
T-42 or H3 | 106206-3 (1/2) |  | 0 | 0 | 0 | 5 | 2.5 | 2.5 | 0 | 106204-999 | NA | 0.81 |  | 0
T-42 or H3 | 106206-3 (2/2) |  | 0 | 0 |  | 5 | 1.5 | 1.5 | 1 | 106206-3 (1/2) | NA |  |  | 0
T-42 or H3 | 106207-1 (1/2) |  | 0 | 0 | 0 | 5 | 3 | 3 | 0 | 106205-999 | NA | 0.93 |  | 0
T-42 or H3 | 106207-1 (2/2) |  | 0 | 0 |  | 5 | 1.5 | 1.5 | 1 | 106207-1 (1/2) | NA |  |  | 0
B&S18 | 106210-1 |  | 0 | 0 | 0 | 15 | 16 | 16 | 2 | A06201-0020 | 0.368 | 0.2783 | 12.9 | 0 | 0
Citizen | 106212-1 | Stnd | 0 | 0 | 0 | 30 | 8 | 8 | 1 | A06201-0010 | 0.022 | 0.022 | 3.23 | 0 | 0
Citizen | 106212-3 | Stnd | 0 | 0 | 0 | 30 | 8 | 8 | 1 | A06201-0010 | 0.0164 | 0.0164 | 3.23 | 0 | 0
B&S18 | 106212-1 (1/2) | non stnd | 0 | 0 | 0 | 32 | 8 | 8 | 1 | A06201-0010 | 0.022 | 0.022 | 3.23 | 0 | 0
Drill Press | 106212-1 (2/2) | non stnd | 0 | 0 |  | 182 | 1 | 1 | 0 | 106212-1 (1/2) | NA |  |  | 0
B&S18 | 106212-3 (1/2) | Non Stnd | 0 | 0 | 0 | 40 | 16 | 16 | 2 | A06201-0010 | 0.0164 | 0.0164 | 3.23 | 0 | 0
Drill Press | 106212-3 (2/2) | Non Stnd | 0 | 0 |  | 108 | 0.4 | 0.4 | 0 | 106212-3 (1/2) | NA |  |  | 0
Haas Vertical Mill VF3 | 106215-5 |  | 0 | 0 | 0 | 18 | 1 | 1 | 0 | 106215-999 | NA | 0.13232 |  | 0
Haas Vertical Mill VF3 | 106215-7 |  | 0 | 0 | 0 | 16 | 2 | 2 | 0 | 106215-999 | NA | 0.13232 |  | 0
B&S18 | 106267-1 (1/2) | Non Stnd | 0 | 0 | 0 | 171 | 16 | 16 | 2 | A02002-0022 | 0.3277 | 0.13192 | 18.1 | 0 | 0
B&S18 | 106267-1 (2/2) | Non Stnd | 0 | 0 |  | 171 | 16 | 16 | 2 | 106267-1 (1/2) | NA |  |  | 0
B&S Ultramatic #3 | 106272-1 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-1 | NA | 0.0985 |  | 0
T42 or Cobra | 106272-11 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-1 | NA | 0.0985 |  | 0
B&S Ultramatic #3 | 106272-12 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-2 | NA | 0.0985 |  | 0
B&S Ultramatic #3 | 106272-13 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-1 | NA | 0.0985 |  | 0
B&S Ultramatic #3 | 106272-2 |  | 0 | 0 | 0 | 57 | 4 | 4 | 1 | 106273-1 | NA | 0.0985 |  | 0 | [11 empty] | 0
B&S Ultramatic #3 | 106272-3 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-1 | NA | 0.0985 |  | 0 | [11 empty] | 0
B&S Ultramatic #3 | 106272-5 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-2 | NA | 0.0985 |  | 0 | [11 empty] | 0
B&S Ultramatic #3 | 106272-6 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-2 | NA | 0.0985 |  | 0
B&S Ultramatic #3 | 106272-7 |  | 0 | 0 | 0 | 57 | 16 | 16 | 2 | 106273-2 | NA | 0.0985 |  | 0
Cobra | 106273-1 | Non Stnd | 0 | 0 | 0 | 10 | 16 | 16 | 2 | A06202-0022 | 0.1276 | 0.0985 | 16.7 | 0 | 0
B&S18 | 106273-1 | STND | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A06202-0022 | 0.1276 | 0.0985 | 16.7 | 0 | 0
B&S18 | 106273-2 | STND | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A06202-0028 | 0.2434 | 0.152 | 27.89 | 0 | 0
B&S18 | 106781-1 | Non Stnd | 0 | 0 | 0 | 90 | 16 | 16 | 2 | A02001-0028 | 0.4754 | 0.1804 | 26.58 | 0 | 0
Okuma-Cadet | 106781-1-LF | Non Stnd | 0 | 0 | 0 | 4 | 4 | 4 | 1 | A03001-0028 | 0.4754 | 0.1755 | 26.58 | 0 | 0
B&S18 | 106782-1 | Non Stnd | 0 | 0 | 0 | 82 | 16 | 16 | 2 | A02001-0016 | 0.127 | 0.05808 | 8.68 | 0 | 0
B&S18 | 106782-1-LF | Non Stnd | 0 | 0 | 0 | 82 | 16 | 16 | 2 | A03001-0016 | 0.127 | 0.05808 | 8.68 | 0 | 0
Okuma-Cadet | 106845-1 |  | 0 | 0 | 0 | 8 | 8 | 8 | 1 | A06201-0028 | 0.4762 | 0.3101 | 25.29 | 0 | 0
Okuma-Genos | 1101-11-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.8156 | 0.702 | 106.33 | 0 | 0
Okuma-Genos | 1101-13-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.8156 | 0.68 | 106.33 | 0 | 0
Okuma-Genos | 1101-9-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.8156 | 0.668 | 106.33 | 0 | 0
Okuma-Genos | 1101-9-5/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.8156 | 0.666 | 106.33 | 0 | 0
M1 | 1101-A-BLNK |  | 0 | 0 | 0 | 36 | 2 | 2 | 0 | A02071-0056 | 1.8156 | 0.821 | 106.33 | 0 | 0
Okuma-Genos | 1102-12-5/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.068 | 0.93 | 195.85 | 0 | 0
Okuma-Genos | 1102-14-5/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.068 | 0.89 | 195.85 | 0 | 0
Okuma-Genos | 1102-15-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.068 | 1.06 | 195.85 | 0 | 0
Okuma-Genos | 1102-15-5/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.068 | 1.05 | 195.85 | 0 | 0
Okuma-Genos | 1102-16-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.068 | 0.951 | 195.85 | 0 | 0
Okuma-Genos | 1102-18-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.068 | 0.9266 | 195.85 | 0 | 0
H4 | 1102-A-BLNK |  | 0 | 0 | 0 | 20 | 3 | 3 | 0 | A02071-0076 | 4.068 | 1.1604 | 195.85 | 0 | 0
Haas Vertical Mill VF4 | 1103-16-5/16 |  | 0 | 0 | 0 | 10 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-18-5/16 |  | 0 | 0 | 0 | 10 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-19-1/4 |  | 0 | 0 | 0 | 10 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-20-1/4 |  | 0 | 0 | 0 | 12 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-20-5/16 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-21-1/4 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-21-1/4 |  | 0 | 0 | 0 | 12 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-21-5/16 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-22-1/4 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-23-1/4 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-24-1/4 |  | 0 | 0 | 0 | 9 | 1.5 | 1.5 | 0 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-25-1/4 |  | 0 | 0 | 0 | 7 | 1.5 | 1.5 | 0 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-26-1/4 |  | 0 | 0 | 0 | 9 | 1.5 | 1.5 | 0 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-27-3/16 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-28-3/16 |  | 0 | 0 | 0 | 6 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
Haas Vertical Mill VF4 | 1103-30-3/16 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1103-AF-BLNK | NA | 2.145 |  | 0
H4 | 1103-A-BLNK |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | A02071-0096 | 8.038 | 2.145 | 312.49 | 0 | 0
Okuma-Genos | 1104-12-5/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0072 | 6.1122 | 3.1 | 175.8 | 0 | 0
Okuma-Genos | 1104-13-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | 1104-14-1/4 | 6.1122 | 3.1 |  | 0
Haas Vertical Mill VF4 | 1104-14-1/4-7/8 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | 1104-15-1/4 | NA | 3.1 |  | 0
Okuma-Genos | 1104-15-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0072 | 6.1122 | 3.1 | 175.8 | 0 | 0
Haas Vertical Mill VF4 | 1104-15-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | 1104-A-BLNK | NA | 3.1 |  | 0
Haas Vertical Mill VF4 | 1104-15-1/4-5/8 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | 1104-15-1/4 | NA | 3.1 |  | 0
Haas Vertical Mill VF4 | 1104-15-1/4-7/8 |  | 0 | 0 | 0 | 32 | 2 | 2 | 0 | 1104-15-1/4 | NA | 3.1 |  | 0
Okuma-Genos | 1104-16-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0072 | 6.1122 | 3.1 | 175.8 | 0 | 0
H1 | 1104-A-BLNK |  | 0 | 0 | 0 | 18 | 1.5 | 1.5 | 0 | A02071-0072 | 6.1122 | 3.1 | 175.8 | 0 | 0
H4 | 11-3-A-BLNK | Stnd | 0 | 0 | 0 | 23 | 1 | 1 | 0 | A02071-0076 | 3.941 | 1.372 | 195.85 | 0 | 0
Haas Vertical Mill VF4 | 11-3-27 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 11-3-B-BLNK | NA | 1.372
Haas Vertical Mill VF4 | 11-3-33 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 11-3-B-BLNK | NA | 1.372
M1 | 11-3-A-BLNK | Non Stnd | 0 | 0 | 0 | 23 | 1 | 1 | 0 | A02071-0076 | 3.941 | 1.372 | 195.85 | 0 | 0
H4 | 11-3-B-BLNK |  | 0 | 0 | 0 | 27 | 3 | 3 | 0 | A02071-0096 | 8.089 | 2.239 | 312.49 | 0 | 0
M1 | 11-4-A-BLNK |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0046 | 1.4035 | 0.098 | 71.75 | 0 | 0
H1 | 11-4-C-BLNK | Stnd | 0 | 0 | 0 | 42 | 1 | 1 | 0 | A02071-0056 | 1.6788 | 0.812 | 106.33 | 0 | 0
M1 | 11-4-C-BLNK | Non Stnd | 0 | 0 | 0 | 42 | 1 | 1 | 0 | A02071-0056 | 1.6788 | 0.812 | 106.33 | 0 | 0
H1 | 11-4-F-BLNK |  | 0 | 0 | 0 | 34 | 1 | 1 | 0 | A02071-0064 | 2.354 | 0.9085 | 138.88 | 0 | 0
H1 | 11-4-G-BLNK | Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | A02071-0072 | 3.6511 | 1.364 | 175.8 | 0 | 0
M1 | 11-4-G-BLNK | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | A02071-0072 | 3.6511 | 1.364 | 175.8 | 0 | 0
H4 | 11-4-J-BLNK |  | 0 | 0 | 0 | 13 | 1 | 1 | 0 | A02071-0112 | 12.3501 | 3.6 | 425.33 | 0 | 0
H4 | 11-4-K-BLNK |  | 0 | 0 | 0 | 13 | 1 | 1 | 0 | A02071-0128 | 16.2917 | 5.38 | 555.53 | 0 | 0
H4 | 11-4-L-BLNK |  | 0 | 0 | 0 | 16 | 2 | 2 | 0 | A02071-0096 | 7.9106 | 2.8046 | 312.49 | 0 | 0
H4 | 11-4-N-BLNK |  | 0 | 0 | 0 | 18 | 1 | 1 | 0 | A02071-0088 | 6.4867 | 3.1 | 262.58 | 0 | 0 |  |  |  |  | Was 11-4-I-BLNK
H1 | 11-5-A-BLNK |  | 0 | 0 | 0 | 36 | 3 | 3 | 0 | A02071-0052 | 1.553 | 0.074 | 91.68 | 0 | 0
H1 | 11-5-B-BLNK |  | 0 | 0 | 0 | 29 | 1 | 1 | 0 | A02071-0064 | 2.4487 | 1.3463 | 138.88 | 0 | 0
H1 | 11-6-C-BLNK |  | 0 | 0 | 0 | 24 | 1 | 1 | 0 | A02071-0072 | 3.21 | 0.99 | 175.8 | 0 | 0
H1 | 11-8-A-BLNK |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02071-0052 | 1.321 | 0.838 | 91.68 | 0 | 0
VF3 or VF4 | 1301-19-5/16 |  | 0 | 0 | 0 | 8 | 0.5 | 0.5 | 0 | 1301-AF-BLNK | NA | 1.95 |  | 0
VF3 or VF4 | 1301-20-1/4 |  | 0 | 0 | 0 | 8 | 0.5 | 0.5 | 0 | 1301-AF-BLNK | NA | 1.95 |  | 0
VF3 or VF4 | 1301-20-5/16 |  | 0 | 0 | 0 | 8 | 0.5 | 0.5 | 0 | 1301-AF-BLNK | NA | 1.95 |  | 0
VF3 or VF4 | 1301-22-1/4 |  | 0 | 0 | 0 | 8 | 1 | 1 | 0 | 1301-AF-BLNK | NA | 1.95 |  | 0
VF3 or VF4 | 1301-24-1/4 |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | 1301-AF-BLNK | NA | 1.95 |  | 0
VF3 or VF4 | 1301-30-3/16 |  | 0 | 0 | 0 | 6 | 0.5 | 0.5 | 0 | 1301-AF-BLNK | NA | 1.95 |  | 0
H4 | 1301-A-BLNK | Use 1301-AF | 0 | 0 | 0 | 18 | 1 | 1 | 0 | A02071-0096 | 8.0074 | 1.95 | 312.49 | 0 | 0 | [12 empty] | #REF!
VF3 or VF4 | 1302-20-1/4 |  | 0 | 0 | 0 | 7 | 1 | 1 | 0 | 1302-A-BLNK | NA | 4.53 |  | 0 | [13 empty] | #REF!
VF3 or VF4 | 1302-20-1/4-7/8 |  | 0 | 0 | 0 | 7 | 1 | 1 | 0 | 1302-20-1/4 | NA | 4.53 |  | 0
VF3 or VF4 | 1302-24-1/4-7/8 |  | 0 | 0 | 0 | 7 | 1 | 1 | 0 | 1302-24-1/4 | NA | 4.53 |  | 0
H4 | 1302-A-BLNK |  | 0 | 0 | 0 | 15 | 2 | 2 | 0 | A02071-0088 | 8.9601 | 4.86 | 262.58 | 0 | 0
VF3 or VF4 | 1303-23-5/16 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-25-1/4 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-25-5/16 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-26-5/16 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-27-1/4 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-28-1/4 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-29-1/4 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-30-1/4 |  | 0 | 0 | 0 | 12 | 4 | 4 | 1 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-30-3/16 |  | 0 | 0 | 0 | 6 | 1 | 1 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-34-3/16 |  | 0 | 0 | 0 | 4 | 0.5 | 0.5 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-35-3/16 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-36-3/16 |  | 0 | 0 | 0 | 4 | 0.5 | 0.5 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-37-3/16 |  | 0 | 0 | 0 | 4 | 0.5 | 0.5 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1303-40-3/16 |  | 0 | 0 | 0 | 4 | 0.5 | 0.5 | 0 | 1303-AF-BLNK | NA | 2.79 |  | 0
H4 | 1303-A-BLNK | Use 1303-AF | 0 | 0 | 0 | 13 | 1 | 1 | 0 | A02071-0112 | 11.8444 | 2.79 | 425.33 | 0 | 0
VF3 or VF4 | 1304-28-5/16 |  | 0 | 0 | 0 | 6 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-30-5/16 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-32-1/4 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-33-1/4 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-34-1/4 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-36-1/4 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-38-1/4 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-39-3/16 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-40-3/16 |  | 0 | 0 | 0 | 6 | 0.75 | 0.75 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
VF3 or VF4 | 1304-40-5/32 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1304-AF-BLNK | NA | 2.79 |  | 0
H4 | 1304-A-BLNK | Use 1304-AF | 0 | 0 | 0 | 13 | 1 | 1 | 0 | A02071-0128 | 18.305 | 2.79 | 555.53 | 0 | 0
H1 | 1305-A-BLNK | Use 1305-AF | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A02071-0144 | 22.6 | 5.1 | 469 | 0 | 0
Haas Vertical Mill VF4 | 1305-31-5/16 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1305-AF-BLNK | NA | 5.1 |  | 0
Haas Vertical Mill VF4 | 1305-36-1/4 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1305-AF-BLNK | NA | 5.1 |  | 0
Haas Vertical Mill VF4 | 1305-38-1/4 | Non Stnd | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1305-AF-BLNK | NA | 5.1 |  | 0
Haas Vertical Mill VF4 | 1305-40-1/4 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1305-AF-BLNK | NA | 5.1 |  | 0
Haas Vertical Mill VF4 | 1305-50-3/16 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1305-AF-BLNK | NA | 5.1 |  | 0
H1 | 1306-A-BLNK |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0152 | 26.2 | 5.6 | 524.64 | 0 | 0
Haas Vertical Mill VF4 | 1306-36-5/16 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 1308-A-BLNK | NA | 5.6 |  | 0
H4 | 1307-A-BLNK |  | 0 | 0 | 0 | 12 | 3 | 3 | 0 | A02071-0112 | 16.0253 | 5.5 | 425.33 | 0 | 0 |  |  |  |  | 2018
Haas Vertical Mill VF4 | 1307-39-5/32-7/8 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1307-A-BLNK | NA | 5.5 |  | 0 | [5 empty] | 2018
Haas Vertical Mill VF4 | 1307-40-5/32-7/8 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 1307-A-BLNK | NA | 5.5 |  | 0 | [5 empty] | 2018
Haas Vertical Mill VF4 | 1308-44-5/16 |  | 0 | 0 | 0 | 6 | 4 | 4 | 1 | 1308-A-BLNK | NA | 8.17 |  | 0
Haas Vertical Mill VF4 | 1308-52-1/4 |  | 0 | 0 | 0 | 6 | 4 | 4 | 1 | 1308-A-BLNK | NA | 8.17 |  | 0
H1 | 1308-A-BLNK (1/2) |  | 0 | 0 | 0 | 10 | 1 | 1 | 0 | A02071-0176 | 43.6371 | 8.17 | 700.24 | 0 | 0
H3 | 1308-A-BLNK (2/2) |  | 0 | 0 |  | 20 | 1 | 1 | 0 | 1308-A-BLNK (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | 13-4-21 |  | 0 | 0 | 0 | 4 | 0.75 | 0.75 | 0 | 13-4-B-BLNK | NA | 2.345 |  | 0 | [5 empty] | 2018
H4 | 13-4-A-BLNK |  | 0 | 0 | 0 | 12 | 3 | 3 | 0 | A02071-0128 | 7.966 | 2.926 | 555.53 | 0 | 0
H4 | 13-4-B-BLNK |  | 0 | 0 | 0 | 12 | 3 | 3 | 0 | A02071-0096 | 7.68 | 2.345 | 312.49 | 0 | 0 |  |  |  |  | 2018
H4 | 13-5-A-BLNK |  | 0 | 0 | 0 | 15 | 2 | 2 | 0 | A02071-0076 | 6.92 | 0.6 | 195.85 | 0 | 0
H4 | 13-5-C-BLNK |  | 0 | 0 | 0 | 17 | 1 | 1 | 0 | A02071-0096 | 6.982 | 2.16 | 312.49 | 0 | 0
Goss#1 Backup ONLY | 143003-02-C | Hydromat | 0 | 0 | 0 | 43 | 16 | 16 | 2 | 143003-02-C-10 | 1 | 1.008 |  | 0
Goss#1 Backup ONLY | 143126-2-C | Hydromat | 0 | 0 | 0 | 43 | 16 | 16 | 2 | 143126-2-C-10 | 1 | 0.905 |  | 0
Goss#1 | 143139-1-C (2/2) |  | 0 | 0 | 0 | 35 | 16 | 16 | 2 | 143139-1-C (1/2) | NA | 1.602 |  | 0
Goss#1 | 143176-1-C (2/2) |  | 0 | 0 | 0 | 35 | 10 | 10 | 1 | 143176-1-C (1/2) | NA | 1.575 |  | 0
Goss#1 | 143304-01-C (2/2) | Stnd | 0 | 0 | 0 | 43 | 16 | 16 | 2 | 143304-01-C (1/2) | NA | 1.546 |  | 0
Okuma-Cadet | 143304-01-C (1/3) | Non Stnd | 0 | 0 | 0 | 11 | 3 | 3 | 0 | A01102-0060 | 3.0265 | 1.546 | 124.29 | 0 | 0
Okuma-Cadet | 143304-01-C (2/3) | Non Stnd | 0 | 0 |  | 22 | 16 | 16 | 2 | 143304-01-C (1/3) | 1 |  |  | 0
Hass Vertical Mill VF4 | 143304-01-C (3/3) | Non Stnd | 0 | 0 |  | 40 | 16 | 16 | 2 | 143304-01-C (2/3) | 1 |  |  | 0
B&S16 | 143314-01-C (2/2) |  | 0 | 0 |  | 49 | 4 | 4 | 1 | 143314-01-C (1/2) | NA |  |  | 0
Goss#1 | 143344-01-C (2/2) |  | 0 | 0 |  | 35 | 16 | 16 | 2 | 143344-01-C (1/2) | NA |  |  | 0
B&S18 | 143353-01-C |  | 0 | 0 | 0 | 85 | 4 | 4 | 1 | A01102-0040 | 0.5402 | 0.2982 | 55.24 | 0 | 0
B&S16 | 143354-01-C (2/2) |  | 0 | 0 |  | 40 | 4 | 4 | 1 | 143354-01-C (1/2) | NA |  |  | 0
Goss#1 Backup ONLY | 143356-01-C (2/2) | Hydromat | 0 | 0 |  | 43 | 16 | 16 | 2 | 143356-01-C (2/2) | 1 |  |  | 0
B&S16 | 143357-01-C (2/2) |  | 0 | 0 |  | 44 | 4 | 4 | 1 | 143357-01-C (1/2) | NA |  |  | 0
Goss#1 Backup ONLY | 143358-01-C (2/2) | Hydromat | 0 | 0 |  | 43 | 16 | 16 | 2 | 143358-01-C (1/2) | 1 |  |  | 0
B&S16 | 143359-01-C (2/2) |  | 0 | 0 |  | 61 | 4 | 4 | 1 | 143359-01-C (1/2) | NA |  |  | 0
B&S18 | 209-64BK (1/2) |  | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02002-0022 | 0.1082 | 0.0377 | 18.1 | 0 | 0
B&S Ultramatic #3 | 209-64BK (2/2) |  | 0 | 0 |  | 360 | 16 | 16 | 2 | 209-64BK (1/2) | NA |  |  | 0
B&S16 | 21256A (2/2) | Hydromat | 0 | 0 |  | 152 | 2 | 2 | 0 | 21256A (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | 2201-10-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-2-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-3-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-3-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-4-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-4-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-5-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-6-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-6-3/16-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-7-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-8-3/16-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
Haas Vertical Mill VF4 | 2201-9-3/16-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2201-A-BLNK | NA | 1.6182 |  | 0
H4 | 2201-A-BLNK |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | A01301-0088 | 4.7912 | 1.6182 | 243 | 0 | 0
Haas Vertical Mill VF4 | 2203-2-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-2-5/16-0 |  | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-3-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-3-5/16-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-4-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-4-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-6-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-6-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-8-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203-9-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-10-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-2-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-2-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-3-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-3-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-4-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-4-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-4-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-5-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-6-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-6-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-8-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-8-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-9-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203A-9-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
H4 | 2203-A-BLNK |  | 0 | 0 | 0 | 3 | 8 | 8 | 1 | A01301-0088 | 6.5365 | 3.2699 | 243 | 0 | 0
Haas Vertical Mill VF4 | 2203C-2-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-3-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-3-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-4-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-4-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-6-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-6-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-6-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-8-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2203C-9-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2203-A-BLNK | NA | 3.2699 |  | 0
Haas Vertical Mill VF4 | 2211-10-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0
Haas Vertical Mill VF4 | 2211-2-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0
Haas Vertical Mill VF4 | 2211-3-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0
Haas Vertical Mill VF4 | 2211-4-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0
Haas Vertical Mill VF4 | 2211-5-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0
Haas Vertical Mill VF4 | 2211-6-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0
Haas Vertical Mill VF4 | 2211-7-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0
Haas Vertical Mill VF4 | 2211-8-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2211-A-BLNK | NA | 1.6185 |  | 0 | [15 empty] | #REF!
H4 | 2211-A-BLNK |  | 0 | 0 | 0 | 2 | 8 | 8 | 1 | A06501-0088 | 4.7912 | 1.6185 | 242.3 | 0 | 0 | [14 empty] | #REF!
H4 | 2213-A-BLNK |  | 0 | 0 | 0 | 2 | 16 | 16 | 2 | A06501-0088 | 6.5365 | 1.6185 | 242.3 | 0 | 0
Okuma-Cadet | 22442487-C (1/2) |  | 0 | 0 | 0 | 56 | 4 | 4 | 1 | A01002-0024 | 0.19 | 0.087 | 19.89 | 0 | 0
Cobra | 22442487-C (2/2) |  | 0 | 0 |  | 8 | 4 | 4 | 1 | 22442487-C (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | 2803-10-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-10-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-11-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-11-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-11-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-12-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-12-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-12-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-13-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-13-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-14-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-14-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-16-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-16-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-16-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-17-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-17-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-18-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-20-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-6-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-6-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-6-5/16-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-7-1/4-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-7-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-7-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-8-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-8-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-8-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-9-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-9-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803-11-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803A-12-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803A-18-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803A-20-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803A-7-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803A-8-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803A-8-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
H4 | 2803-A-BLNK |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | A01301-0112 | 12.9759 | 5.41 | 392.52 | 0 | 0
Haas Vertical Mill VF4 | 2803B-4-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-5-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-10-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-10-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-11-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-12-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-12-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-12-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-14-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-14-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-16-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-16-3/16-0 |  | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-17-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-18-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-20-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-24-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-34-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-6-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-6-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-6-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-8-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-9-3/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 2803B-9-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2803-A-BLNK | NA | 5.41 |  | 0
Haas Vertical Mill VF4 | 280701-15-3/8 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-16-5/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-18-1/4 |  | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-18-5/16 |  | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-20-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-20-5/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-21-1/4 |  | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-21-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-22-1/4 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0 | [14 empty] | #REF!
Haas Vertical Mill VF4 | 280701-22-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-22-5/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0 | [14 empty] | #REF!
Haas Vertical Mill VF4 | 280701-23-1/4 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-24-1/4 |  | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-24-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-24-5/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-25-1/4 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-25-5/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-26-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-26-5/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-28-1/4 |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-28-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-29-1/4 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-29-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-30-1/4 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-32-1/4 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-32-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-34-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 280701-36-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280701-BLNK | NA | 6.38 |  | 0
H1 or Okuma-Cadet | 280701-BLNK (1/2) |  | 0 | 0 | 0 | 9 | 2 | 2 | 0 | A01301-0160 | 16.8746 | 6.38 | 801.84 | 0 | 0
H1 or Okuma-Cadet | 280701-BLNK (2/2) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | 280701-BLNK (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | 280702 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280702-BLNK | NA | 10.754 |  | 0
Haas Vertical Mill VF4 | 280702B |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 280702-BLNK | NA | 10.754 |  | 0
H4 | 280702-BLNK (1/2) |  | 0 | 0 | 0 | 4 | 5 | 5 | 1 | A01301-0112 | 10.754 | 4.19 | 392.52 | 0 | 0
H1 or H4 | 280702-BLNK (2/2) |  | 0 | 0 |  | 4 | 5 | 5 | 1 | 280702-BLNK (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | 2813-9-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-10-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-11-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-12-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-12-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-14-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-6-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-7-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-8-1/4-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813-9-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
H4 | 2813-A-BLNK |  | 0 | 0 | 0 | 3 | 8 | 8 | 1 | A06501-0112 | 13.4853 | 5.8577 | 392.5 | 0 | 0
Haas Vertical Mill VF4 | 2813B-5-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813B-7-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813B-8-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813B-10-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 2813B-12-5/16-0 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 2813-A-BLNK | NA | 5.8577 |  | 0
Haas Vertical Mill VF4 | 281701-24-1/4 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 281701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 281701-25-5/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 281701-BLNK | NA | 6.38 |  | 0
Haas Vertical Mill VF4 | 281701-29-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 281701-BLNK | NA | 6.38 |  | 0 | [5 empty] | 2018
Haas Vertical Mill VF4 | 281701-36-3/16 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 281701-BLNK | NA | 6.38 |  | 0 | [5 empty] | 2018
H1 or Okuma-Cadet | 281701-BLNK (1/2) |  | 0 | 0 | 0 | 9 | 8 | 8 | 1 | A06501-0160 | 16.8746 | 6.38 | 801 | 0 | 0 |  |  |  |  | 2018
H1 or Okuma-Cadet | 281701-BLNK (2/2) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | 281701-BLNK (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | 281702 |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 281702-BLNK | 10.754 | 4.19 |  | 0 | [5 empty] | 2018
Haas Vertical Mill VF4 | 281702B |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 281702-BLNK | 10.754 | 4.19 |  | 0 | [5 empty] | 2018
H4 | 281702-BLNK (1/2) |  | 0 | 0 | 0 | 4 | 5 | 5 | 1 | A06501-0112 | 10.756 | 4.19 | 392.5 | 0 | 0 |  |  |  |  | 2018
H1 or H4 | 281702-BLNK (2/2) |  | 0 | 0 |  | 4 | 5 | 5 | 1 | 280702-BLNK (1/2) | NA |  |  | 0
B&S17 | 314605-C |  | 0 | 0 | 0 | 85 | 4 | 4 | 1 | 314605-C-10 | NA | 0.159 |  | 0
H3 | 3-3-A-BLNK |  | 0 | 0 | 0 | 61 | 1 | 1 | 0 | A02071-0020 | 0.0956 | 0.0376 | 13.56 | 0 | 0
H3 | 3-3-B-BLNK |  | 0 | 0 | 0 | 50 | 1 | 1 | 0 | A02071-0022 | 0.171 | 0.01 | 16.41 | 0 | 0
H1 | 3-3-E-BLNK |  | 0 | 0 | 0 | 50 | 1 | 1 | 0 | A02071-0028 | 0.288 | 0.04 | 26.58 | 0 | 0
Cobra | 37081528-C (1/2) |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02002-0024 | 0.2033 | 0.098 | 21.54 | 0 | 0
Cobra | 37081528-C (2/2) |  | 0 | 0 |  | 31 | 1 | 1 | 0 | 37081528-C (1/2) | NA |  |  | 0
Citizen | 401-2-3/16 |  | 0 | 0 | 0 | 54 | 2 | 2 | 0 | A02071-0026 | 0.2442 | 0.09315 | 22.95 | 0 | 0
Citizen | 401-6-3/16 |  | 0 | 0 | 0 | 54 | 2 | 2 | 0 | A02071-0026 | 0.2442 | 0.09315 | 22.95 | 0 | 0
H1 | 401-A-BLNK |  | 0 | 0 | 0 | 41 | 2 | 2 | 0 | A02071-0026 | 0.2426 | 0.09315 | 22.95 | 0 | 0
H1 | 402-A-BLNK |  | 0 | 0 | 0 | 54 | 2 | 2 | 0 | A02071-0034 | 0.4966 | 0.181 | 39.2 | 0 | 0
Okuma-Genos | 407-4-3/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.4966 | 0.14 | 39.2 | 0 | 0
Okuma-Genos | 407-5-3/16 |  | 0 | 0 | 0 | 34 | 2.5 | 2.5 | 0 | A02071-0034 | 0.5281 | 0.13 | 39.2 | 0 | 0
M1 | 407-A-BLNK |  | 0 | 0 | 0 | 35 | 2.5 | 2.5 | 0 | A02071-0034 | 0.5281 | 0.178 | 39.2 | 0 | 0
Citizen 2 | 419995 |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 | A06461-0008 | 0.0091 | 0.003 | 2.06 | 0 | 0 |  |  |  |  | 2018
Okuma-Genos | 4-2.5-10 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0040 | 0.5522 | 0.2032 | 54.25 | 0 | 0
Citizen | 4-2.5-2 |  | 0 | 0 | 0 | 70 | 1 | 1 | 0 | A02071-0016 | 0.0576 | 0.04 | 8.68 | 0 | 0
Citizen | 4-2.5-3 |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0016 | 0.0576 | 0.04 | 8.68 | 0 | 0
Citizen | 4-2.5-8 |  | 0 | 0 | 0 | 45 | 1 | 1 | 0 | A02071-0026 | 0.257 |  | 22.95 | 0 | 0
Citizen | 4-2.5-A-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0016 | 0.0576 | 0.04 | 8.68 | 0 | 0
H3 | 4-2.5-B-BLNK |  | 0 | 0 | 0 | 98 | 0.5 | 0.5 | 0 | A02071-0022 | 0.1618 | 0.07 | 16.41 | 0 | 0
H3 | 4-2.5-F-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0028 | 0.289 | 0.099 | 26.58 | 0 | 0
H1 | 4-2.5-G-BLNK |  | 0 | 0 | 0 | 563 | 16 | 16 | 2 | A02071-0030 | 0.355 | 0.11 | 30.52 | 0 | 0
Okuma-LB3000 | 4-3-5 | Stnd | 0 | 0 | 0 | 30 | 1 | 1 | 0 | A02071-0026 | 0.243 | 0.0996 | 22.95 | 0 | 0 |  |  |  |  | 2018 Moved from Drill room
H3 | 4-3-A-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0020 | 0.113 | 0.02 | 13.56 | 0 | 0
Citizen | 4-3-B-BLNK |  | 0 | 0 | 0 | 42 | 1.5 | 1.5 | 0 | A02071-0026 | 0.243 | 0.0996 | 22.95 | 0 | 0
H1 | 4-3-C-BLNK |  | 0 | 0 | 0 | 53 | 1 | 1 | 0 | A02071-0028 | 0.292 | 0.07 | 26.58 | 0 | 0
H1 | 4-3-D-BLNK |  | 0 | 0 | 0 | 55 | 1 | 1 | 0 | A02071-0032 | 0.4816 | 0.221 | 34.72 | 0 | 0
H1 | 4-3-E-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0040 | 0.5522 | 0.203 | 54.25 | 0 | 0
H1 | 4-4-B-BLNK |  | 0 | 0 | 0 | 52 | 1 | 1 | 0 | A02071-0034 | 0.525 | 0.195 | 39.2 | 0 | 0
H1 | 4-4-C-BLNK |  | 0 | 0 | 0 | 43 | 2 | 2 | 0 | A02071-0040 | 0.6318 | 0.1804 | 54.25 | 0 | 0
M1 | 4-4-D-BLNK |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0052 | 1.3665 | 0.38 | 91.68 | 0 | 0
Citizen | 501-3-3/16 |  | 0 | 0 | 0 | 36 | 2 | 2 | 0 | A02071-0028 | 0.2814 | 0.1077 | 26.58 | 0 | 0 |  |  |  |  | Citizen 2017
Citizen | 501-4-3/16 |  | 0 | 0 | 0 | 36 | 2 | 2 | 0 | A02071-0028 | 0.2832 | 0.1077 | 26.58 | 0 | 0 |  |  |  |  | Citizen 2017
Hass Vertical Mill VF3 | 501-5-3/16 | non stnd | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 501-A-BLNK | NA | 0.1077 |  | 0
Citizen | 501-6-3/16 |  | 0 | 0 | 0 | 36 | 2 | 2 | 0 | A02071-0028 | 0.3382 | 0.1077 | 26.58 | 0 | 0 |  |  |  |  | Citizen 2017
H1 | 501-A-BLNK |  | 0 | 0 | 0 | 36 | 2 | 2 | 0 | A02071-0028 | 0.2832 | 0.1077 | 26.58 | 0 | 0
Okuma-Genos | 502-6-1/4 | non stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.4788 | 0.18 | 39.2 | 0 | 0
Okuma-Genos | 502-6-3/16 | non stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.5094 | 0.18 | 39.2 | 0 | 0
Okuma-Genos | 502-7-3/16 | non stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.5094 | 0.18 | 39.2 | 0 | 0
Okuma-Genos | 502-8-3/16 | non stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.4788 | 0.18 | 39.2 | 0 | 0
Okuma-Genos | 502-9-3/16 | non stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.4788 | 0.18 | 39.2 | 0 | 0
M1 | 502-A-BLNK |  | 0 | 0 | 0 | 33 | 2 | 2 | 0 | A02071-0034 | 0.5711 | 0.18 | 39.2 | 0 | 0
H1 | 502-A-BLNK |  | 0 | 0 | 0 | 30 | 2 | 2 | 0 | A02071-0034 | 0.5094 | 0.18 | 39.2 | 0 | 0
H1 | 503-A-BLNK |  | 0 | 0 | 0 | 41 | 2 | 2 | 0 | A02071-0028 | 0.41 | 0.237 | 26.58 | 0 | 0
Okuma-LB3000 | 5-4-7 |  | 0 | 0 | 0 | 30 | 2 | 2 | 0 | A02071-0040 | 0.6361 | 0.1983 | 54.25 | 0 | 0 |  |  |  |  | LB3000 2018
Hass Vertical Mill VF3 | 5-4-8 |  | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 5-4-C-BLNK | NA | 0.1983 |  | 0
Okuma-LB3000 | 5-4-8 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.5205 | 0.1983 | 54.25 | 0 | 0 |  |  |  |  | LB3000 2018
Hass Vertical Mill VF3 | 5-4-9 | non stnd | 0 | 0 | 0 | 27 | 1 | 1 | 0 | 5-4-D-BLNK | NA | 0.399 |  | 0
Okuma-Genos | 5-4-9 | non stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.2882 | 0.399 | 91.68 | 0 | 0
Okuma-Genos | 5-4-12 | non stnd | 0 | 0 | 0 | 12 | 2 | 2 | 0 | A02071-0052 | 1.2882 | 0.399 | 91.68 | 0 | 0
H1 | 5-2.5-B-BLNK |  | 0 | 0 | 0 | 108 | 2 | 2 | 0 | A02071-0026 | 0.181 | 0.075 | 22.95 | 0 | 0
H1 | 5-2.5-D-BLNK |  | 0 | 0 | 0 | 45 | 2 | 2 | 0 | A02071-0030 | 0.3796 | 0.1715 | 30.52 | 0 | 0
H4 | 5-2.5-E-BLNK |  | 0 | 0 | 0 | 34 | 1 | 1 | 0 | A02071-0040 | 0.591 | 0.17 | 54.25 | 0 | 0
H4 | 5-2.5-F-BLNK |  | 0 | 0 | 0 | 7 | 1 | 1 | 0 | A02071-0112 | 10.7643 | 2.4243 | 425.33 | 0 | 0
C2 | 5-3-A-BLNK |  | 0 | 0 | 0 | 108 | 2 | 2 | 0 | A02071-0020 | 0.099 | 0.06 | 13.56 | 0 | 0
C2 | 5-3-B-BLNK | stnd | 0 | 0 | 0 | 108 | 2 | 2 | 0 | A02071-0026 | 0.2605 | 0.1215 | 22.95 | 0 | 0
H1 | 5-3-B-BLNK | non stnd | 0 | 0 | 0 | 56 | 2 | 2 | 0 | A02071-0026 | 0.2605 | 0.1215 | 22.95 | 0 | 0
H1 | 5-3-C-BLNK |  | 0 | 0 | 0 | 48 | 4 | 4 | 1 | A02071-0028 | 0.34 | 0.07 | 26.58 | 0 | 0
H1 | 5-3-D-BLNK |  | 0 | 0 | 0 | 38 | 2 | 2 | 0 | A02071-0040 | 0.856 | 0.28 | 54.25 | 0 | 0
H1 | 5-4-B-BLNK |  | 0 | 0 | 0 | 56 | 1 | 1 | 0 | A02071-0032 | 0.4512 | 0.1903 | 34.72 | 0 | 0
H1 or H3 | 5-4-C-BLNK |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 | A02071-0040 | 0.6361 | 0.1983 | 54.25 | 0 | 0
Okuma-Genos | 5-4-D-BLNK | Non Stnd | 0 | 0 | 0 | 35 | 2 | 2 | 0 | A02071-0052 | 1.2882 | 0.399 | 91.68 | 0 | 0
M1 | 5-4-D-BLNK | STND | 0 | 0 | 0 | 49 | 2 | 2 | 0 | A02071-0052 | 1.3684 | 0.399 | 91.68 | 0 | 0
H1 | 5-5-A-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0028 | 0.244 | 0.11 | 26.58 | 0 | 0
H1 | 5-5-B-BLNK |  | 0 | 0 | 0 | 54 | 2 | 2 | 0 | A02071-0034 | 0.5063 | 0.1985 | 39.2 | 0 | 0
Citizen | 6022D |  | 0 | 0 | 0 | 9 | 1.5 | 1.5 | 0 | A02001-0024 | 0.4844 | 0.164 | 19.53 | 0 | 0
Okuma-Genos | 701-3-5/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.5025 | 0.223 | 39.2 | 0 | 0
Okuma-Genos | 701-4-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.5025 | 0.223 | 39.2 | 0 | 0
Okuma-Genos | 701-5-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.5025 | 0.223 | 39.2 | 0 | 0
Okuma-Genos | 701-6-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.5025 | 0.223 | 39.2 | 0 | 0
H1 | 701-A-BLNK |  | 0 | 0 | 0 | 42 | 2 | 2 | 0 | A02071-0034 | 0.5344 | 0.223 | 39.2 | 0 | 0
Okuma-Genos | 702-10-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-11-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-12-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-3-3/8 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-4-3/8 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-5-5/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-6-5/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-7-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-8-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 702-9-3/16 | Non Stnd | 0 | 0 | 0 | 15 | 2 | 2 | 0 | A02071-0040 | 0.7903 | 0.3221 | 54.25 | 0 | 0
H1 or Genos | 702-A-BLNK |  | 0 | 0 | 0 | 33 | 1 | 1 | 0 | A02071-0040 | 0.8392 | 0.3221 | 54.25 | 0 | 0
Okuma-Genos | 703-12-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 1.0974 | 0.562 | 54.25 | 0 | 0
Haas Vertical Mill VF3 | 703-12-3/16-5/8 | Non Stnd | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 703-12-3/16 | NA | 0.562 |  | 0
Okuma-Genos | 703-6-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 1.0974 | 0.562 | 54.25 | 0 | 0
Okuma-Genos | 703-8-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0040 | 1.0974 | 0.562 | 54.25 | 0 | 0
H1 | 703-A-BLNK |  | 0 | 0 | 0 | 29 | 2 | 2 | 0 | A02071-0040 | 1.162 | 0.562 | 54.25 | 0 | 0
Okuma-Genos | 705-12-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.3286 | 0.39 | 91.68 | 0 | 0
Haas Vertical Mill VF4 | 705-14-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | 705-A-BLNK | NA | 0.39 |  | 0
Okuma-Genos | 705-15-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.3286 | 0.39 | 91.68 | 0 | 0
Okuma-Genos | 705-16-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.3286 | 0.39 | 91.68 | 0 | 0
H1 | 705-A-BLNK |  | 0 | 0 | 0 | 34 | 2 | 2 | 0 | A02071-0052 | 1.4109 | 0.39 | 91.68 | 0 | 0
H1 | 706-A-BLNK |  | 0 | 0 | 0 | 31 | 7.5 | 7.5 | 1 | A02071-0056 | 1.5 | 0.35 | 106.33 | 0 | 0
H1/H4 | 707-A-BLNK |  | 0 | 0 | 0 | 21 | 2.5 | 2.5 | 0 | A02071-0072 | 3.7932 | 0.956 | 175.8 | 0 | 0
H4 | 708-A-BLNK |  | 0 | 0 | 0 | 17 | 2 | 2 | 0 | A02071-0096 | 7.8342 | 2.19 | 312.49 | 0 | 0
Haas Vertical Mill VF4 | 708-22-1/4 | Non Stnd | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 708-A-BLNK | NA | 2.19 |  | 0
Haas Vertical Mill VF4 | 7-2.5-30 | Non Stnd | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 7-2.5-F-BLNK | NA | 1 |  | 0
Okuma-Genos | 7-2.5-30 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.2739 | 1.163 | 195.85 | 0 | 0
H1 | 7-2.5-A-BLNK |  | 0 | 0 | 0 | 42 | 1 | 1 | 0 | A02071-0034 | 0.369 | 0.21 | 39.2 | 0 | 0
H1 | 7-2.5-C-BLNK |  | 0 | 0 | 0 | 43 | 1 | 1 | 0 | A02071-0040 | 0.788 | 0.37 | 54.25 | 0 | 0
H1 | 7-2.5-D-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0048 | 1.043 | 0.36 | 78.12 | 0 | 0
H1 | 7-2.5-E-BLNK |  | 0 | 0 | 0 | 30 | 1 | 1 | 0 | A02071-0056 | 1.582 | 0.47 | 106.33 | 0 | 0
H4 or M1 | 7-2.5-F-BLNK |  | 0 | 0 | 0 | 20 | 1 | 1 | 0 | A02071-0076 | 4.2739 | 2.5 | 195.85 | 0 | 0
Citizen | 7-3-A-BLNK |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0028 | 0.361 | 0.23 | 26.58 | 0 | 0
H1 | 7-3-B-BLNK |  | 0 | 0 | 0 | 34 | 2 | 2 | 0 | A02071-0032 | 0.3617 | 0.2011 | 34.72 | 0 | 0
Haas Vertical Mill VF3 | 7-3-18 | Non Stnd | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 7-3-E-BLNK | NA | 0.823 | 0.675 | 0
Haas Vertical Mill VF3 | 7-3-20 | Non Stnd | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 7-3-E-BLNK | NA | 0.66 |  | 0
Haas Vertical Mill VF3 | 7-4-10 | Non Stnd | 0 | 0 | 0 | 12 | 2 | 2 | 0 | 7-4-D-BLNK | NA | 0.675 |  | 0
Haas Vertical Mill VF3 | 7-4-11 | Non Stnd | 0 | 0 | 0 | 12 | 2 | 2 | 0 | 7-4-E-BLNK | NA | 0.418 |  | 0
Haas Vertical Mill VF3 | 7-4-23 | Non Stnd | 0 | 0 | 0 | 12 | 2 | 2 | 0 | 7-4-K-BLNK | NA | 0.54 |  | 0
Haas Vertical Mill VF3 | 7-4-24 | Non Stnd | 0 | 0 | 0 | 7 | 2 | 2 | 0 | 7-4-K-BLNK | NA | 0.54 |  | 0
H1 | 7-3-C-BLNK |  | 0 | 0 | 0 | 34 | 2 | 2 | 0 | A02071-0040 | 0.6512 | 0.273 | 54.25 | 0 | 0
M1 | 7-3-D-BLNK |  | 0 | 0 | 0 | 43 | 1 | 1 | 0 | A02071-0052 | 1.3483 | 0.4625 | 91.68 | 0 | 0
H1 or M1 | 7-3-E-BLNK |  | 0 | 0 | 0 | 21 | 1.5 | 1.5 | 0 | A02071-0068 | 2.9218 | 0.823 | 156.79 | 0 | 0
H4 | 7-3-F-BLNK |  | 0 | 0 | 0 | 14 | 1 | 1 | 0 | A02071-0076 | 11.7325 | 2.921 | 195.85 | 0 | 0
Citizen | 7-4-A-BLNK |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02071-0028 | 0.326 | 0.25 | 26.58 | 0 | 0
M1 | 7-4-B-BLNK | NON STND | 0 | 0 | 0 | 46 | 6 | 6 | 1 | A02071-0034 | 0.5991 | 0.291 | 39.2 | 0 | 0
H1 | 7-4-B-BLNK | STND | 0 | 0 | 0 | 43 | 2 | 2 | 0 | A02071-0034 | 0.488 | 0.291 | 39.2 | 0 | 0
M1 | 7-4-C-BLNK | NON STND | 0 | 0 | 0 | 41 | 1 | 1 | 0 | A02071-0040 | 0.6404 | 0.388 | 54.25 | 0 | 0
H1 | 7-4-C-BLNK | STND | 0 | 0 | 0 | 52 | 1 | 1 | 0 | A02071-0040 | 0.6404 | 0.388 | 54.25 | 0 | 0
M1 | 7-4-D-BLNK |  | 0 | 0 | 0 | 46 | 1 | 1 | 0 | A02071-0046 | 1.3613 | 0.675 | 71.75 | 0 | 0
M1 | 7-4-E-BLNK |  | 0 | 0 | 0 | 33 | 1.5 | 1.5 | 0 | A02071-0056 | 1.6703 | 0.54 | 106.33 | 0 | 0
H1 | 7-4-G-BLNK |  | 0 | 0 | 0 | 23 | 2 | 2 | 0 | A02071-0072 | 3.277 | 0.942 | 175.8 | 0 | 0
H4 | 7-4-J-BLNK |  | 0 | 0 | 0 | 14 | 1 | 1 | 0 | A02071-0112 | 11.7325 | 4.05 | 425.33 | 0 | 0
H4 | 7-4-K-BLNK |  | 0 | 0 | 0 | 17 | 3 | 3 | 0 | A02071-0088 | 6.3906 | 1.798 | 262.58 | 0 | 0 |  |  |  |  | Was 7-4-I-BLNK
H1 | 7-5-B-BLNK |  | 0 | 0 | 0 | 56 | 1 | 1 | 0 | A02071-0034 | 0.476 | 0.23 | 39.2 | 0 | 0
H1 | 7-5-C-BLNK |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0040 | 0.811 | 0.33 | 54.25 | 0 | 0
H1 | 7-6-A-BLNK |  | 0 | 0 | 0 | 41 | 1 | 1 | 0 | A02071-0036 | 0.5714 | 0.274 | 43.94 | 0 | 0
H1 | 7-6-B-BLNK |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0040 | 0.79 | 0.271 | 54.25 | 0 | 0
Okuma-Genos | 901-10-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.7489 | 0.51 | 91.68 | 0 | 0
Okuma-Genos | 901-12-3/16 | Non Stnd | 0 | 0 | 0 | 13 | 2 | 2 | 0 | A02071-0052 | 1.7489 | 0.542 | 91.68 | 0 | 0
Okuma-Genos | 901-13-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.7489 | 0.531 | 91.68 | 0 | 0
Okuma-Genos | 901-8-5/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.7489 | 0.57 | 91.68 | 0 | 0
Okuma-Genos | 901-9-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 1.7489 | 0.522 | 91.68 | 0 | 0
M1 or H1 | 901-A-BLNK |  | 0 | 0 | 0 | 35 | 2 | 2 | 0 | A02071-0052 | 1.8526 | 0.6225 | 91.68 | 0 | 0
Okuma-Genos | 902-10-5/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.96 | 0.771 | 106.33 | 0 | 0
Okuma-Genos | 902-12-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 2.0283 | 0.575 | 106.33 | 0 | 0
Okuma-Genos | 902-14-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.96 | 0.551 | 106.33 | 0 | 0
Okuma-Genos | 902-15-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 2.0283 | 0.54 | 106.33 | 0 | 0
Okuma-Genos | 902-16-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.96 | 0.771 | 106.33 | 0 | 0
Okuma-Genos | 902-19-3/16 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 2.0283 | 0.55 | 106.33 | 0 | 0
Okuma-Genos | 902-20-3/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0056 | 1.96 | 0.55 | 106.33 | 0 | 0
M1 | 902-A-BLNK |  | 0 | 0 | 0 | 34 | 0.5 | 0.5 | 0 | A02071-0056 | 2.1486 | 0.771 | 106.33 | 0 | 0
Okuma-Genos | 903-12-1/4 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0052 | 2.3508 | 1.16 | 91.68 | 0 | 0
Haas Vertical Mill VF3 | 903-10-1/4-9/8 |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 903-10-1/4 | NA | 0.94 |  | 0
M1 | 903-A-BLNK |  | 0 | 0 | 0 | 9 | 4 | 4 | 1 | A02071-0052 | 2.4857 | 1.16 | 91.68 | 0 | 0
H4 | 9-2.5-B-BLNK |  | 0 | 0 | 0 | 17 | 1 | 1 | 0 | A02071-0096 | 8.1782 | 2.2 | 312.49 | 0 | 0
Haas Vertical Mill VF3 | 9-3-26 | Non Stnd | 0 | 0 | 0 | 12 | 2 | 2 | 0 | 9-3-E-BLNK | NA | 1.06 |  | 0
H1 | 9-3-A-BLNK |  | 0 | 0 | 0 | 42 | 1 | 1 | 0 | A02071-0040 | 0.6103 | 0.366 | 54.25 | 0 | 0
M1 | 9-3-C-BLNK |  | 0 | 0 | 0 | 51 | 1 | 1 | 0 | A02071-0056 | 1.6703 | 0.6225 | 106.33 | 0 | 0
H1 | 9-3-D-BLNK |  | 0 | 0 | 0 | 28 | 2 | 2 | 0 | A02071-0068 | 3.0733 | 0.96 | 156.79 | 0 | 0
H4 or M1 | 9-3-E-BLNK |  | 0 | 0 | 0 | 24 | 2 | 2 | 0 | A02071-0076 | 4.3326 | 1.0766 | 195.85 | 0 | 0
Okuma-Genos | 9-3-26 | Non Stnd | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.3326 | 1.307 | 195.85 | 0 | 0
Haas Vertical Mill VF3 | 9-4-12 | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 9-4-F-BLNK | NA | 0.43 |  | 0
Haas Vertical Mill VF4 | 9-8-3 | Non Stnd | 0 | 0 | 0 | 12 | 1 | 1 | 0 | 9-8-A-BLNK | NA | 0.668 |  | 0
Haas Vertical Mill VF4 | 9-8-4 | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 9-8-A-BLNK | NA | 0.668 |  | 0
Haas Vertical Mill VF4 | 9-8-5 | Non Stnd | 0 | 0 | 0 | 8 | 1 | 1 | 0 | 9-8-A-BLNK | NA | 0.668 |  | 0
Haas Vertical Mill VF4 | 9-8-6 | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 9-8-B-BLNK | NA | 1.066 |  | 0
Haas Vertical Mill VF4 | 9-8-7 | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 9-8-B-BLNK | NA | 1.066 |  | 0
Haas Vertical Mill VF4 | 9-8-8 | Non Stnd | 0 | 0 | 0 | 5 | 1 | 1 | 0 | 9-8-B-BLNK | NA | 1.066 |  | 0
Haas Vertical Mill VF4 | 9-8-9 | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 9-8-C-BLNK | NA | 1.672 |  | 0
Haas Vertical Mill VF4 | 9-8-10 | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 9-8-C-BLNK | NA | 1.672 |  | 0
Haas Vertical Mill VF4 | 9-8-11 | Non Stnd | 0 | 0 | 0 | 19 | 1 | 1 | 0 | 9-8-C-BLNK | NA | 1.672 |  | 0
H1 | 9-4-A-BLNK |  | 0 | 0 | 0 | 36 | 2 | 2 | 0 | A02071-0036 | 0.7019 | 0.536 | 43.94 | 0 | 0
M1 | 9-4-D-BLNK |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0044 | 1.112 | 0.54 | 65.64 | 0 | 0
H1, M1 or Genos | 9-4-F-BLNK |  | 0 | 0 | 0 | 42 | 1.5 | 1.5 | 0 | A02071-0052 | 1.323 | 0.43 | 91.68 | 0 | 0
H1 | 9-4-G-BLNK |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 | A02071-0064 | 2.4454 | 0.8592 | 138.88 | 0 | 0
H1 or M1 | 9-4-H-BLNK |  | 0 | 0 | 0 | 22 | 1 | 1 | 0 | A02071-0072 | 3.5376 | 0.8492 | 175.8 | 0 | 0
H4 | 9-4-K-BLNK |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0112 | 12.3536 | 3.61 | 425.33 | 0 | 0
H4 | 9-4-L-BLNK |  | 0 | 0 | 0 | 14 | 1 | 1 | 0 | A02071-0088 | 6.461 | 2.0647 | 262.58 | 0 | 0 |  |  |  |  | Was 9-4-I-BLNK
H1 | 9-5-A-BLNK |  | 0 | 0 | 0 | 54 | 4 | 4 | 1 | A02071-0040 | 0.73 | 0.41 | 54.25 | 0 | 0
H1 | 9-5-B-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0048 | 1.472 | 0.71 | 78.12 | 0 | 0
H1 | 9-6-A-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0048 | 1.472 | 0.54 | 78.12 | 0 | 0
M1 | 9-8-A-BLNK |  | 0 | 0 | 0 | 27 | 6 | 6 | 1 | A02071-0060 | 2.1325 | 0.668 | 122.07 | 0 | 0
H4 | 9-8-B-BLNK |  | 0 | 0 | 0 | 18 | 6 | 6 | 1 | A02071-0076 | 4.0825 | 1.066 | 195.85 | 0 | 0
H4 | 9-8-C-BLNK |  | 0 | 0 | 0 | 14 | 6 | 6 | 1 | A02071-0096 | 7.8302 | 1.672 | 312.49 | 0 | 0
H2 | A10 |  | 0 | 0 | 0 | 40 | 1 | 1 | 0 | A02001-0044 | 0.2151 | 0.1 | 65.64 | 0 | 0
H2 | A12 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0044 | 0.2151 | 0.1 | 65.64 | 0 | 0
H2 | A15 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
H2 | A17 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0044 | 0.2151 | 0.1 | 65.64 | 0 | 0
H2 | A20 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
T42 or Cobra | A24001 (1/2) |  | 0 | 0 | 0 | 22 | 1 | 1 | 0 | A02002-0032 | 0.3124 | 0.1038 | 38.29 | 0 | 0
Cobra | A24001 (2/2) |  | 0 | 0 |  | 22 | 1 | 1 | 0 | A24001 (1/2) | 0.3124 |  |  | 0
T42 | A24010 (1/2) |  | 0 | 0 | 0 | 22 | 4 | 4 | 1 | A02001-0022 | 0.2352 | 0.0411 | 16.41 | 0 | 0
Cobra | A24010 (2/2) |  | 0 | 0 |  | 22 | 4 | 4 | 1 | A24010 (1/2) | NA |  |  | 0
T42 | A24023 (1/2) |  | 0 | 0 | 0 | 13 | 4 | 4 | 1 | A02002-0032 | 0.4476 | 0.132 | 38.29 | 0 | 0
Cobra | A24023 (2/2) |  | 0 | 0 |  | 13 | 4 | 4 | 1 | A24023 (1/2) | NA |  |  | 0
H2 | A25 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
H2 | A3 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
H2 | A30 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
Cut Off Saw | A3096-12 (1/2) |  | 0 | 0 | 0 | 72 | 0 | 0 | 0 | A02001-0010 | 0.2758 | 0.25 | 3.39 | 0 | 0
Caged Die Head | A3096-12 (2/2) |  | 0 | 0 |  | 192 | 1 | 1 | 0 | A3096-12 (1/2) | NA |  |  | 0
Cut Off Saw | A3096-14 (1/2) |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | A02001-0010 | 0.2758 | 0.25 | 3.39 | 0 | 0
Caged Die Head | A3096-14 (2/2) |  | 0 | 0 |  | 283 | 1 | 1 | 0 | A3096-14 (1/2) | NA |  |  | 0
B&S18 | A3193-1 |  | 0 | 0 | 0 | 144 | 8 | 8 | 1 | A02001-0024 | 0.0882 | 0.022 | 19.53 | 0 | 0
B&S18 | A3194-1 |  | 0 | 0 | 0 | 354 | 16 | 16 | 2 | A02001-0036 | 0.2303 | 0.06718 | 43.94 | 0 | 0
B&S18 | A3198-1 |  | 0 | 0 |  | 36 | 16 | 16 | 2 | A06202-0032 | 0.2147 | 0.119 | 36.43 | 0 | 0
H2 | A35 |  | 0 | 0 | 0 | 40 | 1 | 1 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
TAPPER-0056 | A3646-2 |  | 0 | 0 | 0 | 120 | 16 | 2 | 0 | A3646-2U | NA | 0.00502 |  | 0
Cut Off Saw | A3712-16 (1/4) |  | 0 | 0 | 0 | 60 | 16 | 2 | 0 | A02001-0014 | 0.736 | 0.7286 | 6.65 | 0 | 0
Lathe | A3712-16 (2/4) |  | 0 | 0 |  | 60 | 16 | 2 | 0 | A3712-16 (1/4) | NA |  |  | 0
Caged Die Head | A3712-16 (3/4) |  | 0 | 0 |  | 60 | 16 | 2 | 0 | A3712-16 (2/4) | NA |  |  | 0
Drill Press | A3712-16 (4/4) |  | 0 | 0 |  | 60 | 16 | 2 | 0 | A3712-16 (3/4) | NA |  |  | 0
Thread Roller | A3865-1-3.8 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | A3865U-3 | NA | 0.02256 |  | 0
Thread Roller | A3865-1-6 |  | 0 | 0 | 0 | 240 | 0 | 0 | 0 | A3865U-1 | NA | 0.03044 |  | 0
Drill Press-Deburr | A3942-1 | obsolete part | 0 | 0 | 0 | 190 | 1 | 1 | 0 | A3942-1-10 | NA | 0.01354 |  | 0
B&S18 | A3995-1 | Non Stnd | 0 | 0 | 0 | 650 | 16 | 16 | 2 | A02002-0026 | 0.05 | 0.00949 | 25.27 | 0 | 0
B&S18 | A3995-1-LF | Non Stnd | 0 | 0 | 0 | 519 | 16 | 16 | 2 | A03002-0026 | 0.05 | 0.00949 | 25.27 | 0 | 0
H2 | A40 |  | 0 | 0 | 0 | 40 | 1 | 1 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
B&S18 | A4014-1 |  | 0 | 0 | 0 | 20 | 16 | 16 | 2 | A06201-0028 | 0.1019 | 0.0259 | 25.29 | 0 | 0
B&S 18 | A4014-2 |  | 0 | 0 | 0 | 17 | 16 | 16 | 2 | A06201-0028 | 0.686 | 0.0259 | 25.29 | 0 | 0
B&S 18 | A4014-3 |  | 0 | 0 | 0 | 17 | 16 | 16 | 2 | A06201-0020 | 0.051 | 0.0105 | 12.9 | 0 | 0
Cut Off Saw | A4035-1 (1/2) |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-6U | NA | 0.0204 |  | 0
Caged Die Head | A4035-1 (2/2) |  | 0 | 0 |  | 192 | 1 | 1 | 0 | A4035-1 (1/2) | NA |  |  | 0
Bridgeport Drill Press | A4096-3 |  | 0 | 0 |  | 80 | 0.5 | 0.5 | 0 | A4096-4 | NA | 0.168 |  | 0
Citizen | A4-3-3 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A09201-0020 | 0.18 | 0.02 | 4.42 | 0 | 0
Hass Vertical Mill VF3 | A4-3-7 |  | 0 | 0 | 0 | 53 | 1 | 1 | 0 | A4-3-C-BLNK | NA | 0.02 |  | 0
H1 | A4-3-C-BLNK |  | 0 | 0 | 0 | 53 | 1 | 1 | 0 | A19101-0028 | 0.0954 | 0.036 | 8.485 | 0 | 0
Okuma-Cadet | A48001 (1/2) |  | 0 | 0 | 0 | 14 | 4 | 4 | 1 | A02002-0038 | 0.4721 | 0.121 | 54.03 | 0 | 0
Cobra | A48001 (2/2) |  | 0 | 0 |  | 22 | 4 | 4 | 1 | A48001 (1/2) | NA |  |  | 0
Okuma-Cadet | A48002 (1/2) |  | 0 | 0 | 0 | 13 | 4 | 4 | 1 | A02002-0038 | 0.52301 | 0.23501 | 54.03 | 0 | 0
Cobra | A48002 (2/2) |  | 0 | 0 |  | 13 | 2 | 2 | 0 | A48002 (1/2) | NA |  |  | 0
T42 | A48010(1/2) |  | 0 | 0 | 0 | 15 | 2 | 2 | 0 | A02001-0028 | 0.2763 | 0.0653 | 26.58 | 0 | 0
T42 | A48010(2/2) |  | 0 | 0 |  | 13 | 2 | 2 | 0 | A48010(1/2) | NA |  |  | 0
H2 | A50 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
B/S | A5004-1 |  | 0 | 0 | 0 | 70 | 16 | 16 | 2 | A02006-0005 | 0.0042 | 0.0042 | 0.23 | 0 | 0
Citizen 2 | A5007 |  | 0 | 0 | 0 | 33 | 16 | 16 | 2 | A06201-0012 | 0.0897 | 0.0603 | 4.65 | 0 | 0
B&S18- Backup Only | A5010 | NON STND--Backup Only | 0 | 0 | 0 | 115 | 8 | 8 | 1 | A06201-0008 | 0.0296 | 0.0283 | 2.06 | 0 | 0
B&S18 | A5012 (1/2) |  | 0 | 0 | 0 | 96 | 8 | 8 | 1 | A02001-0020 | 0.2536 | 0.1893 | 13.56 | 0 | 0 |  |  |  |  | Family 1
Drill Press Special | A5012 (2/2) |  | 0 | 0 |  | 240 | 1 | 1 | 0 | A5012 (1/2) | NA |  |  | 0
B&S18 | A5012-LF(1/2) |  | 0 | 0 | 0 | 48 | 8 | 8 | 1 | A03001-0020 | 0.2674 | 0.1893 | 13.56 | 0 | 0 |  |  |  |  | Family 1
Drill Press Special | A5012-LF(2/2) |  | 0 | 0 |  | 240 | 1 | 1 | 0 | A5012-LF(1/2) | NA |  |  | 0
T42 | A5012SS |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | A06201-0020 | 0.2722 | 0.176 | 12.9 | 0 | 0
Thread Roller | A5037-1-3 |  | 0 | 0 | 0 | 192 | 0.75 | 0.75 | 0 | A5037-1-3U | NA | 0.02702 |  | 0
Thread Roller | A5037-1-6 |  | 0 | 0 | 0 | 192 | 0.75 | 0.75 | 0 | A5037-1-6U | NA | 0.0555 |  | 0
B&S18 | A5128 (1/2) |  | 0 | 0 | 0 | 96 | 8 | 8 | 1 | A02001-0020 | 0.2333 | 0.1813 | 13.56 | 0 | 0 |  |  |  |  | Family 1
Drill Press Special | A5128 (2/2) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | A5128 (1/2) | NA | 0.0271 |  | 0
B&S18 | A5128-LF (1/2) |  | 0 | 0 | 0 | 144 | 16 | 16 | 2 | A03001-0020 | 0.2657 | 0.1864 | 13.56 | 0 | 0 |  |  |  |  | Family 1
Drill Press Special | A5128-LF (2/2) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | A5128-LF (1/2) | NA |  |  | 0
B&S18 | A5129 (1/2) |  | 0 | 0 | 0 | 96 | 8 | 8 | 1 | A02001-0020 | 0.2522 | 0.169 | 13.56 | 0 | 0 |  |  |  |  | Family 1
Drill Press Special | A5129 (2/2) |  | 0 | 0 |  | 240 | 1 | 1 | 0 | A5129 (1/2) | NA |  |  | 0
B&S18 | A5129-LF (1/2) |  | 0 | 0 | 0 | 96 | 8 | 8 | 1 | A03001-0020 | 0.2522 | 0.1565 | 13.56 | 0 | 0
Drill Press Special | A5129-LF (2/2) |  | 0 | 0 |  | 240 | 1 | 1 | 0 | A5129-LF (1/2) | NA |  |  | 0
B&S18-Backup only | A5171 | NON STND--Backup Only | 0 | 0 | 0 | 511 | 16 | 16 | 2 | A06201-0003 | 0.0008 | 0.00054 | 0.29 | 0 | 0
B&S18 | A5202-1 |  | 0 | 0 | 0 | 160 | 8 | 8 | 1 | A02001-0016 | 0.0119 | 0.001 | 8.68 | 0 | 0
B&S18 | A5202-1-LF |  | 0 | 0 | 0 | 80 | 8 | 8 | 1 | A03001-0016 | 0.008 | 0.001739 | 8.68 | 0 | 0
B&S18 | A5395-SR (1/3) |  | 0 | 0 | 0 | 134 | 8 | 8 | 1 | A02002-0024 | 0.2433 | 0.0829 | 21.54 | 0 | 0
B&S17 | A5395-SR (2/3) |  | 0 | 0 |  | 134 | 8 | 8 | 1 | A5395-SR (1/3) | NA |  |  | 0
Haas Vertical Mill VF4 | A5395-SR (3/3) |  | 0 | 0 |  | 13 | 1.25 | 1.25 | 0 | A5395-SR (2/3) | NA |  |  | 0
H2 | A8 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
H2 | AA-BLNK |  | 0 | 0 | 0 | 15 | 2 | 2 | 0 | A06101-0044 | 0.114 | 0.093 | 62.46 | 0 | 0
H2 | A-BLNK |  | 0 | 0 | 0 | 18 | 2 | 2 | 0 | A02001-0044 | 0.185 | 0.1 | 65.64 | 0 | 0
B&S17 | AP2503 (2/2) | Non Stnd | 0 | 0 |  | 192 | 4 | 4 | 1 | AP2503 (1/2) | NA |  |  | 0
B&S17 | AP5003 (2/2) | Non Stnd | 0 | 0 |  | 100 | 4 | 4 | 1 | AP5003 (1/2) | NA |  |  | 0
B&S17 | AP7501(2/4) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | AP7501(1/4) | NA |  |  | 0
4 Way | AP7501(3/4) |  | 0 | 0 |  | 240 | 4 | 4 | 1 | AP7501(2/4) | NA |  |  | 0
Hass Vertical Mill VF3 | AP7501(4/4) |  | 0 | 0 |  | 120 | 4 | 4 | 1 | AP7501(3/4) | NA |  |  | 0
B&S17 | AP7502(2/2) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | AP7502(1/2) | NA |  |  | 0
H2 | AR15 |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 | A02001-0044 | 0.8565 | 0.1235 | 65.64 | 0 | 0
H2 | AR17 |  | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02001-0044 | 0.8565 | 0.1235 | 65.64 | 0 | 0
H2 | AR25 |  | 0 | 0 | 0 | 24 | 1 | 1 | 0 | A02001-0044 | 0.8565 | 0.1235 | 65.64 | 0 | 0
H2 | AR50 |  | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02001-0044 | 0.8565 | 0.1235 | 65.64 | 0 | 0
H2 | AR-BLNK |  | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02001-0044 | 0.908 | 0.28 | 65.64 | 0 | 0
LB3000 | ASC-11 | Stnd | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02071-0052 | 2.5329 | 0.817 | 91.68 | 0 | 0
H1 or H3 | ASC-11 (1/2) | Non Stnd | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02071-0052 | 1.74 | 0.817 | 91.68 | 0 | 0
H2 | ASC-11 (2/2) | Non Stnd | 0 | 0 |  | 20 | 1 | 1 | 0 | ASC-11 (1/2) | NA |  |  | 0
H1 or H3 | ASC-13 (1/2) |  | 0 | 0 | 0 | 11 | 1 | 1 | 0 | A02071-0060 | 3.074 | 1.112 | 122.07 | 0 | 0
H2 | ASC-13 (2/2) |  | 0 | 0 |  | 20 | 1 | 1 | 0 | ASC-13 (1/2) | NA |  |  | 0
LB3000 | ASC-5 | Stnd | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02071-0024 | 0.14 | 0.054 | 19.53 | 0 | 0
H1 or H3 | ASC-5 (1/2) | Non Stnd | 0 | 0 | 0 | 36 | 3 | 3 | 0 | A02071-0024 | 0.14 | 0.054 | 19.53 | 0 | 0
H2 | ASC-5 (2/2) | Non Stnd | 0 | 0 |  | 36 | 2 | 2 | 0 | ASC-5 (1/2) | NA |  |  | 0
LB3000 | ASC-7 | Stnd | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02071-0032 | 0.6144 | 0.19 | 34.72 | 0 | 0
H1 or H3 | ASC-7 (1/2) | Non Stnd | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02071-0032 | 0.547 | 0.19 | 34.72 | 0 | 0
H2 | ASC-7 (2/2) | Non Stnd | 0 | 0 |  | 44 | 1 | 1 | 0 | ASC-7 (1/2) | NA |  |  | 0
Okuma-Genos | ASC-9 | Stnd | 0 | 0 | 0 | 44 | 1 | 1 | 0 | A02071-0044 | 0.942 | 0.46 | 65.64 | 0 | 0
H1 or H3 | ASC-9 (1/2) | Non Stnd | 0 | 0 | 0 | 15 | 3 | 3 | 0 | A02071-0044 | 0.942 | 0.46 | 65.64 | 0 | 0
H2 | ASC-9 (2/2) | Non Stnd | 0 | 0 |  | 26 | 2 | 2 | 0 | ASC-9 (1/2) | NA |  |  | 0
Drill Press | B0700-2 |  | 0 | 0 | 0 | 240 | 0.16 | 0.16 | 0 | B0700-1-LF | NA | 0.578 |  | 0
Dedicated Mill | B1001-1(2/2) |  | 0 | 0 |  | 18 | 2 | 2 | 0 | B1001-1(1/2) | NA |  |  | 0
Dedicated Mill | B1001-1-LF(2/2) |  | 0 | 0 |  | 30 | 2 | 2 | 0 | B1001-1-LF(1/2) | NA |  |  | 0
FLOAT TAPPER-0055 | B3051-1 | Purchased | 0 | 0 |  | 240 | 0.5 | 0.5 | 0 | B3051-1U | NA |  |  | 0
Drill Press | B3056-1 |  | 0 | 0 | 0 | 240 | 1 | 1 | 0 | B3056-1U | NA | 0.00292 |  | 0
Cut Saw | B3132-1(1/2) |  | 0 | 0 |  | 240 | 0.5 | 0.5 | 0 | C3000-1-7.150 | NA |  |  | 0
Thread Roller | B3132-1(2/2) |  | 0 | 0 |  | 240 | 0.5 | 0.5 | 0 | B3132-1(1/2) | NA |  |  | 0
B&S18 | B3211-1 |  | 0 | 0 | 0 | 48 | 16 | 16 | 2 | A02002-0026 | 0.353 | 0.1085 | 25.27 | 0 | 0
B&S18 | B3212-1 (1/2) |  | 0 | 0 | 0 | 128 | 8 | 8 | 1 | A02001-0028 | 0.2203 | 0.068 | 26.58 | 0 | 0
B&S16 | B3212-1 (2/2) |  | 0 | 0 |  | 99 | 4 | 4 | 1 | B3212-1 (1/2) | NA |  |  | 0
B&S18 | B3222-2 |  | 0 | 0 | 0 | 64 | 12 | 12 | 2 | A02001-0020 | 0.0812 | 0.0342 | 13.56 | 0 | 0
B&S18 | B3222-3 (1/2) |  | 0 | 0 | 0 | 13 | 1.5 | 1.5 | 0 | A02001-0024 | 0.1426 | 0.03361 | 19.53 | 0 | 0
B&S17 | B3222-3 (2/2) |  | 0 | 0 |  | 64 | 12 | 12 | 2 | B3222-3 (1/2) | NA |  |  | 0
B&S18 | B3222-3-LF |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A03001-0024 | 0.1426 | 0.0036 | 19.53 | 0 | 0
Cobra | B3222-4-LF |  | 0 | 0 | 0 | 2 | 16 | 16 | 2 | A03002-0028 | 0.2477 | 0.0492 | 29.31 | 0 | 0
Tapper | B3246-1 | purchased | 0 | 0 |  | 411 | 16 | 16 | 2 | B3246U-1 | NA |  |  | 0
Tapper | B3246-2 | purchased | 0 | 0 |  | 240 | 1 | 1 | 0 | B3246-2U | NA |  |  | 0
Tapper | B3246-3 | purchased | 0 | 0 |  | 240 | 1 | 1 | 0 | B3246-3U | NA |  |  | 0
Bridgeport Drill Press | B3432-1 | purchased | 0 | 0 |  | 240 | 0.16 | 0.16 | 0 | B3432-1U | NA |  |  | 0
B&S18 | B3451-1 |  | 0 | 0 | 0 | 144 | 16 | 16 | 2 | A02002-0014 | 0.0801 | 0.0363 | 7.33 | 0 | 0
B&S18 | B3452-1 |  | 0 | 0 | 0 | 144 | 16 | 16 | 2 | A02002-0018 | 0.1539 | 0.0582 | 12.11 | 0 | 0
B&S18 | B3453-1 |  | 0 | 0 | 0 | 332 | 16 | 16 | 2 | A02002-0022 | 0.2336 | 0.0938 | 18.1 | 0 | 0
B&S18 | B3453-1-LF |  | 0 | 0 | 0 | 48 | 8 | 8 | 1 | A03002-0022 | 0.2175 | 0.0938 | 18.1 | 0 | 0
Cobra | B3454-1-LF |  | 0 | 0 | 0 | 2 | 16 | 16 | 2 | A03002-0026 | 0.3129 | 0.137 | 25.27 | 0 | 0
FLOAT TAPPER-0055 | B3496-2 |  | 0 | 0 | 0 | 22 | 1 | 1 | 0 | B3496-2U | NA | 0.01876 |  | 0
B/S 17 | B3687-5(2/3) |  | 0 | 0 |  | 131 | 4 | 4 | 1 | B3687-5(1/3) | NA |  |  | 0
CNC Bridgeport | B3687-5(3/3) |  | 0 | 0 |  | 38 | 3 | 3 | 0 | B3687-5(2/3) | NA |  |  | 0
B/S 17 | B3687-5-LF(2/3) |  | 0 | 0 |  | 131 | 4 | 4 | 1 | B3687-5-LF(1/3) | NA |  |  | 0
CNC Bridgeport | B3687-5-LF(3/3) |  | 0 | 0 |  | 38 | 3 | 3 | 0 | B3687-5-LF(2/3) | NA |  |  | 0
Cut Off Saw | B5025U-2 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | B5025-1 | NA | 0.0262 |  | 0
Thread Roller | B5025-2 |  | 0 | 0 |  | 192 | 1 | 1 | 0 | B5025U-2 | NA |  |  | 0
B&S17 | BDV20015(2/2) | obsolete | 0 | 0 |  | 80 | 2 | 2 | 0 | BDV20015(1/2) | NA |  |  | 0
B&S17 | BDV20016(2/2) |  | 0 | 0 |  | 80 | 2 | 2 | 0 | BDV20016(1/2) | NA |  |  | 0
H3 | BF1201 | Backup for Davenport | 0 | 0 | 0 | 26 | 16 | 16 | 2 | A02002-0014 | 0.051 | 0.03568 | 7.33 | 0 | 0
H2 | C-BLNK |  | 0 | 0 | 0 | 47 | 1 | 1 | 0 | A02001-0036 | 0.124 | 0.623 | 43.94 | 0 | 0
H2 | C1 |  | 0 | 0 | 0 | 25 | 1 | 1 | 0 | A02001-0036 | 0.144 | 0.06995 | 43.94 | 0 | 0
H2 | C10 |  | 0 | 0 | 0 | 42 | 2 | 2 | 0 | A02001-0036 | 0.144 | 0.06995 | 43.94 | 0 | 0
H2 | C12 |  | 0 | 0 | 0 | 25 | 1 | 1 | 0 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 0 | 0
H2 | C15 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0036 | 0.144 | 0.06995 | 43.94 | 0 | 0
H2 | C15A |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A06101-0036 | 0.137 | 0.06995 | 40.56 | 0 | 0
H2 | C17 |  | 0 | 0 | 0 | 25 | 1 | 1 | 0 | A02001-0036 | 0.144 | 0.06995 | 43.94 | 0 | 0
H2 | C2 |  | 0 | 0 | 0 | 25 | 1 | 1 | 0 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 0 | 0
H2 | C20 |  | 0 | 0 | 0 | 25 | 1 | 1 | 0 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 0 | 0
H2 | C3 |  | 0 | 0 | 0 | 31 | 3 | 3 | 0 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 0 | 0
H2 | C30 |  | 0 | 0 | 0 | 31 | 3 | 3 | 0 | A02001-0036 | 0.124 | 0.06995 | 43.94 | 0 | 0
H2 | C4 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0036 | 0.124 | 0.065 | 43.94 | 0 | 0
H2 | C40 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0036 | 0.124 | 0.065 | 43.94 | 0 | 0
H2 | C5 |  | 0 | 0 | 0 | 25 | 1 | 1 | 0 | A02001-0036 | 0.124 | 0.065 | 43.94 | 0 | 0
H2 | C50 |  | 0 | 0 | 0 | 25 | 1 | 1 | 0 | A02001-0036 | 0.124 | 0.065 | 43.94 | 0 | 0
H2 | C6 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0036 | 0.144 | 0.065 | 43.94 | 0 | 0
H2 | C8 |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0036 | 0.144 | 0.065 | 43.94 | 0 | 0
Cut Off Saw | C3000-1-2.4U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-3U | NA | 0.010088 |  | 0
Thread Roller | C3000-1-2.4 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-2.4U | NA | 0.010088 |  | 0
Thread Roller | C3000-1-2.5 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-2.5U | NA | 0.010088 |  | 0
Cut Off Saw | C3000-1-2.5U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-3U | NA | 0.010088 |  | 0
Cut Off Saw | C3000-1-2.78U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-6U | NA | 0.00196 |  | 0
Thread Roller | C3000-1-2.78 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-2.78U (A) | NA | 0.00196 |  | 0
Cut Off Saw | C3000-1-2 (1/2) |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-3U | NA | 0.002 |  | 0
Thread Roller | C3000-1-2 (2/2) |  | 0 | 0 |  | 192 | 1 | 1 | 0 | C3000-1-2 (1/2) | NA |  |  | 0
Thread Roller | C3000-1-3 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-3U | NA | 0.01198 |  | 0
Cut Off Saw | C3000-1-4U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-4.5U | NA | 0.018 |  | 0
Thread Roller | C3000-1-4 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-4U | NA | 0.018 |  | 0
Cut Off Saw | C3000-1-4.25U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-4.5U | NA | 0.019 |  | 0
Thread Roller | C3000-1-4.25 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-4.25U | NA | 0.019 |  | 0
Cut Off Saw | C3000-1-4.30U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-4.5U | NA | 0.019 |  | 0
Thread Roller | C3000-1-4.30 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-4.30U | NA | 0.019 |  | 0
Thread Roller | C3000-1-4.5 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-4.5U | NA | 0.0204 |  | 0
Thread Roller | C3000-1-5.90 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-5.90U | NA | 0.0247 |  | 0
Cut Off Saw | C3000-1-5.90U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-6U | NA | 0.0247 |  | 0
Thread Roller | C3000-1-6 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-6U | NA | 0.02782 |  | 0
Thread Roller | C3000-1-8.90 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-1-8.90U | NA | 0.042 |  | 0
Cut Off Saw | C3000-3-2.780U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-6U | NA | 0.013 |  | 0
Lathe-0467 | C3000-3-2.780 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-2.780U | NA | 0.013 |  | 0
Lathe-0467 | C3000-3-2.8 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-2.8U | NA | 0.0165 |  | 0
Cut Off Saw | C3000-3-3.4U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-6U | NA | 0.0165 |  | 0
Lathe-0467 | C3000-3-3.4 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-3.4U | NA | 0.0165 |  | 0
Cut Off Saw | C3000-3-3U |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-6U | NA | 0.0166 |  | 0
Lathe-0467 | C3000-3-3 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-3U | NA | 0.0166 |  | 0
Cut Off Saw | C3000-3-4.600 (1/2) |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-6U | NA | 0.017 |  | 0
Lathe-0467 | C3000-3-4.600 (2/2) |  | 0 | 0 |  | 192 | 1 | 1 | 0 | C3000-3-4.600 (1/2) | NA |  |  | 0
Lathe-0467 | C3000-3-6 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | C3000-3-6U | NA | 0.03075 |  | 0
Hardinge-Lathe | C3838005-1 |  | 0 | 0 | 0 | 240 | 1 | 1 | 0 | C3838005 | NA | 0.00122 |  | 0
Lathe 0468 | C3838005-2 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | C3838005 | NA | 0.001185 |  | 0
Hardinge-Lathe | C3838005-3 |  | 0 | 0 | 0 | 240 | 1 | 1 | 0 | C3838005 | NA | 0.00119 |  | 0
Ganesh CNC | C3838B22 | Non Stnd | 0 | 0 | 0 | 15 | 3.5 | 3.5 | 0 | A02002-0026 | 0.3518 | 0.0957 | 25.27 | 0 | 0 |  |  |  |  | Hydromat
Okuma-Cadet or H3 | C3838B22 (1/3) | Non Stnd | 0 | 0 | 0 | 15 | 3.5 | 3.5 | 0 | A02002-0026 | 0.3701 | 0.0957 | 25.27 | 0 | 0 |  |  |  |  | Hydromat
Cobra | C3838B22 (2/3) | Non Stnd | 0 | 0 |  | 26 | 2 | 2 | 0 | C3838B22 (1/3) | NA |  |  | 0 | [5 empty] | Hydromat
Hass Vertical Mill VF3 | C3838B22 (3/3) | Non Stnd | 0 | 0 |  | 240 | 2 | 2 | 0 | C3838B22 (2/3) | NA |  |  | 0 | [5 empty] | Hydromat
Okuma-Cadet | C3850001 (1/3) | STND | 0 | 0 | 0 | 6 | 2 | 2 | 0 | A02002-0028 | 0.6598 | 0.24672 | 29.31 | 0 | 0
Cobra | C3850001 (2/3) | STND | 0 | 0 |  | 27 | 1.5 | 1.5 | 0 | C3850001 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | C3850001 (3/3) | STND | 0 | 0 |  | 23 | 1 | 1 | 0 | C3850001 (2/3) | NA |  |  | 0
Hass Vertical Mill VF3 | C3850001 | non stnd | 0 | 0 | 0 | 23 | 1 | 1 | 0 | C3850001-00 | NA | 0.24672 |  | 0
Hass Vertical Mill VF3 | C3850001 | STND | 0 | 0 | 0 | 23 | 1 | 1 | 0 | C3850001-10 | NA | 0.24672 |  | 0
Hass Vertical Mill VF3 | C3850001-00 |  | 0 | 0 |  | 240 | 2 | 2 | 0 | C3850001-10 | NA |  |  | 0
Cadet or Cobra | C3850001-10 (1/2) | NON STND | 0 | 0 | 0 | 6 | 2 | 2 | 0 | A02002-0028 | 0.6482 |  | 29.31 | 0 | 0
Cobra | C3850001-10 (2/2) | NON STND | 0 | 0 |  | 6 | 2 | 2 | 0 | C3850001-10 (1/2) | NA |  |  | 0
Hass Vertical Mill VF3 | C5038B22 | non stnd | 0 | 0 | 0 | 240 | 2 | 2 | 0 | C5038B22-00 | NA | 0.104 |  | 0
Okuma-Cadet | C5038B22 (1/3) | STND | 0 | 0 | 0 | 13 | 15 | 15 | 2 | A02002-0022 | 0.33 | 0.104 | 18.1 | 0 | 0
Okuma-Cadet | C5038B22 (2/3) |  | 0 | 0 |  | 13 | 3 | 3 | 0 | C5038B22 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | C5038B22 (3/3) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | C5038B22 (2/3) | NA |  |  | 0
Hass Vertical Mill VF3 | C5050001-02 |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | C5050001-00 | NA | 0.232 |  | 0
VF3 or B/P CNC Mill | C5050001-5 |  | 0 | 0 | 0 | 24 | 3 | 3 | 0 | C5050001-10 | NA | 0.232 |  | 0
Lathe -0468 | C5050006-2 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | C5050006 | NA | 0.002495 |  | 0
Lathe -0468 | C5050006-3 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | C5050006 | NA | 0.002495 |  | 0
Lathe -0468 | C5050006-4 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | C5050006 | NA | 0.002495 |  | 0
Lathe -0468 | C5050006-5 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | C5050006 | NA | 0.002495 |  | 0
Lathe -0468 | C5050006-6 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | C5050006 | NA | 0.002495 |  | 0
Ganesh CNC | C5087B21 | Stnd | 0 | 0 | 0 | 36 | 16 | 16 | 2 | A02002-0036 | 0.904 | 0.245 | 48.45 | 0 | 0
Okuma-Cadet | C5087B21-10 (1/2) | Non Stnd | 0 | 0 | 0 | 6 | 2 | 2 | 0 | A02002-0036 | 0.904 | 0.245 | 48.45 | 0 | 0
Cobra | C5087B21-10 (2/2) | Non Stnd | 0 | 0 |  | 27 | 1.5 | 1.5 | 0 | C5087B21-10 | NA |  |  | 0
Hass Vertical Mill VF3 | C5087B21 | Stnd | 0 | 0 | 0 | 240 | 2 | 2 | 0 | C5087B21-10 | NA | 0.245 |  | 0
4 Way | C5087B21 (1/2) | Alternate | 0 | 0 | 0 | 240 | 2 | 2 | 0 | C5087B21-10 | NA | 0.245 |  | 0
Haas Vertical Mill VF4 | C5087B21 (2/2) | Alternate | 0 | 0 |  | 12 | 16 | 16 | 2 | C5087B21 (1/2) | NA |  |  | 0
Ganesh CNC | C7510001 | Stnd | 0 | 0 | 0 | 36 | 16 | 16 | 2 | A02002-0042 | 1.9915 | 0.921 | 65.95 | 0 | 0
H3 or H1 | C7510001-10 (1/2) |  | 0 | 0 | 0 | 12 | 16 | 16 | 2 | A02002-0042 | 1.9915 | 0.921 | 65.95 | 0 | 0
Cobra or H1 | C7510001-10 (2/2) |  | 0 | 0 |  | 4 | 5 | 5 | 1 | C7510001-10 (1/2) | NA |  |  | 0
Ganesh CNC | C7510001-00 | Stnd | 0 | 0 | 0 | 36 | 16 | 16 | 2 | A02002-0042 | 1.9915 | 0.921 | 65.95 | 0
Hass Vertical Mill VF3 | C7510001-00 | Non Stnd | 0 | 0 | 0 | 36 | 16 | 16 | 2 | C7510001-10 | NA | 0.921 |  | 0
Hass Vertical Mill VF3 | C7510001 | non Stnd | 0 | 0 | 0 | 20 | 2 | 2 | 0 | C7510001-10 | NA | 0.921 |  | 0
Cobra | C7550001-10 (1/2) |  | 0 | 0 |  | 36 | 16 | 16 | 2 | A02002-0036 | 1.1601 | 0.325 | 48.45 | 0 | 0
H3 | C7550001-10 (2/2) |  | 0 | 0 |  | 4 | 5 | 5 | 1 | C7550001-10 (1/2) | NA |  |  | 0
Hass Vertical Mill VF3 | C7550001 |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | C7550001-10 | NA | 0.325 |  | 0
Hass Vertical Mill VF3 | C7550001-02 |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | C7550001-10 | NA | 0.325 |  | 0
Hass Vertical Mill VF3 | C7575001 | Non Stnd | 0 | 0 | 0 | 240 | 2 | 2 | 0 | C7575001-00 | NA | 0.681 |  | 0
H3 | C7575001 (1/3) |  | 0 | 0 | 0 | 12 | 4 | 4 | 1 | A02002-0036 | 1.4448 | 0.681 | 48.45 | 0 | 0
Cobra | C7575001 (2/3) | Hydromat | 0 | 0 |  | 27 | 1.5 | 1.5 | 0 | C7575001 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | C7575001 (3/3) | Hydromat | 0 | 0 |  | 20 | 2 | 2 | 0 | C7575001 (2/3) | NA |  |  | 0
Haas Vertical Mill VF3 | C7575001-02 |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | C7575001-00 | NA | 0.681 |  | 0
H2 | CA-BLNK |  | 0 | 0 | 0 | 18 | 2 | 2 | 0 | A06131-0038 | 0.137 | 0.069 | 45.23 | 0 | 0
C2 | CH01-3-3-16 |  | 0 | 0 | 0 | 30 | 1 | 1 | 0 | A02072-0024 | 0.2237 | 0.091 | 21.54 | 0 | 0
C2 | CH01-4-3/16 |  | 0 | 0 | 0 | 30 | 1 | 1 | 0 | A02072-0024 | 0.2237 | 0.091 | 21.54 | 0 | 0
C2 | CH01-4-5/32 |  | 0 | 0 | 0 | 34 | 1 | 1 | 0 | A02072-0024 | 0.2144 | 0.091 | 21.54 | 0 | 0
C2 | CH01-6-144 |  | 0 | 0 | 0 | 30 | 1 | 1 | 0 | A02072-0024 | 0.2237 | 0.101 | 21.54 | 0 | 0
C2 | CH01-8-3/16 |  | 0 | 0 | 0 | 30 | 1 | 1 | 0 | A02072-0024 | 0.2237 | 0.091 | 21.54 | 0 | 0
C2 | CH01-A-BLNK | stnd | 0 | 0 | 0 | 48 | 1 | 1 | 0 | A02072-0024 | 0.2237 | 0.11 | 21.54 | 0 | 0 | [8 empty] | 0 | A02072-0024 | 0.2237 | #N/A | #REF! | #REF!
C2 | CHAT01 | STND | 0 | 0 | 0 | 84 | 4 | 4 | 1 | A02002-0024 | 0.2127 | 0.074 | 21.54 | 0 | 0
T-42 | CHAT01 (1/2) | Non STND | 0 | 0 | 0 | 84 | 4 | 4 | 1 | A02002-0024 | 0.1842 | 0.074 | 21.54 | 0 | 0
Cobra | CHAT01 (2/2) | NON STND | 0 | 0 |  | 84 | 4 | 4 | 1 | CHAT01 (1/2) | 0.1973 |  |  | 0
LB3000 or H2 | CR10 | NON STND | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.6441 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR12 |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.55 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR15 |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.5218 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR17 |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.55 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR20 |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.55 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR30 |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.55 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR30 | STND | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.5806 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR6 |  | 0 | 0 | 0 | 28 | 1 | 1 | 0 | A02001-0040 | 0.55 | 0.118 | 54.25 | 0 | 0
LB3000 or H2 | CR-BLNK |  | 0 | 0 | 0 | 22 | 1 | 1 | 0 | A02001-0040 | 0.55 | 0.118 | 54.25 | 0 | 0
H2 | CR50A-135 |  | 0 | 0 | 0 | 84 | 4 | 4 | 1 | A06101-0038 | 0.4242 | 0.093 | 46.59 | 0 | 0
T42 | CRV7503(1/2) |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A06201-0036 | 0.354 | 0.0426 | 40.56 | 0 | 0 |  |  |  |  | 2018
Cobra | CRV7503(2/2) |  | 0 | 0 |  | 22 | 8 | 8 | 1 | CRV7503(1/2) | NA |  |  | 0 | [5 empty] | 2018
Citizen 1 | CRV7505 | Stnd | 0 | 0 | 0 | 14 | 8 | 8 | 1 | A06201-0016 | 0.0361 | 0.008 | 8.26 | 0 | 0 |  |  |  |  | 2018
T42 or Cobra | CRV7505 (1/2) | Non Stnd | 0 | 0 | 0 | 14 | 8 | 8 | 1 | A06201-0016 | 0.0361 | 0.008 | 8.26 | 0 | 0 |  |  |  |  | 2018
Hass Vertical Mill VF3 | CRV7505 (2/2) | Non Stnd | 0 | 0 |  | 22 | 8 | 8 | 1 | CRV7505 (1/2) | NA
H1 | CRV7507 |  | 0 | 0 | 0 | 11 | 8 | 8 | 1 | A06201-0064 | 0.9506 | 0.0426 | 128.2 | 0 | 0 |  |  |  |  | 2018
H3 | CRV7510(1/2) |  | 0 | 0 | 0 | 11 | 8 | 8 | 1 | A06201-0054 | 0.2622 | 0.133 | 91.5 | 0 | 0 |  |  |  |  | 2018
Hass Vertical Mill VF4 | CRV7510(2/2) |  | 0 | 0 |  | 22 | 8 | 8 | 1 | CRV7510(1/2) | NA |  |  | 0 | [5 empty] | 2018
H1 or H3 | CRV7512 | will be purchased | 0 | 0 | 0 | 18 | 8 | 8 | 1 | A06201-0052 | 0.3632 | 0.038 | 84.62 | 0 | 0 |  |  |  |  | 2018
H3 | CS1201 | backup only-nonstnd | 0 | 0 | 0 | 50 | 16 | 16 | 2 | A02002-0014 | 0.0402 | 0.01875 | 7.33 | 0 | 0
Cobra | CS2501 | backup only | 0 | 0 | 0 | 50 | 16 | 16 | 2 | A02002-0018 | 0.0785 | 0.0331 | 12.11 | 0 | 0
B&S18 | CS2502 |  | 0 | 0 | 0 | 131 | 16 | 16 | 2 | A02001-0012 | 0.0249 | 0.006 | 4.88 | 0 | 0
Hass Vertical Mill VF3 | CTM30 |  | 0 | 0 | 0 | 54 | 1.5 | 1.5 | 0 | CTM30-10 | NA | 0.11708 |  | 0
H3 | CY10110 | Backup Only | 0 | 0 | 0 | 8 | 8 | 8 | 1 | A02001-0010 | 0.219 | 0.0042 | 3.39 | 0 | 0
Citizen 1 | CY10111 | Backup Only | 0 | 0 | 0 | 8 | 8 | 8 | 1 | A02001-0016 | 0.0383 | 0.005 | 8.68 | 0 | 0
Cobra | CY10111 | Backup Only | 0 | 0 | 0 | 8 | 8 | 8 | 1 | A02001-0016 | 0.0428 | 0.005 | 8.68 | 0 | 0
T42 | CY10112 | Backup Only | 0 | 0 | 0 | 8 | 8 | 8 | 1 | A02001-0008 | 0.0064 | 0.0007 | 2.17 | 0 | 0
Cobra | CY10115 | Backup Only | 0 | 0 | 0 | 8 | 8 | 8 | 1 | A02001-0010 | 0.0097 | 0.002 | 3.39 | 0 | 0
Bridgeport CNC Mill | CY11101(2/2) |  | 0 | 0 |  | 240 | 1 | 1 | 0 | CY11101(1/2) | NA |  |  | 0
Bridgeport Drill Press | CY12001 (2/2) | backup only | 0 | 0 |  | 19 | 0.4 | 0.4 | 0 | CY12001 (2/2) | NA |  |  | 0
Ganesh CNC | CY12001 | Stnd | 0 | 0 | 0 | 19 | 0.4 | 0.4 | 0 | A02002-0042 | 0.6601 | 0.198 | 65.95 | 0 | 0
H3 | CY12010 (1/2) |  | 0 | 0 | 0 | 10 | 0.4 | 0.4 | 0 | A01002-0042 | 0.532 | 0.203 | 60.9 | 0 | 0 |  |  |  |  | 2018
Hass Vertical Mill VF3 | CY12010 (2/2) |  | 0 | 0 |  | 40 | 2 | 2 | 0 | CY12010 (1/2) | NA |  |  | 0
H2 | CY12012 |  | 0 | 0 | 0 | 22 | 0.4 | 0.4 | 0 | A02001-0032 | 0.1746 | 0.1 | 34.72 | 0 | 0 |  |  |  |  | 2018
H2 | CY12013 |  | 0 | 0 | 0 | 80 | 0.4 | 0.4 | 0 | A02001-0028 | 0.2604 | 0.2 | 26.58 | 0 | 0 |  |  |  |  | 2018
Cobra | CY12002 |  | 0 | 0 | 0 | 27 | 1 | 1 | 0 | A02001-0032 | 0.0808 | 0.011928 | 34.72 | 0 | 0
Okuma-LB3000 | CY12501 |  | 0 | 0 | 0 | 15 | 1 | 1 | 0 | A02031-0038 | 0.5434 | 0.233 | 49 | 0 | 0
T42 | CY12503 |  | 0 | 0 |  | 27 | 1 | 1 | 0 | A02001-0012 | 0.0214 | 0.014 | 4.88 | 0 | 0
T42 | CY12503-LF |  | 0 | 0 |  | 27 | 1 | 1 | 0 | A03001-0012 | 0.026 | 0.014 | 4.88 | 0 | 0
Okuma-Genos | CY16501 |  | 0 | 0 | 0 | 12 | 16 | 16 | 2 | A19101-0044 | 0.27272 | 0.27272 | 1.746 | 0 | 0
Okuma-Cadet | CY30001 (1/2) | Non Stnd | 0 | 0 | 0 | 8 | 4 | 4 | 1 | A06101-0040 | 0.4625 | 0.00381 | 50.08 | 0 | 0
T42 | CY30001 (2/2) | Non Stnd | 0 | 0 |  | 16 | 2 | 2 | 0 | CY30001 (1/2) | NA |  |  | 0
Citizen 2 | CY90001 | Stnd | 0 | 0 | 0 | 16 | 2 | 2 | 0 | A02002-0024 | 0.229 | 0.1179 | 21.54 | 0 | 0
Cobra | CY90001 (1/2) | Non Stnd | 0 | 0 | 0 | 16 | 2 | 2 | 0 | A02002-0024 | 0.236 | 0.1179 | 21.54 | 0 | 0 |  |  |  |  | 2015
H3 | CY90001 (2/2) | Non Stnd | 0 | 0 |  | 16 | 2 | 2 | 0 | CY90001 (1/2) | NA |  |  | 0
Cobra | CY90003 |  | 0 | 0 | 0 | 32 | 4 | 4 | 1 | A02001-0013 | 0.029 | 0.00958 | 5.73 | 0 | 0 |  |  |  |  | 2015
Citizen | CY90031 |  | 0 | 0 | 0 | 38 | 1 | 1 | 0 | A02001-0010 | 0.007 | 0.001 | 3.39 | 0 | 0
Ganesh | CY90040 |  | 0 | 0 | 0 | 14 | 32 | 32 | 4 | A02001-0032 | 0.6766 | 0.31 | 34.72 | 0 | 0 |  |  |  |  | 2018
Drill Press | DA5002(2/2) |  | 0 | 0 |  | 40 | 2 | 2 | 0 | DA5002(1/2) | NA
Cobra | DCN1500 |  | 0 | 0 | 0 | 24 | 4 | 4 | 1 | A11001-0048 | 1.0395 | 0.4995 | 72.17 | 0 | 0
Cobra | DCN316 |  | 0 | 0 | 0 | 24 | 3 | 3 | 0 | A01461-7194 | 0.029 | 0.01105 | 1.2 | 0 | 0
Cobra | DCN516 |  | 0 | 0 | 0 | 24 | 4 | 4 | 1 | A01461-73154 | 0.014 | 0.01105 | 1.6 | 0 | 0
Okuma-Cadet | DM2202 | Non Stnd | 0 | 0 | 0 | 22 | 5 | 5 | 1 | A02002-0034 | 0.5095 | 0.17 | 43.22 | 0 | 0 |  |  |  |  | 2015
Ganesh CNC | DM2203 | Stnd | 0 | 0 | 0 | 11 | 3 | 3 | 0 | A02001-0036 | 0.6871 | 0.166 | 43.94 | 0 | 0 |  |  |  |  | 2016
T-42 | DM2203 (1/2) | backup only | 0 | 0 | 0 | 8 | 3 | 3 | 0 | A02001-0036 | 0.6871 | 0.166 | 43.94 | 0 | 0 |  |  |  |  | 2015
T-42 | DM2203 (2/2) | backup only | 0 | 0 |  | 7.5 | 6 | 6 | 1 | DM2203 (1/2) | NA |  |  | 0 | [5 empty] | 2015
Cobra | DM1203 | Non-STND | 0 | 0 | 0 | 12 | 16 | 16 | 2 | A02002-0020 | 0.1549 | 0.045 | 14.96 | 0 | 0
H1 | DM2513 | backup only - NON STND | 0 | 0 | 0 | 80 | 16 | 16 | 2 | A02001-0018 | 0.0366 | 0.00886 | 10.99 | 0 | 0
C1 | DM2514 | backup only - NON STND | 0 | 0 | 0 | 50 | 16 | 16 | 2 | A02001-0012 | 0.039 | 0.00856 | 4.88 | 0 | 0
H2 | E1 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0032 | 0.1138 | 0.05 | 34.72 | 0 | 0
H2 | E1-1/2 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0032 | 0.1138 | 0.05 | 34.72 | 0 | 0
H2 | E10 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0032 | 0.1138 | 0.05 | 34.72 | 0 | 0
H2 | E12 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E12 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02071-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E15 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E17 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E2 |  | 0 | 0 | 0 | 42 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E25 |  | 0 | 0 | 0 | 42 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E2-1/2 |  | 0 | 0 | 0 | 31 | 1.5 | 1.5 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E3 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E30 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E4 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E5 |  | 0 | 0 | 0 | 40 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E6 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
H2 | E8 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0032 | 0.1138 | 0.05 | 34.72 | 0 | 0
H2 | E-BLNK |  | 0 | 0 | 0 | 43 | 2 | 2 | 0 | A02001-0032 | 0.098 | 0.05 | 34.72 | 0 | 0
Drill Press-Deburr | E5011 (2/2) | purchased | 0 | 0 |  | 360 | 1 | 1 | 0 | E5011 (2/2) | NA |  |  | 0
Cobra | EC3150-00 (1/2) |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | A02002-0028 | 0.3575 | 0.10036 | 29.31 | 0 | 0
Cobra | EC3150-00 (2/2) |  | 0 | 0 |  | 12 | 8 | 8 | 1 | EC3150-00 (1/2) | NA |  |  | 0
Okuma-Cadet | EH38005 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A19101-0036 | 0.2171 | 0.033 | 14.03 | 0 | 0
T-42 | EH38006 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A19101-0036 | 0.1385 | 0.0329 | 14.03 | 0 | 0
T-42 | EH38008 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A19101-0050 | 0.0951 | 0.028 | 27.06 | 0 | 0
Cobra | EH38009 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A19101-0016 | 0.0482 | 0.027 | 2.83 | 0 | 0
T-42 | EH38010 (1/2) |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A19101-0016 | 0.0482 | 0.034 | 2.83 | 0 | 0
T-42 or Cobra | EH38010 (2/2) |  | 0 | 0 |  | 12 | 8 | 8 | 1 | EH38010 (1/2) | NA |  |  | 0
Cobra | EH38023 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A05501-0028 | 0.012 | 0.012 | 3.71 | 0 | 0
T-42 | EH38025 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A02001-0014 | 0.001 | 0.001 | 6.65 | 0 | 0
Cobra | EH38026 | obsolete | 0 | 0 |  | 12 | 8 | 8 | 1 | A05501-0028 | 0.004 | 0.004 | 3.71 | 0 | 0
Cobra | EH38027 |  | 0 | 0 |  | 12 | 8 | 8 | 1 | A05501-0028 | 0.005 | 0.004 | 3.71 | 0 | 0
Cobra | EH38029 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A02001-0020 | 0.1 | 0.013 | 13.56 | 0 | 0
Okuma-Genos | EH38030 |  | 0 | 0 | 0 | 12 | 8 | 8 | 1 | A02001-0036 | 0.2171 | 0.102 | 43.94 | 0 | 0
Okuma-LB3000 | ER3 |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0032 | 0.27 | 0.072 | 34.72 | 0 | 0
Okuma-LB3000 | ER4 |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0032 | 0.27 | 0.072 | 34.72 | 0 | 0
H2 | ER10 | Non-Stnd | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0032 | 0.27 | 0.072 | 34.72 | 0 | 0
Okuma-LB3000 | ER10 | STND | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0032 | 0.27 | 0.072 | 34.72 | 0 | 0
H2 | ER15 |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0032 | 0.27 | 0.072 | 34.72 | 0 | 0
H2 | ER-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0032 | 0.27 | 0.072 | 34.72 | 0 | 0
Hass Vertical Mill VF3 | ESV3820 (2/2) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | ESV3820 (2/2) | NA |  |  | 0
B&S18 | F504W | obsolete | 0 | 0 |  | 107 | 4 | 4 | 1 | A02002-0028 | 0.2853 |  | 29.31 | 0 | 0
T42 | F6250B21 (1/3) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A02002-0032 | 0.9114 | 0.314 | 38.29 | 0 | 0
Cobra | F6250B21 (2/3) |  | 0 | 0 |  | 14 | 4 | 4 | 1 | F6250B21 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | F6250B21 (3/3) |  | 0 | 0 |  | 27 | 3 | 3 | 0 | F6250B21 (2/3) | NA |  |  | 0
B&S18 | F6860-C |  | 0 | 0 | 0 | 125 | 16 | 16 | 2 | A02001-0026 | 0.1048 | 0.04294 | 22.95 | 0 | 0
Hass Vertical Mill VF3 | F7575001-02 |  | 0 | 0 | 0 | 240 | 2 | 2 | 0 | F7575001 | NA | 0.498 |  | 0
B&S16 | FC2515 | non stnd | 0 | 0 | 0 | 131 | 8 | 8 | 1 | A02002-0024 | 0.0473 | 0.0103 | 21.54 | 0 | 0
B&S17 | FC7504 (2/2) |  | 0 | 0 |  | 192 | 4 | 4 | 1 | FC7504(1/2) | NA |  |  | 0
Haas Vertical Mill VF3 | FS12 (2/2) | Hydromat | 0 | 0 |  | 100 | 4 | 4 | 1 | FS12 (1/2) | NA |  |  | 0
Cobra | FS128 |  | 0 | 0 | 0 | 13 | 3 | 3 | 0 | A02001-0016 | 0.0253 | 0.0045 | 8.68 | 0 | 0
Cobra or T42 | FS134(1/2) |  | 0 | 0 | 0 | 12 | 3 | 3 | 0 | A02002-0024 | 0.1962 | 0.085 | 21.54 | 0 | 0
Cobra or T42 | FS134(2/2) |  | 0 | 0 |  | 19 | 2 | 2 | 0 | FS134(1/2) | NA |  |  | 0
Cobra or T42 | FS135(1/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A02002-0022 | 0.1491 | 1.0522 | 18.1 | 0 | 0
Cobra or T42 | FS135(2/2) |  | 0 | 0 |  | 12 | 1 | 1 | 0 | FS135(1/2) | NA |  |  | 0
B&S18 | FS136 |  | 0 | 0 | 0 | 45 | 8 | 8 | 1 | A02001-0010 | 0.0044 | 0.000638 | 3.39 | 0 | 0
Cobra | FS31 |  | 0 | 0 | 0 | 12 | 3 | 3 | 0 | A02001-0012 | 0.0162 | 0.0052 | 4.88 | 0 | 0
H3 | FS35 (1/2) |  | 0 | 0 |  | 54 | 3 | 3 | 0 | A06502-0020 | 0.1707 | 0.069 | 13.8 | 0 | 0
H3 | FS35 (2/2) |  | 0 | 0 |  | 25 | 3 | 3 | 0 | FS35 (1/2) | NA |  |  | 0
Cobra | FT10101 (1/3) |  | 0 | 0 | 0 | 8 | 3 | 3 | 0 | A02002-0032 | 0.727 | 0.307 | 38.29 | 0 | 0
Cobra | FT10101 (2/3) |  | 0 | 0 |  | 29 | 2 | 2 | 0 | FT10101 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | FT10101 (3/3) |  | 0 | 0 |  | 20 | 2 | 2 | 0 | FT10101 (2/3) | NA |  |  | 0
Haas Vertical Mill VF3 | FT10501(2/2) |  | 0 | 0 |  | 24 | 1 | 1 | 0 | FT10501(1/2) | NA |  |  | 0
Okuma-Cadet | FT111 (1/3) |  | 0 | 0 | 0 | 9 | 3 | 3 | 0 | A02032-0028 | 1.0458 | 0.048 | 29.31 | 0 | 0
Cobra | FT111 (2/3) |  | 0 | 0 |  | 9 | 3 | 3 | 0 | FT111 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | FT111 (3/3) |  | 0 | 0 |  | 60 | 3 | 3 | 0 | FT111 (2/3) | NA |  |  | 0
Drill Press 464 | FT11401 |  | 0 | 0 | 0 | 50 | 2 | 2 | 0 | FT11401-0 | NA | 0.0846 |  | 0
H1 | FT12401 | Non Stnd | 0 | 0 | 0 | 30 | 3 | 3 | 0 | A02001-0032 | 0.2624 | 0.06545 | 34.72 | 0 | 0
Cobra | FT13301 |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A02002-0024 | 0.2826 | 0.147 | 21.54 | 0 | 0
T42 | FT13801 (1/2) | Non-Stnd | 0 | 0 | 0 | 22 | 0 | 0 | 0 | A02002-0018 | 0.2352 | 0.03594 | 12.11 | 0 | 0 |  |  |  |  | 2018
Cobra | FT13801 (2/2) | Non-Stnd | 0 | 0 |  | 22 | 0 | 0 | 0 | FT13801 (1/2) | NA |  |  | 0
Okuma-LB3000 | FT13801 | Stnd | 0 | 0 | 0 | 22 | 0 | 0 | 0 | A02002-0018 | 0.2352 | 0.03594 | 12.11 | 0 | 0
H2 | G1 |  | 0 | 0 | 0 | 31 | 1.3 | 1.3 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G10 |  | 0 | 0 | 0 | 30 | 2 | 2 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G12 |  | 0 | 0 | 0 | 30 | 2 | 2 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G15 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G17 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G2 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
LB3000 | G2-1/2 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G2A |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A06101-0024 | 0.0609 | 0.032 | 18.02 | 0 | 0
H2 | G20 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
LB3000 | G3 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G3/4 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G4 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G5 |  | 0 | 0 | 0 | 42 | 1 | 1 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G6 |  | 0 | 0 | 0 | 39 | 1 | 1 | 0 | A02071-0024 | 0.064 | 0.028 | 19.53 | 0 | 0
H2 | G8 |  | 0 | 0 | 0 | 31 | 2 | 2 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
H2 | G-BLNK |  | 0 | 0 | 0 | 31 | 1.3 | 1.3 | 0 | A02001-0024 | 0.055 | 0.028 | 19.53 | 0 | 0
Miyano 2 Jaw | G100-1A (1/3) |  | 0 | 0 | 0 | 10 | 2 | 2 | 0 | G100-1A-BLNK | NA | 2.04 |  | 0
Miyano 2 Jaw | G100-1A (2/3) |  | 0 | 0 |  | 10 | 2 | 2 | 0 | G100-1A (1/3) | NA |  |  | 0
Miyano 2 Jaw | G100-1A (3/3) |  | 0 | 0 |  | 10 | 2 | 2 | 0 | G100-1A (2/3) | NA |  |  | 0
Miyano 2 Jaw | G100-1ASS (1/3) |  | 0 | 0 | 0 | 10 | 2 | 2 | 0 | G100-1ASS-BLNK | NA | 2.04 |  | 0
Miyano 2 Jaw | G100-1ASS (2/3) |  | 0 | 0 |  | 10 | 2 | 2 | 0 | G100-1ASS (1/3) | NA |  |  | 0
Miyano 2 Jaw | G100-1ASS (3/3) |  | 0 | 0 |  | 10 | 2 | 2 | 0 | G100-1ASS (2/3) | NA |  |  | 0
Miyano 3 Jaw | G100-1G (1/3) |  | 0 | 0 | 0 | 10 | 2.5 | 2.5 | 0 | G100-1G-BLNK | NA | 2.28 |  | 0
Miyano 3 Jaw | G100-1G (2/3) |  | 0 | 0 |  | 10 | 2.5 | 2.5 | 0 | G100-1G (1/3) | NA |  |  | 0
Miyano 2 Jaw | G100-1G (3/3) |  | 0 | 0 |  | 10 | 2.5 | 2.5 | 0 | G100-1G (2/3) | NA |  |  | 0
Miyano 3 Jaw | G100-1GSS (1/3) |  | 0 | 0 | 0 | 10 | 2.5 | 2.5 | 0 | G100-1GSS-BLNK | NA | 2.28 |  | 0
Miyano 3 Jaw | G100-1GSS (2/3) |  | 0 | 0 |  | 10 | 2.5 | 2.5 | 0 | G100-1GSS (1/3) | NA |  |  | 0
Miyano 2 Jaw | G100-1GSS (3/3) |  | 0 | 0 |  | 10 | 2.5 | 2.5 | 0 | G100-1GSS (2/3) | NA |  |  | 0
H3 | G100-2 (1/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A02001-0064 | 2.1617 | 0.595 | 138.88 | 0 | 0
H1 | G100-2 (2/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | G100-2 (1/2) | NA |  |  | 0
H3 | G100-2B (1/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | A02001-0064 | 2.7437 | 0.33 | 138.88 | 0 | 0
H1 | G100-2B (2/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | G100-2B (1/2) | NA |  |  | 0
H3 | G100-2BSS (1/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A06201-0064 | 2.7501 | 0.542 | 128.2 | 0 | 0
H2 | G100-2BSS (2/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | G100-2BSS (1/2) | NA |  |  | 0
H3 | G100-2SC (1/2) |  | 0 | 0 | 0 | 1 | 3 | 3 | 0 | A02001-0064 | 2.7437 | 0.516 | 138.88 | 0 | 0
H2 | G100-2SC (2/2) |  | 0 | 0 |  | 7 | 3 | 3 | 0 | G100-2SC (1/2) | NA |  |  | 0
H3 | G100-2SS (1/2) | NON STND | 0 | 0 | 0 | 1 | 3 | 3 | 0 | A06201-0064 | 2.1545 | 0.516 | 128.2 | 0 | 0
H2 | G100-2SS (2/2) |  | 0 | 0 |  | 7 | 3 | 3 | 0 | G100-2SS (1/2) | NA |  |  | 0
Miyano-Bar CNC | G100-3SS | purchased | 0 | 0 |  | 10 | 3 | 3 | 0 | A06201-0044 | 1.0144 |  | 60.59 | 0 | 0
Haas H2 Only | G100-4 | Obsolete sub -G100-4SS | 0 | 0 | 0 | 36 | 3.5 | 3.5 | 0 | A02001-0032 | 0.0867 | 0.0445 | 34.72 | 0 | 0
H2 | G100-4BSC |  | 0 | 0 | 0 | 36 | 3.5 | 3.5 | 0 | A02001-0028 | 0.069 | 0.348 | 26.58 | 0 | 0
Haas H2 Only | G100-4HSS |  | 0 | 0 | 0 | 36 | 3.5 | 3.5 | 0 | A06201-0032 | 0.1432 | 0.048 | 32.04 | 0 | 0
Haas H2 Only | G100-4SS |  | 0 | 0 | 0 | 36 | 3.5 | 3.5 | 0 | A06201-0032 | 0.0817 |  | 32.04 | 0 | 0
H3 | G100-5ASS |  | 0 | 0 |  | 10 | 3 | 3 | 0 | A06201-0028 | 0.0699 | 0.021 | 25.29 | 0 | 0
C1 or C2 | G100-8BSS |  | 0 | 0 | 0 | 10 | 4 | 4 | 1 | A06201-0010 | 0.0703 | 0.055 | 3.23 | 0 | 0
B/S 18 | G100-8SS (1/2) |  | 0 | 0 | 0 | 45 | 4 | 4 | 1 | A06201-0010 | 0.0703 | 0.055 | 3.23 | 0 | 0
B/S 17 | G100-8SS (2/2) |  | 0 | 0 |  | 45 | 4 | 4 | 1 | G100-8SS (1/2) | NA |  |  | 0
C3 | G125-10 | stnd | 0 | 0 | 0 | 35 | 4 | 4 | 1 | A02001-0020 | 0.1357 | 0.0408 | 13.56 | 0 | 0
Okuma-Cadet | G125-10 (1/2) | non stnd | 0 | 0 | 0 | 35 | 4 | 4 | 1 | A02001-0020 | 0.1357 | 0.08 | 13.56 | 0 | 0
Hass Vertical Mill VF3 | G125-10 (2/2) | non stnd | 0 | 0 |  | 6 | 1.5 | 1.5 | 0 | G125-10 (1/2) | NA |  |  | 0
C3 | G125-10SS | stnd | 0 | 0 | 0 | 35 | 4 | 4 | 1 | A06201-0020 | 0.1274 | 0.0408 | 12.9 | 0 | 0
Okuma-Cadet | G125-10SS (1/2) | non stnd | 0 | 0 |  | 15 | 4 | 4 | 1 | A06201-0020 | 0.1274 | 0.08 | 12.9 | 0 | 0
Hass Vertical Mill VF3 | G125-10SS (2/2) | non stnd | 0 | 0 |  | 15 | 4 | 4 | 1 | G125-10SS (1/2) | NA |  |  | 0
Miyano 3 Jaw Chucker | G125-1A (1/3) |  | 0 | 0 | 0 | 10 | 2.5 | 2.5 | 0 | G125-1A-BLNK | NA | 2.3 |  | 0
Miyano 2 Jaw Chucker | G125-1A (2/3) |  | 0 | 0 |  | 10 | 2.5 | 2.5 | 0 | G125-1A (1/3) | NA |  |  | 0
Miyano 2 Jaw Chucker | G125-1A (3/3) |  | 0 | 0 |  | 10 | 2.5 | 2.5 | 0 | G125-1A (2/3) | NA |  |  | 0
Miyano Checker 3 Jaw | G125-1G (1/3) |  | 0 | 0 | 0 | 5 | 2.5 | 2.5 | 0 | G125-1G-BLNK | NA | 2.67 |  | 0
Miyano Chucker 2 Jaw | G125-1G (2/3) |  | 0 | 0 |  | 5 | 2.5 | 2.5 | 0 | G125-1G (1/3) | NA |  |  | 0
Miyano Chucker 2 Jaw | G125-1G (3/3) |  | 0 | 0 |  | 5 | 2.5 | 2.5 | 0 | G125-1G (2/3) | NA |  |  | 0
H4 | G125-2 (1/2) |  | 0 | 0 | 0 | 44 | 3 | 3 | 0 | A02001-0072 | 3.0727 | 0.075 | 175.8 | 0 | 0
H2 | G125-2 (2/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | G125-2 (1/2) | NA |  |  | 0
H4 | G125-2B (1/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A02001-0072 | 3.7181 | 0.745 | 175.8 | 0 | 0
H2 | G125-2B (2/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | G125-2B (1/2) | NA |  |  | 0
H3 | G125-21SS |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A06201-0024 | 0.0799 | 0.034 | 18.58 | 0 | 0
Okuma-Cadet | G125-3 | purchased | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0022 | 0.9318 |  | 16.41 | 0 | 0
H2 | G125-4 |  | 0 | 0 | 0 | 13 | 3 | 3 | 0 | A02001-0036 | 0.1914 | 0.041 | 43.94 | 0 | 0
H2 | G125-4B |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A02001-0036 | 0.1914 | 0.041 | 43.94 | 0 | 0
Okuma-Cadet | G125-5A |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | A02001-0044 | 0.301 | 0.06395 | 65.64 | 0 | 0
B/S 18 | G125-8 (1/2) |  | 0 | 0 | 0 | 45 | 4 | 4 | 1 | A02001-0012 | 0.1154 | 0.0914 | 4.88 | 0 | 0
B/S 17 | G125-8 (2/2) |  | 0 | 0 |  | 45 | 4 | 4 | 1 | G125-8 (1/2) | NA |  |  | 0
Miyano 3 Jaw Chucker | G150-1A (1/3) |  | 0 | 0 | 0 | 34 | 2 | 2 | 0 | G150-1A-BLNK | NA | 2.79 |  | 0
Miyano 2 Jaw Chucker | G150-1A (2/3) |  | 0 | 0 |  | 34 | 2 | 2 | 0 | G150-1A (1/3) | NA |  |  | 0
Miyano 2 Jaw Chucker | G150-1A (3/3) |  | 0 | 0 |  | 34 | 2 | 2 | 0 | G150-1A (2/3) | NA |  |  | 0
Miyano 3 Jaw Chucker | G150-1ASS (1/3) |  | 0 | 0 | 0 | 14 | 4 | 4 | 1 | G150-1ASS-BLNK | NA | 3.53 |  | 0
Miyano 2 Jaw Chucker | G150-1ASS (2/3) |  | 0 | 0 |  | 34 | 2 | 2 | 0 | G150-1ASS (1/3) | NA |  |  | 0
Miyano 2 Jaw Chucker | G150-1ASS (3/3) |  | 0 | 0 |  | 34 | 2 | 2 | 0 | G150-1ASS (2/3) | NA |  |  | 0
Miyano Checker 3 Jaw | G150-1GSS(1/3) |  | 0 | 0 | 0 | 34 | 2 | 2 | 0 | G150-1GSS-BLNK | NA | 3.53 |  | 0
Miyano Chucker 2 Jaw | G150-1GSS(2/3) |  | 0 | 0 |  | 34 | 2 | 2 | 0 | G150-1GSS(1/3) | NA |  |  | 0
Miyano Chucker 2 Jaw | G150-1GSS(3/3) |  | 0 | 0 |  | 34 | 2 | 2 | 0 | G150-1GSS(2/3) | NA |  |  | 0
H4 | G150-2 (1/2) |  | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A02001-0080 | 4.3411 | 0.745 | 217.01 | 0 | 0
Hass Vertical Mill VF4 | G150-2 (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G150-2 (1/2) | NA |  |  | 0
H4 | G150-2SS (1/2) |  | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A06201-0080 | 4.1304 | 0.95 | 200.3 | 0 | 0
T42 | G150-2SS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G150-2SS (1/2) | NA |  |  | 0
H4 | G150-2B (1/2) |  | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A02001-0080 | 5.1756 | 0.97 | 217.01 | 0 | 0
Hass Vertical Mill VF4 | G150-2B (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G150-2B (1/2) | NA |  |  | 0
H4 | G150-2BSS (1/2) |  | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A06201-0080 | 4.6472 | 0.89 | 200.3 | 0 | 0
T42 | G150-2BSS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G150-2BSS (1/2) | NA |  |  | 0
H4 | G150-2SS (1/2) |  | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A06201-0080 | 4.1304 | 0.94 | 200.3 | 0 | 0
T42 | G150-2SS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G150-2SS (1/2) | NA |  |  | 0
H2 | G150-4BSS |  | 0 | 0 | 0 | 14 | 4 | 4 | 1 | A06201-0044 | 0.2186 | 0.098 | 60.59 | 0 | 0
H2 | G150-4HBSS |  | 0 | 0 | 0 | 10 | 5 | 5 | 1 | A06201-0048 | 0.2583 | 0.106 | 72.1 | 0 | 0
H2 | G150-4HSS |  | 0 | 0 | 0 | 10 | 5 | 5 | 1 | A06201-0048 | 0.113 | 0.11 | 72.1 | 0 | 0
H2 | G150-4SS |  | 0 | 0 | 0 | 7 | 5 | 5 | 1 | A06201-0048 | 0.3584 | 0.108 | 72.1 | 0 | 0
Haas H1 or H3 | G150-5A | Obsolete Sub-G150-5ASS | 0 | 0 | 0 | 45 | 3.5 | 3.5 | 0 | A02001-0044 | 0.2305 | 0.104 | 65.64 | 0 | 0
Haas H1 or H3 | G150-5ASS |  | 0 | 0 | 0 | 11 | 4 | 4 | 1 | A06201-0044 | 0.2894 | 0.1 | 60.59 | 0 | 0
Citizen 2 | G150-8BSS |  | 0 | 0 | 0 | 10 | 4 | 4 | 1 | A06201-0012 | 0.1192 | 0.095 | 4.65 | 0 | 0
B/S 18 | G150-8SS (1/2) |  | 0 | 0 | 0 | 45 | 4 | 4 | 1 | A06201-0012 | 0.1166 | 0.094 | 4.65 | 0 | 0
B/S 17 | G150-8SS (2/2) |  | 0 | 0 |  | 45 | 4 | 4 | 1 | G150-8SS (1/2) | NA |  |  | 0
Cut Saw | G20A-13SS (1/2) |  | 0 | 0 | 0 | 12 | 1 | 1 | 0 | A01216-6021 | 0.51 | 0.443 | 5.1 | 0 | 0
Haas Vertical Mill VF4 | G20A-13SS (2/2) |  | 0 | 0 | 0 | 12 | 1 | 1 | 0 | G20A-13SS (1/2) | NA |  |  | 0
Cobra or Cadet | G200-10 (1/2) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A02001-0024 | 0.2442 | 0.08229 | 19.53 | 0 | 0
Haas Vertical Mill VF3 | G200-10 (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G200-10 (1/2) | NA |  |  | 0
Cobra or Cadet | G200-10SS (1/2) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0024 | 0.2201 | 0.06 | 18.58 | 0 | 0
Haas Vertical Mill VF3 | G200-10SS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G200-10SS (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | G200-11SS |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | G200-11SS-BLNK | NA | 0.2665 |  | 0
Okuma-Cadet | G200-12 |  | 0 | 0 | 0 | 27 | 2 | 2 | 0 | A02002-0040 | 0.1342 | 0.038 | 59.82 | 0 | 0
Okuma-Cadet | G200-12SS |  | 0 | 0 | 0 | 20 | 3 | 3 | 0 | A06202-0040 | 0.1394 | 0.037 | 55.21 | 0 | 0
Brown and Sharpe #18 | G200-13B (1/2) |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | A02001-0024 | 0.5651 | 0.362 | 19.53 | 0 | 0
Haas Vertical Mill VF4 | G200-13B (2/2) |  | 0 | 0 |  | 11 | 2 | 2 | 0 | G200-13B (1/2) | NA |  |  | 0
Brown and Sharpe #18 | G200-13BSS (1/2) |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | A06201-0024 | 0.532 | 0.338 | 18.58 | 0 | 0
Haas Vertical Mill VF4 | G200-13BSS (2/2) |  | 0 | 0 |  | 2 | 2 | 2 | 0 | G200-13BSS (1/2) | NA |  |  | 0
Drill Press | G200-13SS |  | 0 | 0 | 0 | 10 | 2 | 2 | 0 | G200-13SS-BLNK | NA | 0.112 |  | 0
Bridgeport CNC Mill | G200-14SS |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | G200-14SS-BLNK | NA |  |  | 0
Citizen | G200-17 | NON STND | 0 | 0 | 0 | 50 | 16 | 16 | 2 | A02001-0010 | 0.038 |  | 3.39 | 0 | 0
Citizen | G200-17SS | NON STND | 0 | 0 | 0 | 50 | 16 | 16 | 2 | A06201-0010 | 0.0448 | 0.026 | 3.23 | 0 | 0
Miyano 3 Jaw Chucker | G200-1A (1/3) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G200-1A-BLNK | NA | 6.1 |  | 0
Miyano 2 Jaw Chucker | G200-1A (2/3) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G200-1A (1/3) | NA |  |  | 0
Miyano 2 Jaw Chucker | G200-1A (3/3) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G200-1A (2/3) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-1ASS (1/3) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G200-1ASS-BLNK | NA | 6.33 |  | 0
Miyano 2 Jaw Chucker | G200-1ASS (2/3) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G200-1ASS (1/3) | NA |  |  | 0
Miyano 2 Jaw Chucker | G200-1ASS (3/3) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G200-1ASS (2/3) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-1G (1/3) |  | 0 | 0 | 0 | 27 | 3 | 3 | 0 | G200-1G-BLNK | NA | 7.35 |  | 0
Miyano 3 Jaw Chucker | G200-1G (2/3) |  | 0 | 0 |  | 27 | 3 | 3 | 0 | G200-1G (1/3) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-1G (3/3) |  | 0 | 0 |  | 27 | 3 | 3 | 0 | G200-1G (2/3) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-1GSS (1/3) |  | 0 | 0 | 0 | 14 | 3 | 3 | 0 | G200-1GSS-BLNK | NA | 6.62 |  | 0
Miyano 3 Jaw Chucker | G200-1GSS (2/3) |  | 0 | 0 |  | 14 | 3 | 3 | 0 | G200-1GSS (1/3) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-1GSS (3/3) |  | 0 | 0 |  | 14 | 3 | 3 | 0 | G200-1GSS (2/3) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-2 | purchased | 0 | 0 | 0 | 40 | 1.5 | 1.5 | 0 | G200-2-BLNK | NA |  |  | 0
Okuma Cadet | G200-22 | purchased | 0 | 0 | 0 | 15 | 2 | 2 | 0 | A02002-0040 | 0.3583 | 0.107 | 59.82 | 0 | 0
Okuma Cadet | G200-22SS |  | 0 | 0 | 0 | 12 | 2 | 2 | 0 | A06202-0040 | 0.382 | 0.107 | 55.21 | 0 | 0
Miyano 3 Jaw Chucker | G200-2B (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G200-2B-BLNK | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-2B (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G200-2B (1/2) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-2SC (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G200-2-BLNK | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-2SC (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G200-2SC (1/2) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-2SS (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G200-2SS-BLNK | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-2SS(2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G200-2SS (1/2) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-3 (1/2) | purchased | 0 | 0 | 0 | 36 | 2 | 2 | 0 | G200-3-BLNK | NA | 0.822 |  | 0
Miyano 3 Jaw Chucker | G200-3 (2/2) | purchased | 0 | 0 |  | 36 | 2 | 2 | 0 | G200-3 (1/2) | NA |  |  | 0
Miyano 3 Jaw Chucker | G200-3SS (1/2) |  | 0 | 0 | 0 | 22 | 2 | 2 | 0 | G200-3SS-BLNK | NA | 0.822 |  | 0
Miyano 3 Jaw Chucker | G200-3SS (2/2) |  | 0 | 0 |  | 22 | 2 | 2 | 0 | G200-3SS(1/2) | NA |  |  | 0
Haas H1 | G200-4HBSS (1/2) |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | A06201-0064 | 0.5865 | 0.201 | 128.2 | 0 | 0
Haas Vertical Mill VF4 | G200-4HBSS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G200-4HBSS (1/2) | NA |  |  | 0
Haas H1 | G200-4HSS (1/2) |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | A06201-0064 | 0.5228 | 0.21 | 128.2 | 0 | 0
Haas Vertical Mill VF4 | G200-4HSS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G200-4HSS (1/2) | NA |  |  | 0
M1 or H1 | G200-4SS (1/2) |  | 0 | 0 | 0 | 6 | 3 | 3 | 0 | A06201-0064 | 0.6832 | 0.203 | 128.2 | 0 | 0
Haas Vertical Mill VF4 | G200-4SS (2/2) |  | 0 | 0 |  | 46 | 0.5 | 0.5 | 0 | G200-4SS (1/2) | NA |  |  | 0
Okuma-Cadet | G200-5ASS |  | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A06201-0060 | 0.5972 | 0.288 | 112.7 | 0 | 0
Citizen | G200-8BSS | Stnd | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A06201-0012 | 0.149 | 0.117 | 4.65 | 0 | 0
Brown and Sharpe #18 | G200-8BSS (1/3) | Non Stnd | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A06201-0012 | 0.149 | 0.117 | 4.65 | 0 | 0
Brown and Sharpe #17 | G200-8BSS (2/3) | Non Stnd | 0 | 0 |  | 10 | 3 | 3 | 0 | G200-8BSS (1/3) | NA |  |  | 0
Drill Press | G200-8BSS (3/3) | Non Stnd | 0 | 0 |  | 10 | 3 | 3 | 0 | G200-8BSS (2/3) | NA |  |  | 0
Brown and Sharpe #18 | G200-8SS (1/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A06201-0012 | 0.1462 | 0.114 | 4.65 | 0 | 0
Brown and Sharpe #17 | G200-8SS (2/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | G200-8SS (1/2) | NA |  |  | 0
Miyano Chucker 2 Jaw | G300-15 (1/2) |  | 0 | 0 | 0 | 10 | 2 | 2 | 0 | G300-15-BLNK | NA | 0.125 |  | 0
Drill Press | G300-15 (2/2) |  | 0 | 0 |  | 10 | 2 | 2 | 0 | G300-15 (1/2) | NA |  |  | 0
Miyano 3 Jaw Chucker | G300-1A (1/3) |  | 0 | 0 | 0 | 14 | 3 | 3 | 0 | G300-1A-BLNK | NA |  |  | 0
Miyano 2 Jaw Chucker | G300-1A (2/3) |  | 0 | 0 |  | 14 | 3 | 3 | 0 | G300-1A (1/3) | NA |  |  | 0
Miyano 2 Jaw Chucker | G300-1A (3/3) |  | 0 | 0 |  | 14 | 3 | 3 | 0 | G300-1A (2/3) | NA |  |  | 0
Miyano Chucker 3 Jaw | G300-1ASS (1/2) |  | 0 | 0 | 0 | 7 | 3 | 3 | 0 | G300-1ASS-BLNK | NA | 19.28 |  | 0
Miyano Chucker 2 Jaw | G300-1ASS (2/2) |  | 0 | 0 |  | 7 | 3 | 3 | 0 | G300-1ASS (1/2) | NA |  |  | 0
Miyano Chucker 2 Jaw | G300-1G (1/2) |  | 0 | 0 | 0 | 7 | 3 | 3 | 0 | G300-1G-BLNK | NA | 19.28 |  | 0
Miyano Chucker 2 Jaw | G300-1G (2/2) |  | 0 | 0 |  | 7 | 3 | 3 | 0 | G300-1G (1/2) | NA |  |  | 0
Miyano Chucker 3 Jaw | G300-2 (1/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G300-2-BLNK | NA |  |  | 0
Miyano Chucker 3 Jaw | G300-2 (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G300-2 (1/2) | NA |  |  | 0
Miyano Chucker 3 Jaw | G300-2BSS (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G300-2BSS-BLNK | NA | 2.97 |  | 0
Miyano Chucker 3 Jaw | G300-2BSS (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G300-2BSS (1/2) | NA |  |  | 0
Miyano Chucker 3 Jaw | G300-2SS (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G300-2SS-BLNK | NA | 2.97 |  | 0
Miyano Chucker 3 Jaw | G300-2SS (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G300-2SS (1/2) | NA |  |  | 0
Miyano Chucker 3 Jaw | G300-3 (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G300-3-BLNK | NA | 2.51 |  | 0
Miyano Chucker 3 Jaw | G300-3 (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G300-3 (1/2) | NA |  |  | 0
Miyano 3 jaw Chucker | G300-3BSS (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G300-3BSS-BLNK | NA | 2.51 |  | 0
Miyano 3 jaw Chucker | G300-3BSS (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G300-3BSS (1/2) | NA |  |  | 0
Miyano 3 jaw Chucker | G300-3SS (1/2) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | G300-3SS-BLNK | NA | 2.51 |  | 0
Miyano 3 jaw Chucker | G300-3SS (2/2) |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G300-3SS (1/2) | NA |  |  | 0
H4 | G300-4BSS (1/2) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0096 | 1.6712 | 0.7 | 288.4 | 0 | 0
Hass Vertical Mill VF4 | G300-4BSS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G300-4BSS (1/2) | NA |  |  | 0
H4 | G300-4SS (1/2) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0096 | 1.5732 | 0.7 | 288.4 | 0 | 0
Hass Vertical Mill VF4 | G300-4SS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G300-4SS (1/2) | NA |  |  | 0
H4 | G300-5ASS |  | 0 | 0 | 0 | 12 | 3.5 | 3.5 | 0 | A06201-0096 | 1.6202 | 0.885 | 288.4 | 0 | 0
Brown and Sharpe #18 | G300-5BSS |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | G300-5SS | NA | 0.002 |  | 0
Brown and Sharpe #18 | G300-8 (1/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A02001-0012 | 0.1705 | 0.129 | 4.88 | 0 | 0
Brown and Sharpe #17 | G300-8 (2/2) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | G300-8 (1/2) | NA |  |  | 0
T42 | G300-8BSS (1/2) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0012 | 0.1901 | 0.1225 | 4.65 | 0 | 0
T42 | G300-8BSS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G300-8BSS (1/2) | NA |  |  | 0
Brown and Sharpe #18 | G300-8SS (1/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A06201-0012 | 0.1579 | 0.1225 | 4.65 | 0 | 0
Brown and Sharpe #17 | G300-8SS (2/2) |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | G300-8SS (1/2) | NA
C3 | G50-10 | STND | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A02001-0020 | 0.1493 | 0.04735 | 13.56 | 0 | 0
Okuma or Miyano | G50-10 (1/2) | NON STND | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A02001-0020 | 0.1493 | 0.04735 | 13.56 | 0 | 0
Hass Vertical Mill VF4 | G50-10 (2/2) | NON STND | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-10 (1/2) | NA |  |  | 0
C3 | G50-10SS | STND | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0020 | 0.1334 | 0.043 | 12.9 |  | 0
Okuma-Cadet | G50-10SS (1/2) | NON STND | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0020 | 0.1334 | 0.043 | 12.9 |  | 0
Bridgeport CNC Mill | G50-10SS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-10SS (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | G50-11SS |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | G50-11SS-BLNK | NA | 0.126 |  | 0
Okuma-Cadet | G50-12 | Acme | 0 | 0 | 0 | 17 | 4 | 4 | 1 | A02002-0036 | 0.0877 | 0.032 | 48.45 | 0 | 0 |  |  |  |  | 2017
Okuma-Cadet | G50-12SS | Acme | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06202-0036 | 0.0907 | 0.0302 | 44.72 | 0 | 0 |  |  |  |  | 2017
Brown and Sharpe #18 | G50-13B (1/2) |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | A02001-0020 | 0.3264 | 0.192 | 13.56 | 0 | 0
Haas Vertical Mill VF3 | G50-13B (2/2) |  | 0 | 0 |  | 2 | 2 | 2 | 0 | G50-13B (1/2) | NA |  |  | 0
Brown and Sharpe #18 | G50-13BSS (1/2) |  | 0 | 0 | 0 | 20 | 2 | 2 | 0 | A06201-0020 | 0.3264 | 0.192 | 12.9 | 0 | 0
Haas Vertical Mill VF3 | G50-13BSS (2/2) |  | 0 | 0 |  | 2 | 2 | 2 | 0 | G50-13BSS (1/2) | NA |  |  | 0
Bridgeport Drill Press | G50-13SS |  | 0 | 0 | 0 | 10 | 4 | 4 | 1 | G50-13SS-BLNK | NA | 0.051 |  | 0
Haas Vertical Mill VF4 | G50-14SS |  | 0 | 0 | 0 | 20 | 1 | 2 | 0 | G50-14SS-BLNK | NA |  |  | 0
Miyano Chucker/Okuma | G50-15B |  | 0 | 0 |  | 7 | 2 | 2 | 0 | G50-15-BLNK | NA |  |  | 0
Drill Press | G50-15BAC |  | 0 | 0 |  | 7 | 2 | 2 | 0 | G50-15-BLNK | NA |  |  | 0
Miyano Chucker/Okuma | G50-15CSS |  | 0 | 0 |  | 7 | 2 | 2 | 0 | G50-15SS-BLNK | NA |  |  | 0
Miyano Chucker/Okuma | G50-15SS |  | 0 | 0 |  | 22 | 2 | 2 | 0 | G50-15SS-BLNK | NA |  |  | 0
H2 | G50-17 | NON STND | 0 | 0 |  | 68 | 0 | 0 | 0 | A02001-0008 | 0.0204 |  | 2.17 | 0 | 0
H2 | G50-17SS | NON STND | 0 | 0 | 0 | 50 | 16 | 16 | 2 | A06201-0008 | 0.0194 | 0.013 | 2.06 | 0 | 0
Miyano Chucker | G50-1ASS |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G75-1ASS-BLNK | NA |  |  | 0
Miyano Chucker | G50-1G |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G50-1G-BLNK | NA |  |  | 0
H3 | G50-2(1/2) |  | 0 | 0 |  | 5 | 5 | 5 | 1 | A02001-0048 | 1.093 |  | 78.12 | 0 | 0
H2 | G50-2(2/2) |  | 0 | 0 |  | 36 | 2 | 2 | 0 | G50-2(1/2) | NA |  |  | 0
Cobra | G50-21SS | NON STND | 0 | 0 |  | 14 | 4 | 4 | 1 | A06201-0024 | 0.1027 |  | 18.58 | 0 | 0
Okuma-Cadet | G50-21SS | STND | 0 | 0 |  | 15 | 4 | 4 | 1 | A06201-0024 | 0.1093 |  | 18.58 | 0 | 0
Okuma-Cadet | G50-22 |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02002-0036 | 0.2092 |  | 48.45 | 0 | 0
Okuma-Cadet | G50-22SS |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A06202-0036 | 0.2732 |  | 44.72 | 0 | 0
Not Brown/Sharpe | G50-24P(A) |  | 0 | 0 |  | 20 | 2 | 2 | 0 | A06403-0032 | 0.532 |  | 40.8 | 0 | 0
Haas Vertical Mill VF4 | G50-24P(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G200-13BSS(A) | NA |  |  | 0
Haas H3 | G50-2B(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0050 | 1.4387 |  | 84.77 | 0 | 0
H2 | G50-2B(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-2B(A) | NA |  |  | 0
Haas H3 | G50-2BSS(A) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0050 | 1.3544 | 0.301 | 78.24 | 0 | 0
H2 | G50-2BSS(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-2BSS(A) | NA |  |  | 0
Bridgeport Mill | G50-2SS |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-2SS(A) | NA |  |  | 0
Okuma-Cadet | G50-2SS(A) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | A06201-0048 | 1.0357 |  | 72.1 | 0 | 0
Okuma-Cadet | G50-3 | obsolete sub- G50-3SS | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0032 | 0.2293 |  | 34.72 | 0 | 0
Miyano CNC Bar | G50-30SS |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A06202-0044 | 0.3945 |  | 66.8 | 0 | 0
H3 | G50-3SS |  | 0 | 0 | 0 | 10 | 4 | 4 | 1 | A06201-0032 | 0.1957 | 0.957 | 32.04 | 0 | 0
H2 | G50-4B |  | 0 | 0 |  | 13 | 3 | 3 | 0 | A02001-0022 | 0.0459 | 0.3853 | 16.41 | 0 | 0
H2 | G50-4HBSS |  | 0 | 0 |  | 16 | 3 | 3 | 0 | A06201-0024 | 0.0558 |  | 18.58 | 0 | 0
H2 | G50-4HSS |  | 0 | 0 |  | 10 | 5.5 | 5.5 | 1 | A06201-0024 | 0.0805 |  | 18.58 | 0 | 0
H2 | G50-4SS |  | 0 | 0 | 0 | 9 | 3 | 3 | 0 | A06201-0024 | 0.0459 | 0.02 | 18.58 | 0 | 0
Okuma-Cadet | G50-5(A) | obsolete sub G50-5SS | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0020 | 0.0914 |  | 13.56 | 0 | 0
Haas Vertical Mill VF4 | G50-5(B) | obsolete sub G50-5SS | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-5(A) | NA |  |  | 0
Okuma-Cadet | G50-5B |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0020 | 0.0823 |  | 13.56 | 0 | 0
Haas Vertical Mill VF4 | G50-5B(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-5(A) | NA |  |  | 0
Okuma-Cadet | G50-5BSS |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-5SS | NA |  |  | 0
Miyano CNC Bar | G50-5SS(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A06201-0020 | 0.843 |  | 12.9 | 0 | 0
Bridgeport CNC Mill | G50-5SS(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-5(A) | NA |  |  | 0
Citizen | G50-8BSS |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0010 | 0.0903 | 0.044 | 3.23 | 0 | 0
B/S 18 | G50-8SS (1/2) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A06201-0010 | 0.0843 | 0.065 | 3.23 | 0 | 0
B/S 18 | G50-8SS (2/2) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | G50-8SS (1/2) | NA |  |  | 0
Miyano Chucker | G75-1A |  | 0 | 0 |  | 36 | 1 | 1 | 0 | A02001-0024 | 0.055 |  | 19.53 | 0 | 0
Miyano Chucker | G75-1ASS |  | 0 | 0 |  | 5 | 4 | 4 | 1 | G50-1A-BLNK | NA |  |  | 0 | [5 empty] | 2 ops 3 jaw/ 1 op 2 jaw
Miyano Chucker | G75-1GSS |  | 0 | 0 |  | 9 | 4 | 4 | 1 | G75-1ASS-BLNK | NA |  |  | 0 | [5 empty] | 3 ops 2 jaw
H2 | GA-BLNK |  | 0 | 0 |  | 15 | 1 | 1 | 0 | A06101-0024 | 0.0478 |  | 18.02 | 0 | 0
Cobra or Okuma | GP25PTC6001(1/2) |  | 0 | 0 | 0 | 13 | 4 | 4 | 1 | A02002-0024 | 0.2896 | 0.145 | 21.54 | 0 | 0
Cobra or Okuma | GP25PTC6001(2/2) |  | 0 | 0 |  | 24 | 0.33 | 0.33 | 0 | GP25PTC6001(1/2) | NA |  |  | 0
Cobra | GP25PTC6002(1/2) |  | 0 | 0 | 0 | 17 | 4 | 4 | 1 | A02002-0022 | 0.1589 | 0.059 | 18.1 | 0 | 0
Cobra | GP25PTC6002(2/2) |  | 0 | 0 |  | 32 | 1.5 | 1.5 | 0 | GP25PTC6002(1/2) | NA |  |  | 0
H2 | GR4 |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0024 | 0.1413 | 0.034 | 19.53 | 0 | 0
H2 | GR5 |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0024 | 0.1556 | 0.034 | 19.53 | 0 | 0
H2 | GR6 |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02071-0024 | 0.1556 | 0.034 | 19.53 | 0 | 0
H2 | GR-BLNK |  | 0 | 0 | 0 | 39 | 1 | 1 | 0 | A02071-0024 | 0.1413 | 0.034 | 19.53 | 0 | 0
Okuma-Cadet | IC10012 (1/2) |  | 0 | 0 | 0 | 8 | 4 | 4 | 1 | A02002-0048 | 0.978 | 0.44 | 86.14 | 0 | 0
Cobra | IC10012 (2/2) |  | 0 | 0 |  | 3 | 4 | 4 | 1 | IC10012 (1/2) | NA |  |  | 0
Okuma-Cadet | IC10013 (1/2) |  | 0 | 0 | 0 | 3 | 4 | 4 | 1 | A02002-0048 | 1.7709 | 0.419 | 86.14 | 0 | 0
Cobra | IC10013 (2/2) |  | 0 | 0 |  | 3 | 4 | 4 | 1 | IC10013 (1/2) | NA |  |  | 0
Ganesh CNC | IC10021-00 |  | 0 | 0 |  | 16 | 6 | 6 | 1 | A02002-0048 | 2.0997 |  | 86.14 | 0 | 0 | 2017
Ganesh CNC | IC10022 |  | 0 | 0 |  | 10 | 6 | 6 | 1 | A02002-0048 | 1.7835 |  | 86.14 | 0 | 0 | 2017
H3 | IC38001 (1/3) |  | 0 | 0 | 0 | 10 | 6 | 6 | 1 | A02002-0026 | 0.3859 | 0.121 | 25.27 | 0 | 0
H3 | IC38001 (2/3) |  | 0 | 0 |  | 10 | 6 | 6 | 1 | IC38001 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | IC38001 (3/3) |  | 0 | 0 |  | 10 | 6 | 6 | 1 | IC38001 (2/3) | NA |  |  | 0
4 Way | IC75001(A) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | IC75001-10 | NA |  |  | 0
Hass Vertical Mill VF3 | IC75001(B) |  | 0 | 0 |  | 240 | 2 | 2 | 0 | IC75001(A) | NA |  |  | 0
B&S16 | IC75001-10 |  | 0 | 0 |  | 80 | 4 | 4 | 1 | IC75001-20 | NA |  |  | 0
Okuma-Cadet | IC75001-20 |  | 0 | 0 |  | 190 | 16 | 16 | 2 | A02002-0038 | 1.0921 |  | 54.03 | 0 | 0
Haas Vertical Mill VF3 | IF5050B24 (2/2) |  | 0 | 0 |  | 54 | 4 | 4 | 1 | IF5050B24 (1/2) | NA |  |  | 0
Haas Vertical Mill VF3 | IF5050B26 (2/2) |  | 0 | 0 |  | 54 | 4 | 4 | 1 | IF5050B26 (1/2) | NA |  |  | 0
Hass Vertical Mill VF3 | IF6275B25 | obsolete routing | 0 | 0 |  | 54 | 1.5 | 1.5 | 0 | IF6275B25-10 | NA |  |  | 0
Hass Vertical Mill VF3 | IF6275B26 | Non-Stnd | 0 | 0 |  | 54 | 1.5 | 1.5 | 0 | IF6275B25 | NA |  |  | 0
Hass Vertical Mill VF3 | IF7575B24 |  | 0 | 0 |  | 285 | 0.5 | 0.5 | 0 | IF7575B24-10 | NA |  |  | 0
Bridgeport Drill Press | IL10001-01 | Backup Normally Purchased | 0 | 0 |  | 38 | 0.75 | 0.75 | 0 | IL10001 | NA |  |  | 0
DRILL PRESS-0063 | IL10005 | Backup only | 0 | 0 |  | 18 | 1 | 1 | 0 | IL10005-10 | NA |  |  | 0
Ganesh or Genos | IL10005 |  | 0 | 0 | 0 | 13 | 6 | 6 | 1 | A09001-0056 | 0.3063 | 0.0709 | 34.67 | 0 | 0 | 2016
T-42 | IL10005-10 | Backup only | 0 | 0 |  | 24 | 4 | 4 | 1 | IL10005-20 | NA |  |  | 0
T-42 | IL10005-20 | Backup only | 0 | 0 |  | 13 | 6 | 6 | 1 | A09001-0056 | 0.2972 |  | 34.67 | 0 | 0
B&S 17 | IL20014(2/2) |  | 0 | 0 |  | 60 | 4 | 4 | 1 | IL20014(1/2) | NA |  |  | 0
B&S 17 | Il20015 |  | 0 | 0 | 0 | 125 | 4 | 4 | 1 | IL10012 | NA | 0.19074 |  | 0
Haas Vertical Mill VF3 | IM10010 | Backup--Now Purchased | 0 | 0 |  | 38 | 0.75 | 0.75 | 0 | IM10010-10 | NA |  |  | 0
H2 or LB3000 | J1 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J1/2 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J1/4 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J1/4 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J1/6 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J1/9 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J1-1/2 |  | 0 | 0 | 0 | 48 | 2 | 2 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J2 |  | 0 | 0 | 0 | 31 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J2-1/2 |  | 0 | 0 | 0 | 36 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J3 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J3/4 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J4 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J5 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J6 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J8 |  | 0 | 0 | 0 | 64 | 1 | 1 | 0 | A02001-0016 | 0.0284 | 0.013 | 8.68 | 0 | 0
H2 or LB3000 | J-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02001-0016 | 0.024 | 0.013 | 8.68 | 0 | 0
H2 | JR1/2 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | JR-BLNK | NA | 0.026 |  | 0
H2 | JR-BLNK |  | 0 | 0 | 0 | 27 | 3 | 3 | 0 | A02001-0016 | 0.094 | 0.026 | 8.68 | 0 | 0
M1 | KF100601-01(A) |  | 0 | 0 |  | 27 | 3 | 3 | 0 | A02071-0034 | 0.4424 |  | 39.2 | 0 | 0
Drill Room | KF100601-01(B) |  | 0 | 0 |  | 10 | 3 | 3 | 0 | KF100601-01(A) | NA |  |  | 0
H3 | KF105610-10(A) |  | 0 | 0 |  | 5 | 8 | 8 | 1 | A06501-0060 | 0.4424 |  | 112.7 | 0 | 0
Haas Vertical Mill VF4 | KF105610-10(B) |  | 0 | 0 |  | 5 | 8 | 8 | 1 | KF105610-10(A) | NA |  |  | 0
H3 | KF118401-05 |  | 0 | 0 |  | 32 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
H3 | KF118401-05-1/2 |  | 0 | 0 |  | 32 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
H3 | KF118401-05-1/3 |  | 0 | 0 |  | 32 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
H3 | KF118401-05-1/4 |  | 0 | 0 |  | 32 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
H3 | KF118401-05-1/6 |  | 0 | 0 |  | 32 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
H3 | KF118401-05-1/9 |  | 0 | 0 |  | 32 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
Citizen | KF120601-10 |  | 0 | 0 | 0 | 54 | 1 | 1 | 0 | A02001-0026 | 0.242 | 0.087 | 22.95 | 0 | 0
Citizen | KF120601-12 |  | 0 | 0 | 0 | 32 | 1 | 1 | 0 | A02001-0026 | 0.242 | 0.087 | 22.95 | 0 | 0
Okuma-LB3000 | KF131610-4-4 |  | 0 | 0 | 0 | 44 | 3 | 3 | 0 | A19101-0032 | 0.1363 | 0.029 | 11.32 | 0 | 0
H3 | KF990002-10 |  | 0 | 0 | 0 | 44 | 3 | 3 | 0 | A19101-0032 | 0.1363 | 0.029 | 11.32 | 0 | 0
Okuma Genos | KF990002-4-4 |  | 0 | 0 | 0 | 44 | 3 | 3 | 0 | A19101-0032 | 0.1363 | 0.029 | 11.32 | 0 | 0
Haas Vertical Mill VF3 | KF990002-4-5 |  | 0 | 0 |  | 16 | 2 | 2 | 0 | KF990002-10 | NA |  |  | 0
H3 | KF990008 |  | 0 | 0 |  | 44 | 3 | 3 | 0 | A02071-0028 | 0.258 |  | 26.58 | 0 | 0
Haas Vertical Mill VF4 | KF990013-10-0 |  | 0 | 0 |  | 2 | 1 | 1 | 0 | 2803-A-BLNK | NA |  |  | 0
Haas Vertical Mill VF4 | KF990013-7 |  | 0 | 0 |  | 2 | 1 | 1 | 0 | 2803-A-BLNK | NA |  |  | 0
H3 | KF990015-02-5 |  | 0 | 0 |  | 44 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
H3 | KF99015-02 |  | 0 | 0 |  | 44 | 1 | 1 | 0 | A02001-0024 | 0.0592 |  | 19.53 | 0 | 0
H3 | KF99015-02-1 |  | 0 | 0 |  | 44 | 1 | 1 | 0 | A02001-0024 | 0.0554 |  | 19.53 | 0 | 0
H2 | L-BLNK | Backup only | 0 | 0 | 0 | 54 | 3 | 3 | 0 | A02001-0013 | 0.0112 | 0.007 | 5.73 | 0 | 0
H2 | L1/3 |  | 0 | 0 | 0 | 54 | 3 | 3 | 0 | A02001-0013 | 0.0158 | 0.007 | 5.73 | 0 | 0
H2 | L1/4 |  | 0 | 0 | 0 | 54 | 3 | 3 | 0 | A02001-0013 | 0.0158 | 0.007 | 5.73 | 0 | 0
H2 | L1-1/2 | Backup only | 0 | 0 | 0 | 54 | 3 | 3 | 0 | A02001-0013 | 0.0112 | 0.007 | 5.73 | 0 | 0
H2 | L1/9 | Backup only | 0 | 0 | 0 | 54 | 3 | 3 | 0 | A02001-0013 | 0.0112 | 0.007 | 5.73 | 0 | 0
H2 | L6 | Special stamp (H2 only) | 0 | 0 | 0 | 50 | 2 | 2 | 0 | A02001-0013 | 0.0158 | 0.007 | 5.73 | 0 | 0
H3 | LH50004 | Backup only | 0 | 0 |  | 36 | 16 | 16 | 2 | A19101-0022 | 0.0323 |  | 5.35 | 0 | 0
MILL-0469 | LH50011 |  | 0 | 0 |  | 56 | 2 | 2 | 0 | LH50011-10 | 1 |  |  | 0
Cobra | M1212001 | Backup only | 0 | 0 |  | 50 | 16 | 16 | 2 | A02005-0022 | 0.153 |  | 18.1 | 0 | 0
Cobra | M1212002(1/2) | Backup only | 0 | 0 |  | 50 | 0 | 0 | 0 | A02032-0022 | 0.1773 |  | 18.1 | 0 | 0
Cobra | M1212002(2/2) | Backup only | 0 | 0 |  | 50 | 0 | 0 | 0 | M1212002(1/2) | 0.1773 |  |  | 0
Okuma-Cadet | M12527 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A02001-0046 | 1.608 |  | 71.75 | 0 | 0
B&S Ultramatic #3 | M20005-1 |  | 0 | 0 | 0 | 62 | 1 | 1 | 0 | M20005 | NA | 0.02958 |  | 0
Hass Vertical Mill VF4 | M20021 |  | 0 | 0 | 0 | 150 | 0.75 | 0.75 | 0 | M20021-10 | NA | 0.3524 |  | 0
Hass Vertical Mill VF4 | M20021BSP |  | 0 | 0 | 0 | 150 | 0.75 | 0.75 | 0 | M20021-10 | NA | 0.367 |  | 0
Bridgeport Drill Press | M20035BSP-10 |  | 0 | 0 |  | 150 | 0.75 | 0.75 | 0 | M20035-10 | NA |  |  | 0
Citizen | M20055 | Backup for Davenport | 0 | 0 |  | 90 | 16 | 16 | 2 | A02001-0010 | 0.0145 |  | 3.39 | 0 | 0
B/S | M20058 |  | 0 | 0 |  | 35 | 2 | 2 | 0 | A02001-0018 | 0.0178 |  | 10.99 | 0 | 0
B/S | M20066 | Sec for Davenport | 0 | 0 |  | 35 | 2 | 2 | 0 | M20066-10 | NA |  |  | 0
H2 | M20066 (1/2) | New Routing | 0 | 0 | 0 | 17 | 4 | 4 | 1 | A02001-0022 | 0.1756 | 0.0643 | 16.41 | 0 | 0 |  |  |  |  | Moved to H2 2018
H2 | M20066 (2/2) | New Routing | 0 | 0 |  | 28 | 5.5 | 5.5 | 1 | M20066 (1/2) | NA |  |  | 0
B&S 18 | M2525004-10 |  | 0 | 0 | 0 | 120 | 4 | 4 | 1 | A02001-0010 | 0.0097 | 0.003 | 3.39 | 0 | 0
Auto Mill-0469 | M2525082 |  | 0 | 0 | 0 | 72 | 4 | 4 | 1 | M2525051 | NA | 0.00721 |  | 0
Lathe 068 | M2525052 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | M2525051 | NA | 0.00721 |  | 0
Hass Vertical Mill VF4 | M30035-1 |  | 0 | 0 | 0 | 187 | 1 | 1 | 0 | M30035 | NA | 0.539 |  | 0
Okuma-Cadet | M30090 | acme | 0 | 0 |  | 6 | 5 | 5 | 1 | A02002-0032 | 0.6685 |  | 38.29 | 0 | 0
Bridgeport CNC Mill | M30091 (C) | hydromat | 0 | 0 |  | 46 | 0 | 0 | 0 | M30091(B) | NA |  |  | 0
Okuma-Cadet | M30091(A) | hydromat | 0 | 0 |  | 7 | 5 | 5 | 1 | A02002-0032 | 0.6145 |  | 38.29 | 0 | 0
Cobra | M30091(B) | hydromat | 0 | 0 |  | 3 | 12 | 12 | 2 | M30091(A) | NA |  |  | 0
Okuma-Cadet | M30092 | acme | 0 | 0 |  | 29 | 5 | 5 | 1 | A02002-0038 | 0.2456 |  | 54.03 | 0 | 0
Okuma-Cadet | M30096(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02002-0032 | 0.2634 |  | 38.29 | 0 | 0
Okuma-Cadet | M30096(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | M30096(A) | NA |  |  | 0
T42 | M30097(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02002-0032 | 0.475 |  | 38.29 | 0 | 0
T42 | M30097(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | M30097(B) | NA |  |  | 0
Mill | M30097(C) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | M30097(B) | NA |  |  | 0
Cobra | M30281D1 (A) |  | 0 | 0 |  | 8 | 16 | 16 | 2 | NO BOM | NA |  |  | 0
Cobra | M30281D1 (B) |  | 0 | 0 |  | 8 | 8 | 8 | 1 | NO BOM | NA |  |  | 0
Cobra | M30281E1 (A) |  | 0 | 0 |  | 8 | 16 | 16 | 2 | NO BOM | NA |  |  | 0
Cobra | M30281E1 (B) |  | 0 | 0 |  | 8 | 8 | 8 | 1 | NO BOM | NA |  |  | 0
T42 | M31070(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02002-0032 | 0.475 |  | 38.29 | 0 | 0
T42 | M31070(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | M31070(B) | NA |  |  | 0
Mill | M31070(C) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | M31070(B) | NA |  |  | 0
B&S17 | M40070(2/2) |  | 0 | 0 |  | 249 | 1.5 | 1.5 | 0 | M40070(1/2) | NA |  |  | 0
Citizen | M4-4-3 |  | 0 | 0 | 0 | 57 | 0 | 0 | 0 | A02071-0026 | 0.249 | 0.0831 | 22.95 | 0 | 0
4 Way | M7575650 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | M7575650-10 | NA |  |  | 0
4Way | M7575650 |  | 0 | 0 |  | 9 | 4 | 4 | 1 | M7575650-10(B) | NA |  |  | 0
Cobra | M7575650-10 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | M7575650-10(A) | NA |  |  | 0
Okuma-Cadet | M7575650-10(A) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A02002-0036 | 1.31 |  | 48.45 | 0 | 0
T42 | MPC40001 | STND | 0 | 0 | 0 | 11 | 4 | 4 | 1 | A02001-0042 | 1.2907 | 0.298 | 59.81 | 0 | 0
Haas Live Tool (H2) | MPC40001 | NON STND | 0 | 0 | 0 | 6 | 4 | 4 | 1 | A02001-0042 | 1.4551 | 0.298 | 59.81 | 0 | 0
T-42 | MPC40003 | NON STND | 0 | 0 | 0 | 12 | 4.5 | 4.5 | 1 | A02002-0048 | 0.6224 | 0.274 | 86.14 | 0 | 0
Okuma-Cadet | MPC40003 | STND | 0 | 0 | 0 | 12 | 4.5 | 4.5 | 1 | A02002-0048 | 0.6357 | 0.274 | 86.14 | 0 | 0
Drill Press | ND6215 |  | 0 | 0 |  | 161 | 0.5 | 0.5 | 0 | ND6215-10 | NA |  |  | 0
Drill Press | NL2518 |  | 0 | 0 |  | 150 | 1 | 1 | 0 | NL2512 | NA |  |  | 0
B&S17 | NN38B21(2/3) |  | 0 | 0 |  | 103 | 4 | 4 | 1 | NN38B21(3/3) | NA |  |  | 0
Hass Vertical Mill VF3 | NN38B21(3/3) |  | 0 | 0 |  | 90 | 0.5 | 0.5 | 0 | NN38B21(2/3) | NA |  |  | 0
Ganesh CNC | P1010001 |  | 0 | 0 | 0 | 12 | 16 | 16 | 2 | A02002-0048 | 2.9383 | 2.181 | 86.14 | 0 | 0
Ganesh CNC | P1010001-00 |  | 0 | 0 | 0 | 36 | 16 | 16 | 2 | A02002-0048 | 2.9383 | 2.181 | 86.14 | 0 | 0
H3 | P1010001 (1/3) |  | 0 | 0 | 0 | 15 | 4 | 4 | 1 | A02002-0048 | 2.9383 | 2.181 | 86.14 | 0 | 0
H3 | P1010001 (2/3) |  | 0 | 0 |  | 14 | 4 | 4 | 1 | P1010001 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | P1010001 (3/3) |  | 0 | 0 |  | 27 | 3 | 3 | 0 | P1010001 (2/3) | NA |  |  | 0
Hass Vertical Mill VF3 | P1010001 |  | 0 | 0 | 0 | 27 | 3 | 3 | 0 | P1010001-00 | NA | 2.181 |  | 0
Hass Vertical Mill VF3 | P1012001-00 |  | 0 | 0 | 0 | 64 | 4 | 4 | 1 | P1012001-10 | NA | 2.181 |  | 0
Hass Vertical Mill VF3 | P1012001-02 |  | 0 | 0 | 0 | 64 | 4 | 4 | 1 | P1012001-10 | NA | 2.181 |  | 0
Okuma-Cadet | P1212001-10 (1/2) |  | 0 | 0 | 0 | 5 | 2 | 2 | 0 | A02002-0060 | 4.6706 | 1.382 | 134.6 | 0 | 0
Cobra | P1212001-10 (2/2) |  | 0 | 0 |  | 12 | 3 | 3 | 0 | P1212001-10 (1/2) | NA |  |  | 0
Hass Vertical Mill VF3 | P1212001-00 |  | 0 | 0 |  | 64 | 4 | 4 | 1 | P1212001-10 | NA |  |  | 0
Hass Vertical Mill VF3 | P1212001 |  | 0 | 0 |  | 34 | 4 | 4 | 1 | P1212001-10 | NA |  |  | 0
4Way | P1212001(A) |  | 0 | 0 |  | 9 | 4 | 4 | 1 | P1212001-10 | NA |  |  | 0
Hass Vertical Mill VF3 | P1212001(B) |  | 0 | 0 |  | 34 | 4 | 4 | 1 | P1212001(A) | NA |  |  | 0
4Way | P1212001-00 |  | 0 | 0 |  | 34 | 0.5 | 0.5 | 0 | P1212001-10 | NA |  |  | 0
Hass Vertical Mill VF3 | P1212001-02 |  | 0 | 0 |  | 34 | 4 | 4 | 1 | P1212001-00 | NA |  |  | 0
Okuma-Cadet | P1212001-10 (A) |  | 0 | 0 |  | 5 | 2 | 2 | 0 | A02002-0060 | 4.6706 |  | 134.6 | 0 | 0
Cobra | P1212001-10 (B) |  | 0 | 0 |  | 17 | 3 | 3 | 0 | P1212001-10 (A) | NA |  |  | 0
Okuma-Cadet | P1275B40-10 (A) |  | 0 | 0 |  | 8 | 4 | 4 | 1 | A02002-0054 |  |  | 109 | 0 | 0
Cobra | P1275B40-10 (B) |  | 0 | 0 |  | 51 | 4 | 4 | 1 | P1275B40-10 (A) | NA |  |  | 0
4 Way | P1515001(A) |  | 0 | 0 |  | 90 | 4 | 4 | 1 | P1515001-10 | NA |  |  | 0
Hass Vertical Mill VF3 | P1515001(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | P1515001-10 | NA |  |  | 0
Okuma-Cadet | P1515001-10 (1/2) |  | 0 | 0 | 0 | 19 | 2 | 2 | 0 | A02002-0072 | 6.9704 | 1.763 | 193.82 | 0 | 0
Cobra | P1515001-10 (2/2) |  | 0 | 0 |  | 19 | 4 | 4 | 1 | P1515001-10 (1/2) | NA |  |  | 0
Hass Vertical Mill VF4 | P25010 |  | 0 | 0 | 0 | 96 | 4 | 4 | 1 | P25001 | NA | 0.2212 |  | 0
4 Way | P25031 |  | 0 | 0 | 0 | 150 | 0.6 | 0.6 | 0 | P25031-10 | NA | 0.0668 |  | 0
Hass Vertical Mill VF3 | P2550B23 |  | 0 | 0 | 0 | 34 | 4 | 4 | 1 | P2550B23-00 | NA | 0.318 |  | 0
Hass Vertical Mill VF3 | P2575B21 |  | 0 | 0 |  | 30 | 4 | 4 | 1 | P2575B21(A) | NA |  |  | 0
Okuma-Cadet | P2575B21-10 (A) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | A02002-0036 | 0.7571 |  | 48.45 | 0 | 0
Cobra | P2575B21-10 (B) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | P2575B21-10 (A) | NA |  |  | 0
Hass Vertical Mill VF3 | P3838B21 |  | 0 | 0 | 0 | 75 | 4 | 4 | 1 | P3838B21-10 | NA | 0.323 |  | 0
Hass Vertical Mill VF3 | P3838B21-00 |  | 0 | 0 | 0 | 75 | 4 | 4 | 1 | P3838B21-10 | NA | 0.323 |  | 0
4 way | P3850001(A) |  | 0 | 0 |  | 240 | 4 | 4 | 1 | P3850001-10 | NA |  |  | 0
Hass Vertical Mill VF3 | P3850001(B) |  | 0 | 0 |  | 43 | 2 | 2 | 0 | P3850001(A) | NA |  |  | 0
Hass Vertical Mill VF3 | P3850001-02 |  | 0 | 0 |  | 4 | 4 | 4 | 1 | P3850001 | NA |  |  | 0
H3 | P3850001 (1/3) | Stnd | 0 | 0 | 0 | 30 | 16 | 16 | 2 | A02002-0028 | 0.6352 | 0.336 | 29.31 | 0 | 0
Cobra | P3850001 (2/3) | Stnd | 0 | 0 |  | 22 | 2.5 | 2.5 | 0 | P3850001 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | P3850001 (3/3) | Stnd | 0 | 0 |  | 34 | 4 | 4 | 1 | P3850001 (2/3) | NA |  |  | 0
4 way | P3850B21-00 |  | 0 | 0 |  | 30 | 4 | 4 | 1 | P3520B21-10 | NA |  |  | 0
Hass Vertical Mill VF3 | P5050001-02 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | P5050001-00 | NA | 0.265 |  | 0
4 Way | P5050B24-00 |  | 0 | 0 |  | 90 | 4 | 4 | 1 | P5050B21-10 | NA |  |  | 0
4Way | P5050B26 |  | 0 | 0 |  | 93 | 1 | 1 | 0 | P5050B21-10 | NA |  |  | 0
H1 | P5050B26 ( A ) | Backup only | 0 | 0 |  | 93 | 1 | 1 | 0 | P5050B26 (B) | NA |  |  | 0
4Way | P5050B26 ( C ) | Backup only | 0 | 0 |  | 4 | 4 | 4 | 1 | P5050B26 (A) | 0.7571 |  |  | 0
H1 | P5050B26 (B) | Backup only | 0 | 0 |  | 4 | 4 | 4 | 1 | A02002-0032 | 0.7324 |  | 38.29 | 0 | 0
Hass Vertical Mill VF3 | P5075001 |  | 0 | 0 |  | 4 | 4 | 4 | 1 | P5075001-00 | NA |  |  | 0
4 Way | P5075001-00 |  | 0 | 0 |  | 4 | 4 | 4 | 1 | P5075001-10 | NA |  |  | 0
Hass Vertical Mill VF3 | P5075001-02 |  | 0 | 0 | 0 | 4 | 4 | 4 | 1 | P5075001-00 | NA | 0.4095 |  | 0
Hass Vertical Mill VF3 | P5075B21 |  | 0 | 0 |  | 4 | 4 | 4 | 1 | P5075B21(A) | NA |  |  | 0
4 Way | P5075B21(A) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | P5075B21-10 | NA |  |  | 0
Okuma or H3 | P5075B21-10 (A) |  | 0 | 0 |  | 9 | 2 | 2 | 0 | A02002-0038 | 0.885 |  | 54.03 | 0 | 0
Cobra or H3 | P5075B21-10 (B) |  | 0 | 0 |  | 21 | 2 | 2 | 0 | P5075B21-10 (A) | NA |  |  | 0
Hass Vertical Mill VF3 | P5075B23 |  | 0 | 0 |  | 4 | 4 | 4 | 1 | P5075B21 | NA |  |  | 0
4 way | P5075B24 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | P5075B24-10 | NA |  |  | 0
Okuma-Cadet | P5075B24-10 (A) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A02002-0038 | 0.885 |  | 54.03 | 0 | 0
Cobra | P5075B24-10 (B) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | P5075B24-10 (A) | NA |  |  | 0
Cobra | P50P50001 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | P50P50001(A) | NA |  |  | 0
Okuma-Cadet | P50P50001(A) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A06102-0032 | 0.7011 |  | 35.33 | 0 | 0
T42 | P50P50002 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A06101-0024 | 0.1053 |  | 18.02 | 0 | 0
Okuma-Cadet | P50P50003 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A06101-0024 | 0.0317 |  | 18.02 | 0 | 0
Ganesh CNC | P7510001 |  | 0 | 0 | 0 | 16 | 16 | 16 | 2 | A02002-0042 | 1.9287 | 0.6327 | 65.95 | 0 | 0
Hass Vertical Mill VF3 | P7510001 |  | 0 | 0 |  | 90 | 4 | 4 | 1 | P7510001(A) | NA |  |  | 0
4 way | P7510001(A) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | P7510001-10 | NA |  |  | 0
Ganesh CNC | P7510001-00 |  | 0 | 0 |  | 16 | 16 | 16 | 2 | A02002-0042 | 1.9287 |  | 65.95 | 0 | 0
Hass Vertical Mill VF3 | P7510001-02 |  | 0 | 0 | 0 | 16 | 4 | 4 | 1 | P7510001 | NA | 0.4025 |  | 0
CHUCKER | P7510001-10 |  | 0 | 0 |  | 19 | 2 | 2 | 0 | P7510001-20 | NA |  |  | 0
4 Way | P7510001-10(A) |  | 0 | 0 |  | 90 | 4 | 4 | 1 | P7510001-10 | NA |  |  | 0
Bridgeport CNC Mill | P7510001-5 |  | 0 | 0 |  | 27 | 1 | 1 | 0 | P7510001-10 | NA |  |  | 0
Okuma-Cadet | P7510001-5 (1/3) | NON STND | 0 | 0 | 0 | 9 | 2 | 2 | 0 | A02002-0042 | 1.9287 | 0.627 | 65.95 | 0 | 0
Cobra | P7510001-5 (2/3) | NON STND | 0 | 0 |  | 21 | 2 | 2 | 0 | P7510001-5 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | P7510001-5 (3/3) | NON STND | 0 | 0 |  | 19 | 4 | 4 | 1 | P7510001-5 (2/3) | NA |  |  | 0
Ganesh | P7510001-5 | stnd | 0 | 0 | 0 | 12 | 1 | 1 | 0 | A02002-0042 | 1.9287 | 0.627 | 65.95 | 0 | 0
Okuma-Cadet | P7510050 (1/3) |  | 0 | 0 | 0 | 9 | 2 | 2 | 0 | A02002-0042 | 1.91 | 0.65 | 65.95 | 0 | 0
Cobra | P7510050 (2/3) |  | 0 | 0 |  | 21 | 2 | 2 | 0 | P7510050 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | P7510050 (3/3) |  | 0 | 0 |  | 19 | 4 | 4 | 1 | P7510050 (2/3) | NA |  |  | 0
Hass Vertical Mill VF3 | P7515001 |  | 0 | 0 |  | 19 | 4 | 4 | 1 | P7515001-10 | NA |  |  | 0
Okuma-Cadet | P7515001-10 (1/2) |  | 0 | 0 | 0 | 6 | 4 | 4 | 1 | A02002-0072 | 6.9704 | 2.49 | 193.82 | 0 | 0
Cobra | P7515001-10 (2/2) |  | 0 | 0 |  | 19 | 4 | 4 | 1 | P7515001-10 (1/2) | NA |  |  | 0
Hass Vertical Mill VF3 | P7575001-02 |  | 0 | 0 | 0 | 16 | 4 | 4 | 1 | P7575001 | NA | 0.4025 |  | 0
Hass Vertical Mill VF3 | P7575008 |  | 0 | 0 |  | 16 | 4 | 4 | 1 | P7575001-00 | NA |  |  | 0
B&S17 | P7575030 |  | 0 | 0 |  | 94 | 4 | 4 | 1 | P7575030 | NA |  |  | 0
Hass Vertical Mill VF4 | P7575B25 | Hydromat | 0 | 0 | 0 | 16 | 1 | 1 | 0 | P7575B21-00 | NA | 0.332 |  | 0
Lathe-0468 | P7575B26-2 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | P7575B26 | NA | 0.001 |  | 0
Lathe-0468 | P7575B26-3 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | P7575B26 | NA | 0.001 |  | 0
Lathe-0468 | P7575B26-4 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | P7575B26 | NA | 0.001 |  | 0
Lathe-0468 | P7575B26-5 |  | 0 | 0 | 0 | 93 | 1 | 1 | 0 | P7575B26 | NA | 0.001 |  | 0
B&S16 | P7575B31-10 |  | 0 | 0 |  | 80 | 4 | 4 | 1 | P7575B31-20 | NA |  |  | 0
Hass Vertical Mill VF3 | P7575B71-02 |  | 0 | 0 |  | 48 | 1 | 1 | 0 | P7575B71-00-P | NA |  |  | 0
Okuma-Genos | PCV10001 |  | 0 | 0 | 0 | 7 | 16 | 16 | 2 | A01001-0073 | 6.48 | 1.25 | 171.4 | 0 | 0 |  |  |  |  | 2018
M1 | PCV10002 (2/2) |  | 0 | 0 | 0 | 54 | 16 | 16 | 2 | PCV10002 (1/2) | NA |  |  | 0
Citizen 2 | PCV10003 |  | 0 | 0 | 0 | 54 | 16 | 16 | 2 | A06101-7314 | 0.0525 | 0.04 | 3.56 | 0 | 0 |  |  |  |  | 2018
Genos | PCV10004 |  | 0 | 0 | 0 | 22 | 16 | 16 | 2 | A02001-0032 | 0.3937 | 0.1 | 34.72 | 0 | 0 |  |  |  |  | 2018
B&S18 | PG1004 |  | 0 | 0 |  | 80 | 4 | 4 | 1 | A06001-0004 | 0.0054 |  | 0.5004 | 0 | 0
Cobra | PG1005 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A02001-0008 | 0.0061 |  | 2.17 | 0 | 0
T42 | PG1007 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A06101-0016 | 0.404 |  | 8.01 | 0 | 0
T42 | PG1008 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A02001-0020 | 0.0851 |  | 13.56 | 0 | 0
Cobra | PG1011(A) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A01002-0024 | 0.1837 |  | 19.89 | 0 | 0
Cobra | PG1011(B) |  | 0 | 0 |  | 6 | 2 | 2 | 0 | PG1011(A) | NA |  |  | 0
Drill Press | PG1012 |  | 0 | 0 |  | 150 | 0.25 | 0.25 | 0 | PG1012-10 | NA |  |  | 0
Cobra | PG1014 |  | 0 | 0 |  | 6 | 2 | 2 | 0 | A06001-0010 | 0.0046 |  | 3.13 | 0 | 0
Bridgeport- Drill Press | PPV10003(2/2) |  | 0 | 0 |  | 40 | 1 | 1 | 0 | PPV10003(1/2) | NA |  |  | 0
Cobra | PR140401-2 (A) |  | 0 | 0 |  | 18 | 8 | 8 | 1 | PR2545(A) | NA |  |  | 0
Cobra | PR140401-2 (B)
M1 | PR2545(A) |  | 0 | 0 |  | 8 | 0 | 0 | 0 | NO BOM | NA |  |  | 0
M1 | PR2545(B) |  | 0 | 0 |  | 8 | 8 | 8 | 1 | NO BOM | NA |  |  | 0
HEN | PWN150XX-HS |  | 0 | 0 |  | 144 | 1 | 1 | 0 | PWN150XX-HS-10 | NA |  |  | 0
HEN | PWN250XX-HS |  | 0 | 0 |  | 144 | 1 | 1 | 0 | PWN250XX-HS-10 | NA |  |  | 0
HEN | PWN400XX-HS |  | 0 | 0 |  | 144 | 1 | 1 | 0 | PWN400XX-HS-10 | NA |  |  | 0
Bridgeport Drill Press | R1006-1 |  | 0 | 0 |  | 25 | 4 | 4 | 1 | R1006-LF | NA |  |  | 0
Bridgeport Drill Press | R1006-2 |  | 0 | 0 |  | 25 | 4 | 4 | 1 | R1006-LF | NA |  |  | 0
B&S16 | R1310-10 |  | 0 | 0 |  | 153 | 0.08 | 0.08 | 0 | R1310-10U | NA |  |  | 0
B&S16 | R1310-12 |  | 0 | 0 |  | 153 | 0.08 | 0.08 | 0 | R1310-12U | NA |  |  | 0
B&S16 | R1310-48 |  | 0 | 0 |  | 153 | 0.08 | 0.08 | 0 | A06201-0008 | 0.6655 |  | 2.06 | 0 | 0
B/S #3 Ultra Only | R1310-8 |  | 0 | 0 | 0 | 153 | 4 | 4 | 1 | R1310-8U | NA | 0.1109 |  | 0
B&S16 | R1315-10 |  | 0 | 0 | 0 | 60 | 0.08 | 0.08 | 0 | R1315-10U | 1 | 0.998 |  | 0
B&S18 | R1315-12 |  | 0 | 0 | 0 | 153 | 0.08 | 0.08 | 0 | R1315-12U | NA | 0.1109 |  | 0
B&S18 | R1315-18 |  | 0 | 0 |  | 153 | 0.08 | 0.08 | 0 | A06201-0012 | 0.7166 |  | 4.65 | 0 | 0
B&S18 | R1315-24 |  | 0 | 0 |  | 153 | 0.08 | 0.08 | 0 | A06201-0012 | 3.0048 |  | 4.65 | 0 | 0
B&S18 | R1315-8 |  | 0 | 0 |  | 153 | 0.08 | 0.08 | 0 | A06201-0012 | 0.2504 |  | 4.65 | 0 | 0
B&S18 | R1315-96 |  | 0 | 0 |  | 153 | 0.08 | 0.08 | 0 | A06201-0012 | 3.0048 |  | 4.65 | 0 | 0
B&S18 | R400-104 |  | 0 | 0 | 0 | 78 | 6 | 6 | 1 | A01701-0040 | 0.0327 | 0.0137 | 13.8 | 0 | 0
B&S18 | R400-54 |  | 0 | 0 | 0 | 80 | 6 | 6 | 1 | A01701-0020 | 0.0092 | 0.001246 | 2.094 | 0 | 0
B&S18 | R400-64 |  | 0 | 0 | 0 | 80 | 4 | 4 | 1 | A01701-0024 | 0.0101 | 0.013 | 3.352 | 0 | 0
B&S18 | R400-73-3 |  | 0 | 0 |  | 107 | 8 | 8 | 1 | A01701-0024 | 0.48 |  | 3.352 | 0 | 0
Bridgeport Drill Press | R400SS-1 |  | 0 | 0 |  | 25 | 4 | 4 | 1 | R400-80-LF | NA |  |  | 0
Bridgeport Drill Press | R400SS-3/4 |  | 0 | 0 |  | 25 | 4 | 4 | 1 | R400-70-LF | NA |  |  | 0
M1 | R421-12BK-LF | Non Stnd | 0 | 0 | 0 | 37 | 16 | 16 | 2 | A03002-0038 | 0.1268 | 0.0216 | 54.03 | 0 | 0
Brown/Sharpe w/Lipe | R431-10 (1/2) | stnd | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.147 | 0.147 | 2.17 | 0 | 0 |  |  |  |  | 2018
Drill Press | R431-10 (2/2) | stnd | 0 | 0 |  | 128 | 0.5 | 0.5 | 0 | R431-10 (1/2) | NA |  |  | 0
Cut off Saw | R431-10(1/3) | non stnd | 0 | 0 |  | 128 | 0.5 | 0.5 | 0 | A02001-0008 | 0.147 |  | 2.17 | 0 | 0
Caged Die Head | R431-10(2/3) | non stnd | 0 | 0 |  | 128 | 0.5 | 0.5 | 0 | R431-10(1/3) | NA |  |  | 0
Drill Press | R431-10(3/3) | non stnd | 0 | 0 |  | 128 | 0.5 | 0.5 | 0 | R431-10(2/3) | NA |  |  | 0
Cut off Saw | R431-12(A) |  | 0 | 0 |  | 128 | 0.5 | 0.5 | 0 | A02001-0008 | 0.2523 |  | 2.17 | 0 | 0
Caged Die Head | R431-12(B) |  | 0 | 0 |  | 128 | 0.5 | 0.5 | 0 | R431-12(A) | NA |  |  | 0
Cut off Saw | R433-12(1/2) |  | 0 | 0 | 0 | 128 | 0.5 | 0.5 | 0 | A02001-0010 | 0.273 | 0.2703 | 3.39 | 0 | 0
Caged Die Head | R433-12(2/2) |  | 0 | 0 |  | 128 | 0.5 | 0.5 | 0 | R433-12(1/2) | NA |  |  | 0
B&S18 | R434-13(A) |  | 0 | 0 |  | 450 | 8 | 8 | 1 | A02002-0028 | 0.197 |  | 29.31 | 0 | 0
B&S18 | R434-13(B) |  | 0 | 0 |  | 120 | 8 | 8 | 1 | R434-13(A) | NA |  |  | 0
B&S18 | R434-3 (A) |  | 0 | 0 |  | 72 | 7 | 7 | 1 | A02002-0028 | 0.1884 |  | 29.31 | 0 | 0
B&S18 | R434-3 (B) |  | 0 | 0 |  | 144 | 16 | 16 | 2 | R434-3 (A) | NA |  |  | 0
B&S18 | R435-1(A) |  | 0 | 0 |  | 450 | 16 | 16 | 2 | A02002-0020 | 0.1179 |  | 14.96 | 0 | 0
B&S17 | R435-1(B) |  | 0 | 0 |  | 144 | 16 | 16 | 2 | R435-1(A) | NA |  |  | 0
B&S18 | R435-2(A) |  | 0 | 0 |  | 70 | 12 | 12 | 2 | A02002-0024 | 0.2131 |  | 21.54 | 0 | 0
B&S17 | R435-2(B) |  | 0 | 0 |  | 144 | 16 | 16 | 2 | R435-2(A) | NA |  |  | 0
B&S18 | R435-4(A) |  | 0 | 0 |  | 64 | 12 | 12 | 2 | A02002-0014 | 0.0613 |  | 7.33 | 0 | 0
B&S17 | R435-4(B) |  | 0 | 0 |  | 144 | 16 | 16 | 2 | R435-4(A) | NA |  |  | 0
B&S18 | R435-5(A) |  | 0 | 0 |  | 70 | 12 | 12 | 2 | A02002-0018 | 0.1048 |  | 12.11 | 0 | 0
B&S17 | R435-5(B) |  | 0 | 0 |  | 144 | 16 | 16 | 2 | R435-5(A) | NA |  |  | 0
B&S18 | R435-6(A) |  | 0 | 0 |  | 70 | 12 | 12 | 2 | A02002-0012 | 0.0367 |  | 5.38 | 0 | 0
B&S17 | R435-6(B) |  | 0 | 0 |  | 144 | 16 | 16 | 2 | R435-6(A) | NA |  |  | 0
B&S18 | R435-8(A) |  | 0 | 0 | 0 | 72 | 8 | 8 | 1 | A02002-0012 | 0.0325 | 0.0152 | 5.38 | 0 | 0
B&S17 | R435-8(B) |  | 0 | 0 |  | 144 | 16 | 16 | 2 | R435-8(A) | NA |  |  | 0
Cutoff Saw | R436-12 (1/2) |  | 0 | 0 | 0 | 94 | 2.5 | 2.5 | 0 | A02001-0012 | 0.405 | 0.398 | 4.88 | 0 | 0
Caged Die Head | R436-12 (2/2) |  | 0 | 0 |  | 94 | 2.5 | 2.5 | 0 | R436-12 (1/2) | NA |  |  | 0
Thread Roller | R450-10 |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R450-10U | NA |  |  | 0
Brown/Sharpe w/Lipe | R450-1-10 | stnd | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.1506 | 0.1506 | 2.17 | 0 | 0
Cut off Saw | R450-1-10(1/2) | non stnd | 0 | 0 | 0 | 144 | 4 | 4 | 1 | A02001-0008 | 0.1506 | 0.1506 | 2.17 | 0 | 0
Caged Die Head | R450-1-10(2/2) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-10(1/2) | NA |  |  | 0
Caged Die Head | R450-1-12(1/2) | non stnd | 0 | 0 | 0 | 144 | 4 | 4 | 1 | A02001-0008 | 0.1807 | 0.18052 | 2.17 | 0 | 0
Cut off Saw | R450-1-12(1/2) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-12(1/2) | NA |  |  | 0
Brown/Sharpe w/Lipe | R450-1-12 | stnd | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.1807 | 0.18052 | 2.17 | 0 | 0 |  |  |  |  | 2018
Caged Die Head | R450-1-14 (B) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-14(A) | NA |  |  | 0
Cut off Saw | R450-1-14(A) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | A02001-0008 | 0.2523 |  | 2.17 | 0 | 0
Cut off Saw | R450-1-18(A) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | A02001-0008 | 0.2711 |  | 2.17 | 0 | 0
Caged Die Head | R450-1-18(B) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | R450-1-18(A) | NA |  |  | 0
Thread Roller | R450-12 |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R450-12U | NA |  |  | 0
B&S17 | R450-1-2 |  | 0 | 0 |  | 144 | 1 | 1 | 0 | R450-1-2(A) | NA |  |  | 0
B&S18 | R450-1-2(A) |  | 0 | 0 |  | 144 | 1 | 1 | 0 | A02001-0008 | 0.041 |  | 2.17 | 0 | 0
Caged Die Head | R450-1-20 |  | 0 | 0 |  | 144 | 4 | 4 | 1 | R450-1-20(A) | NA |  |  | 0
Cutoff Saw | R450-1-20(A) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | A02001-0008 | 0.378 |  | 2.17 | 0 | 0
Cutoff Saw | R450-1-24 (1/2) |  | 0 | 0 | 0 | 144 | 4 | 4 | 1 | A02001-0008 | 0.3614 | 0.3614 | 2.17 | 0 | 0
Caged Die Head | R450-1-24 (2/2) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | R450-1-24 (1/2) | NA |  |  | 0
Cut off Saw | R450-1-3 (1/2) |  | 0 | 0 | 0 | 144 | 0.5 | 0.5 | 0 | A02001-0008 | 0.0515 | 0.0515 | 2.17 | 0 | 0
Caged Die Head | R450-1-3 (1/2) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-3 (1/2) | NA |  |  | 0
Brown/Sharpe w/Lipe | R450-1-3.5 | stnd | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.599 | 0.589 | 2.17 | 0 | 0 |  |  |  |  | 2018
Caged Die Head | R450-1-3.5 | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-3.5(A) | NA |  |  | 0
Cut off Saw | R450-1-3.5(A) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0008 | 0.0599 |  | 2.17 | 0 | 0
Cut off Saw | R450-1-36(A) |  | 0 | 0 |  | 144 | 4 | 4 | 1 | A02001-0008 | 0.5422 |  | 2.17 | 0 | 0
Caged Die Head | R450-1-36(B) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-36(A) | NA |  |  | 0
Brown/Sharpe w/Lipe | R450-1-4 | stnd | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.0683 | 0.06 | 2.17 | 0 | 0 |  |  |  |  | 2018
Caged Die Head | R450-1-4 | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-4(A) | NA |  |  | 0
Cut off Saw | R450-1-4(A) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0008 | 0.0683 |  | 2.17 | 0 | 0
Brown/Sharpe w/Lipe | R450-1-4.5 | new routing | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.0769 | 0.0769 | 2.17 | 0 | 0 |  |  |  |  | 2018
Cut off Saw | R450-1-4.5 (1/2) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0008 | 0.0769 | 0.0769 | 2.17 | 0 | 0
Caged Die Head | R450-1-4.5 (2/2) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-4.5 (1/2) | NA |  |  | 0
Brown/Sharpe w/Lipe | R450-1-5 | stnd | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.0855 | 0.08 | 2.17 | 0 | 0 |  |  |  |  | 2018
Caged Die Head | R450-1-5 | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-5(A) | NA |  |  | 0
Cutoff Saw | R450-1-5(A) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.25 | 0 | A02001-0008 | 0.0855 |  | 2.17 | 0 | 0
Caged Die Head | R450-16 |  | 0 | 0 |  | 144 | 1 | 1 | 0 | R450-16(A) | NA |  |  | 0
Caged Die Head | R450-1-6 |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0008 | 0.0904 |  | 2.17 | 0 | 0
CutOff Saw | R450-16(A) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0008 | 0.3375 |  | 2.17 | 0 | 0
Cut off Saw | R450-1-7 (1/2) |  | 0 | 0 | 0 | 144 | 4 | 4 | 1 | A02001-0008 | 0.1205 | 0.102 | 2.17 | 0 | 0
Caged Die Head | R450-1-7 (2/2) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-7 (1/2) | NA |  |  | 0
Brown/Sharpe w/Lipe | R450-1-8 | stnd | 0 | 0 | 0 | 96 | 4 | 4 | 1 | A02001-0008 | 0.1205 | 0.12 | 2.17 | 0 | 0 |  |  |  |  | 2018
Cut off Saw | R450-1-8(A) | non stnd | 0 | 0 |  | 144 | 4 | 4 | 1 | A02001-0008 | 0.1205 |  | 2.17 | 0 | 0
Caged Die Head | R450-1-8(B) | non stnd | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R450-1-8(A) | NA |  |  | 0
B&S17 | R450-2 | obsolete sub R450-1-2 | 0 | 0 |  | 144 | 1 | 1 | 0 | R450-2(A) | NA |  |  | 0
B&S18 | R450-2(A) | obsolete sub R450-1-3 | 0 | 0 |  | 144 | 1 | 1 | 0 | A02001-0008 | 0.041 |  | 2.17 | 0 | 0
Thread Roller | R450-3 |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R450-3U | NA |  |  | 0
Cut off Saw | R450-3.5SR |  | 0 | 0 |  | 144 | 1 | 1 | 0 | R450-3.5SR(A) | NA |  |  | 0
Caged Die Head | R450-3.5SR(A) |  | 0 | 0 |  | 144 | 1 | 1 | 0 | A02001-0008 | NA |  | 2.17 | 0 | 0
Thread Roller | R450-4 |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R450-4U | NA |  |  | 0
Thread Roller | R450-5 |  | 0 | 0 | 0 | 192 | 1 | 1 | 0 | R450-5U | NA | 0.055 |  | 0
Thread Roller | R450-6 |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R450-6U | NA |  |  | 0
Thread Roller | R450-8 |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R450-8U | NA |  |  | 0
CutOff Saw | R451-8 (1/2) |  | 0 | 0 | 0 | 144 | 0.5 | 0.5 | 0 | A02001-0010 | 0.182 |  | 3.39 | 0 | 0
Caged Die Head | R451-8 (2/2) |  | 0 | 0
CutOff Saw | R451-12 (1/2) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0010 | 0.273 |  | 3.39 | 0 | 0
Caged Die Head | R451-12 (2/2) |  | 0 | 0 |  | 50 | 1 | 1 | 0 | R451-12(A) | NA |  |  | 0
CutOff Saw | R452-10(1/2) |  | 0 | 0 | 0 | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 0.3375 | 0.337 | 4.88 | 0 | 0
Caged Die Head | R452-10(2/2) |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R452-10(1/2) | NA |  |  | 0
CutOff Saw | R452-12(1/2) |  | 0 | 0 | 0 | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 0.405 | 0.401 | 4.88 | 0 | 0
Caged Die Head | R452-12(2/2) |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R452-12(1/2) | NA |  |  | 0
CutOff Saw | R452-16(1/2) |  | 0 | 0 | 0 | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 0.54 | 0.052 | 4.88 | 0 | 0
Caged Die Head | R452-16(2/2) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R452-16(1/2) | NA |  |  | 0
Caged Die Head | R452-18(B) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R452-18(A) | NA |  |  | 0
CutOff Saw | R452-18(A) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 0.6075 |  | 4.88 | 0 | 0
Caged Die Head | R452-20 |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R452-20(A) | NA |  |  | 0
CutOff Saw | R452-20(A) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 0.675 |  | 4.88 | 0 | 0
CutOff Saw | R452-24 (1/2) |  | 0 | 0 | 0 | 72 | 0 | 0 | 0 | A02001-0012 | 0.81 | 0.8098 | 4.88 | 0 | 0
Caged Die Head | R452-24 (2/2) |  | 0 | 0 |  | 72 | 0.5 | 0.5 | 0 | R452-24 (1/2) | NA |  |  | 0
CutOff Saw | R452-36(A) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 1.215 |  | 4.88 | 0 | 0
Caged Die Head | R452-36(B) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R452-36(A) | NA |  |  | 0
Caged Die Head | R452-4 |  | 0 | 0 |  | 144 | 1 | 1 | 0 | R452-4(A) | NA |  |  | 0
CutOff Saw | R452-4(A) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 0.135 |  | 4.88 | 0 | 0
CutOff Saw | R452-6 (1/2) |  | 0 | 0 | 0 | 72 | 0 | 0 | 0 | A02001-0012 | 0.2314 | 0.197 | 4.88 | 0 | 0
Caged Die Head | R452-6 (2/2) |  | 0 | 0 |  | 72 | 0.5 | 0.5 | 0 | R452-6 (1/2) | NA |  |  | 0
CutOff Saw | R452-60(A) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 2.3361 |  | 4.88 | 0 | 0
Caged Die Head | R452-60(B) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | R452-60(A) | NA |  |  | 0
Caged Die Head | R453-12(B) |  | 0 | 0 |  | 144 | 0.5 | 0.5 | 0 | A02001-0012 | 0.405 |  | 4.88 | 0 | 0
CutOff Saw | R453-12A) |  | 0 | 0 |  | 192 | 1 | 1 | 0 | R453-12(A) | NA |  |  | 0
Caged Die Head | R455-10(A) |  | 0 | 0 |  | 72 | 0.5 | 0.5 | 0 | A02001-0014 | 0.5366 |  | 6.65 | 0 | 0
Cut Off Saw | R455-10(B) |  | 0 | 0 |  | 72 | 0 | 0 | 0 | R455-10(A) | NA |  |  | 0
Cut Off Saw | R455-12 (1/2) |  | 0 | 0 | 0 | 72 | 0.5 | 0.5 | 0 | A02001-0014 | 0.552 | 0.552 | 6.65 | 0 | 0
Caged Die Head | R455-12 (2/2) |  | 0 | 0 |  | 72 | 0 | 0 | 0 | R455-12 (1/2) | NA |  |  | 0
Cut off Saw | R455-24(A) |  | 0 | 0 |  | 72 | 0 | 0 | 0 | A02001-0014 | 1.104 |  | 6.65 | 0 | 0
Caged Die Head | R455-24(B) |  | 0 | 0 |  | 72 | 0.5 | 0.5 | 0 | R455-24(A) | NA |  |  | 0
Cut Off Saw | R455-36(A) |  | 0 | 0 |  | 72 | 0 | 0 | 0 | A02001-0014 | 1.656 |  | 6.65 | 0 | 0
Caged Die Head | R455-36(B) |  | 0 | 0 |  | 72 | 0.5 | 0.5 | 0 | R455-36(A) | NA |  |  | 0
Ganesh CNC | RCF001 | non stnd | 0 | 0 |  | 14 | 16 | 16 | 2 | A02031-0032 | 0.4987 |  | 34.72 | 0 | 0
T42 | RCF003 (1/2) | non stnd | 0 | 0 |  | 11 | 16 | 16 | 2 | A02001-0026 | 0.1442 |  | 22.95 | 0 | 0
Cobra | RCF003 (/2) | non stnd | 0 | 0 |  | 14 | 16 | 16 | 2 | RCF003 (1/2) | NA |  |  | 0
H2 | RCF013 (1/2) |  | 0 | 0 | 0 | 14 | 16 | 16 | 2 | A02001-0020 | 0.7 | 0.0861 | 13.56 | 0 | 0 |  |  |  |  | 2018
H2 | RCF013 (2/2) |  | 0 | 0 |  | 14 | 16 | 16 | 2 | RCF013 (1/2) | NA |  |  | 0 | [5 empty] | 2018
Citizen | RCF015-10 |  | 0 | 0 | 0 | 66 | 8 | 8 | 1 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 0 | 0
Citizen | RCF015-13 |  | 0 | 0 | 0 | 66 | 8 | 8 | 1 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 0 | 0
Citizen | RCF015-17 |  | 0 | 0 | 0 | 66 | 8 | 8 | 1 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 0 | 0
Citizen | RCF015-19 |  | 0 | 0 | 0 | 66 | 8 | 8 | 1 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 0 | 0
Citizen | RCF015-24 |  | 0 | 0 | 0 | 66 | 8 | 8 | 1 | A02001-0010 | 0.0015 | 0.001 | 3.39 | 0 | 0
Ganesh CNC | RCF101 |  | 0 | 0 | 0 | 16 | 16 | 16 | 2 | A02001-0036 | 0.37 | 0.0754 | 43.94 | 0 | 0
Ganesh CNC | RCF301 | new part | 0 | 0 | 0 | 12 | 32 | 32 | 4 | A06201-0032 | 0.5254 | 0.26 | 32.04 | 0 | 0 |  |  |  |  | 2018
Ganesh CNC | RCP001 | new part | 0 | 0 | 0 | 14 | 32 | 32 | 4 | A02001-0040 | 1.0002 | 0.53 | 54.25 | 0 | 0 |  |  |  |  | 2018
H3 | RCP002 | new part | 0 | 0 | 0 | 27 | 8 | 8 | 1 | A02001-0040 | 0.2129 | 0.1 | 54.25 | 0 | 0 |  |  |  |  | 2018
H2 | RCP007 (1/2) | new part | 0 | 0 | 0 | 27 | 8 | 8 | 1 | A02002-0014 | 0.065 | 0.03 | 7.33 | 0 | 0 |  |  |  |  | 2018
H2 | RCP007 (2/2) | new part | 0 | 0 |  | 50 | 4 | 4 | 1 | RCP007 (1/2) | NA |  |  | 0 | [5 empty] | 2018
T42 | RDF003(A) | sample | 0 | 0 |  | 54 | 16 | 16 | 2 | A19101-0060 | 0.001 |  | 38.96 | 0 | 0 |  |  |  |  | 2018
T42 | RDF003(B) |  | 0 | 0 |  | 90 | 16 | 16 | 2 | RDF003(A) | NA |  |  | 0 | [5 empty] | 2018
T42 | RDF004 | sample | 0 | 0 |  | 27 | 16 | 16 | 2 | A02001-0008 | 0.001 |  | 2.17 | 0 | 0 |  |  |  |  | 2018
Cobra | RDF005 | sample | 0 | 0 |  | 36 | 16 | 16 | 2 | A02001-0012 | 0.001 |  | 4.88 | 0 | 0 |  |  |  |  | 2018
T42 | RDF006 | sample | 0 | 0 |  | 72 | 16 | 16 | 2 | A02001-0010 | 0.001 |  | 3.39 | 0 | 0 |  |  |  |  | 2018
Model Shop | RG1331SR-2 |  | 0 | 0 |  | NA | NA | NA | NA | RG1331-2 | NA |  |  | 0
Hass Vertical Mill VF3 | RMB013 |  | 0 | 0 | 0 | 48 | 1 | 1 | 0 | RMB001 | NA | 0.582 |  | 0
Dedicated Drill Press | RP1201 | backup only | 0 | 0 |  | 25 | 0.5 | 0.5 | 0 | RP1200 | NA |  |  | 0
Dedicated Drill Press | RP1202 | backup only | 0 | 0 |  | 37 | 0.5 | 0.5 | 0 | RP1200 | NA |  |  | 0
Ganesh/ Genos | RP1201 | STND | 0 | 0 | 0 | 22 | 6 | 6 | 1 | A02001-0044 | 0.383 | 0.242 | 65.64 | 0 | 0 | 2016
Ganesh/Genos | RP1202 | STND | 0 | 0 | 0 | 23 | 0.5 | 0.5 | 0 | A02001-0044 | 0.383 | 0.242 | 65.64 | 0 | 0 | 2016
Cobra | S119S119001 | Backup for Acme | 0 | 0 |  | 13 | 2 | 2 | 0 | A02002-0040 | 1.3152 |  | 59.82 | 0 | 0
Cobra | S119S119001 |  | 0 | 0 |  | 13 | 2 | 2 | 0 | S119S119001-10 | NA |  |  | 0
Cobra | S119S119002 |  | 0 | 0 |  | 13 | 2 | 2 | 0 | S119S119002-10 | NA |  |  | 0
Drill Press | S119S119003 |  | 0 | 0 |  | 58 | 1 | 1 | 0 | S119S119003-10 | NA |  |  | 0
Okuma-Cadet | S144S144002(2/2) |  | 0 | 0 |  | 32 | 4 | 4 | 1 | S144S144002(1/2) | NA |  |  | 0
Hass Vertical Mill VF3 | S144S144003 (2/2) |  | 0 | 0 |  | 5 | 1 | 1 | 0 | S144S144003 (1/2) | NA |  |  | 0
Okuma-Cadet | S169S169001 |  | 0 | 0 |  | 12 | 3 | 3 | 0 | S169S169001-10 | NA |  |  | 0
OKUMA/T42 | S169S169001-10 |  | 0 | 0 |  | 15 | 6 | 6 | 1 | S169S169001-20 | NA |  |  | 0
T42/Okuma | S169S169002 |  | 0 | 0 |  | 9 | 4 | 4 | 1 | S169S169002-10 | NA |  |  | 0
T42 only | S169S169002-10 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | S169S169002-20 | NA |  |  | 0
OKUMA/Harding | S169S169003 | New | 0 | 0 |  | 22 | 4 | 4 | 1 | S169S169003-20 | NA |  |  | 0
Drill Press Bridgeport | S169S169003 |  | 0 | 0 |  | 9 | 4 | 4 | 1 | S169S169003-10 | NA |  |  | 0
Okuma-Cadet | S20S20001 (A) |  | 0 | 0 |  | 4 | 4 | 4 | 1 | S20S20001-10 | 4.3186 |  |  | 0
Okuma-Cadet | S20S20001 (B) |  | 0 | 0 |  | 15 | 2 | 2 | 0 | S20S20001 (A) | NA |  |  | 0
Okuma-Cadet | S20S20001-10 | SEE MIKE | 0 | 0 |  | 40 | 4 | 4 | 1 | S20S20001-20 | NA |  |  | 0
T-42 | S20S20002 (A) |  | 0 | 0 |  | 7 | 4 | 4 | 1 | S20S20002-10 | NA |  |  | 0
Cobra | S20S20002 (B) |  | 0 | 0 |  | 3 | 4 | 4 | 1 | S20S20002 (A) | NA |  |  | 0
Okuma-Cadet | S20S20002-10 |  | 0 | 0 |  | 46 | 4 | 4 | 1 | S20S20002-20 | NA |  |  | 0
Okuma-Cadet | S20S20002-20 |  | 0 | 0 |  | 108 | 16 | 16 | 2 | A02002-0068 | 2.244 |  | 172.88 | 0 | 0
Bridgeport Drill Press | S20S20003 |  | 0 | 0 |  | 18 | 2 | 2 | 0 | S20S20003-10 | NA |  |  | 0
T-42 | S20S20003 (A) |  | 0 | 0 |  | 9 | 4 | 4 | 1 | A02001-0060 | 1.76 |  | 122.07 | 0 | 0
Cobra | S20S20003 (B) |  | 0 | 0 |  | 11 | 4 | 4 | 1 | S20S20003 (A) | 1.76 |  |  | 0
Cobra | SB2201 (2/3) | STND | 0 | 0 |  | 27 | 2 | 2 | 0 | SB2201 (1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | SB2201 (3/3) | STND | 0 | 0 |  | 15 | 2 | 2 | 0 | SB2201 (2/3) | NA |  |  | 0
Cobra | SB2201 (2/5) | non stnd | 0 | 0 |  | 27 | 2 | 2 | 0 | SB2201 (1/3) | NA |  |  | 0
Chamfer-10 Lathe | SB2201 (3/5) | non stnd | 0 | 0 |  | 120 | 2 | 2 | 0 | SB2201 (2/3) | NA |  |  | 0
4 Way | SB2201 (4/5) | non stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SB2201 (3/5) | NA |  |  | 0
4 Way | SB2201 (5/5) | non stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SB2201 (4/5) | NA |  |  | 0
Haas Vertical Mill VF3 | SB5001 (2/2) | STND | 0 | 0 |  | 15 | 2 | 2 | 0 | SB5001 (1/2) | NA |  |  | 0
Chamfer-10 Lathe | SB5001 (2/4) | non stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SB5001 (1/2) | NA |  |  | 0
4 Way | SB5001 (3/4) | non stnd | 0 | 0 |  | 120 | 0.75 | 0.75 | 0 | SB5001 (2/4) | NA |  |  | 0
4 Way | SB5001 (4/4) | non stnd | 0 | 0 |  | 120 | 0.75 | 0.75 | 0 | SB5001 (3/4) | NA |  |  | 0
4 Way 2X's | SB5050 |  | 0 | 0 |  | 80 | 2 | 2 | 0 | SB5050-10 | NA |  |  | 0
Chamfer-10 Lathe | SB5050-10 |  | 0 | 0 |  | 80 | 2 | 2 | 0 | SB5050-20 | NA |  |  | 0
Haas Vertical Mill VF3 | SB7501 (2/2) | STND | 0 | 0 |  | 15 | 2 | 2 | 0 | SB7501 (1/2) | NA |  |  | 0
Chamfer-10 Lathe | SB7501 (2/4) | non stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SB7501 (1/2) | NA |  |  | 0
4 Way | SB7501 (3/4) | non stnd | 0 | 0 |  | 120 | 0.75 | 0.75 | 0 | SB7501 (2/4) | NA |  |  | 0
4 Way | SB7501 (4/4) | non stnd | 0 | 0 |  | 120 | 0.75 | 0.75 | 0 | SB7501 (3/4) | NA |  |  | 0
Auto Mill | SB7515(2/2) |  | 0 | 0 |  | 52 | 0.5 | 0.5 | 0 | SB7515(1/2) | NA |  |  | 0
Haas Vertical Mill VF3 | SB7550 (2/2) | STND | 0 | 0 |  | 64 | 2 | 2 | 0 | SB7550 (1/2) | NA |  |  | 0
4 Way 2X's | SB7550 |  | 0 | 0 |  | 5 | 2 | 2 | 0 | SB7550-10 | NA |  |  | 0
Chamfer-10 Lathe | SB7550-10 |  | 0 | 0 |  | 80 | 2 | 2 | 0 | SB7550-20 | NA |  |  | 0
Okuma-Cadet | SB7550-20 |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | A02042-0034 | 0.9831 | 0.3217 | 43.22 | 0 | 0
Okuma-Cadet | SB7551 (1/3) | new part | 0 | 0 | 0 | 6 | 0 | 0 | 0 | A02042-0034 | 0.9831 | 0.3217 | 43.22 | 0 | 0
Cobra | SB7551 (2/3) | new part | 0 | 0 |  | 30 | 2 | 2 | 0 | SB7551 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | SB7551 (3/3) | new part | 0 | 0 |  | 5 | 2 | 2 | 0 | SB7551 (2/3) | NA |  |  | 0
Okuma-Cadet | SCB5001 |  | 0 | 0 |  | 3 | 6 | 6 | 1 | A02042-0046 | 1.0988 |  | 79.11 | 0 | 0
Okuma-Cadet | SCB5002 |  | 0 | 0 |  | 3 | 6 | 6 | 1 | A01102-0046 | 0.9704 |  | 73.01 | 0 | 0
Okuma-Cadet | SCB5050 |  | 0 | 0 |  | 6 | 4 | 4 | 1 | A02042-0046 | 1.0988 |  | 79.11 | 0 | 0
Okuma-Cadet | SCB7501 |  | 0 | 0 | 0 | 6 | 4 | 4 | 1 | A02042-0046 | 1.224 | 0.321 | 79.11 | 0 | 0
Okuma-Cadet | SCB7550 |  | 0 | 0 |  | 5 | 4 | 4 | 1 | A02042-0046 | 1.224 |  | 79.11 | 0 | 0
Chamfer-10 Lathe | SF1601-10(A) | non-stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SF1601-10 | NA |  |  | 0
Cobra | SF1601(A) | non-stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | A02042-0028 | 0.5229 |  | 29.31 | 0 | 0
Cobra | SF1601(B) | non-stnd | 0 | 0 |  | 94 | 3 | 3 | 0 | SF1601(A) | NA |  |  | 0
4 Way | SF1601 ( C ) | non-stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SF1601(B) | NA |  |  | 0
4 Way | SF1601(D) | non-stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SF1601 ( C ) | NA |  |  | 0
Citizen | SF3-2.5-2 |  | 0 | 0 |  | 31 | 1 | 1 | 0 | A02071-0028 | 0.286 |  | 26.58 | 0 | 0
Citizen | SF3-2.5-4 |  | 0 | 0 |  | 31 | 1 | 1 | 0 | A02071-0028 | 0.282 |  | 26.58 | 0 | 0
Citizen | SF3-3-3 |  | 0 | 0 |  | 31 | 1 | 1 | 0 | A02071-0028 | 0.326 |  | 26.58 | 0 | 0
H1 | SF401-A-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0026 | 0.223 | 0.07 | 22.95 | 0 | 0
Citizen | SF403-2-3/16 |  | 0 | 0 | 0 | 62 | 1 | 1 | 0 | A02071-0028 | 0.2814 | 0.085 | 26.58 | 0 | 0
Hass Vertical Mill VF3 | SF403-3-1/4 |  | 0 | 0 | 0 | 15 | 0 | 0 | 0 | SF403-A-BLNK | NA | 0.085 |  | 0
Citizen | SF403-3-3/16 |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0028 | 0.2814 | 0.092 | 26.58 | 0 | 0
Citizen | SF403-4-3/16 |  | 0 | 0 | 0 | 50 | 1 | 1 | 0 | A02071-0028 | 0.2184 | 0.092 | 26.58 | 0 | 0
Citizen | SF403-6-3/16 |  | 0 | 0 | 0 | 29 | 1 | 1 | 0 | A02071-0028 | 0.2184 | 0.085 | 26.58 | 0 | 0
H1 or Citizen | SF403-A-BLNK |  | 0 | 0 | 0 | 54 | 2 | 2 | 0 | A02071-0028 | 0.2769 | 0.092 | 26.58 | 0 | 0
Okuma-Genos | SF404-5-1/4 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.4788 | 0.1873 | 39.2 | 0 | 0
Okuma-Genos | SF404-8-3/16 |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0034 | 0.467 | 0.1873 | 39.2 | 0 | 0
Hass Vertical Mill VF3 | SF404-9-3/16 |  | 0 | 0 | 0 | 14 | 0 | 0 | 0 | SF404-A-BLNK | NA | 0.1873 |  | 0
H1 | SF404-A-BLNK |  | 0 | 0 | 0 | 27 | 3 | 3 | 0 | A02071-0034 | 0.5094 | 0.1873 | 39.2 | 0 | 0
Citizen | SF405-A-BLNK | NonStnd | 0 | 0 |  | 27 | 4 | 4 | 1 | A02071-0028 | 0.414 |  | 26.58 | 0 | 0
H1 | SF405-A-BLNK | Stnd | 0 | 0 |  | 27 | 4 | 4 | 1 | A02071-0028 | 0.414 |  | 26.58 | 0 | 0
H1 | SF4-2.5-F-BLNK |  | 0 | 0 |  | 49 | 1 | 1 | 0 | A02071-0028 | 0.289 |  | 26.58 | 0 | 0
Citizen | SF4-3-A-BLNK | Run min Quanties | 0 | 0 | 0 | 67 | 1 | 1 | 0 | A02071-0020 | 0.113 | 0.0377 | 13.56 | 0 | 0 | Family 2
Citizen | SF4-3-2 | Run min Quanties | 0 | 0 | 0 | 67 | 1 | 1 | 0 | A02071-0020 | 0.1003 | 0.0377 | 13.56 | 0 | 0 | Family 2
Citizen | SF4-3-3 | Run min Quanties | 0 | 0 |  | 64 | 1 | 1 | 0 | A02071-0020 | 0.091 |  | 13.56 | 0 | 0 | Family 2
Citizen | SF4-3-4 | Run min Quanties | 0 | 0 |  | 24 | 1 | 1 | 0 | A02071-0026 | 0.854 |  | 22.95 | 0 | 0 | Family 2
Citizen | SF4-3-4 | Run min Quanties | 0 | 0 |  | 50 | 4 | 4 | 1 | A02071-0026 | 0.222 |  | 22.95 | 0 | 0
Citizen | SF4-3-6 | Run min Quanties | 0 | 0 |  | 30 | 1 | 1 | 0 | A02071-0026 | 0.225 |  | 22.95 | 0 | 0 | Family 2
Citizen | SF4-3-8 | Run min Quanties | 0 | 0 |  | 37 | 1 | 1 | 0 | A02071-0028 | 0.192 |  | 26.58 | 0 | 0 | Family 2
H1 | SF4-3-B-BLNK |  | 0 | 0 |  | 49 | 1 | 1 | 0 | A02071-0026 | 0.223 |  | 22.95 | 0 | 0
H1 | SF4-3-D-BLNK |  | 0 | 0 |  | 56 | 1 | 1 | 0 | A02071-0032 | 0.436 |  | 34.72 | 0 | 0
Citizen | SF4-4-2 | Run min Quanties | 0 | 0 |  | 64 | 2 | 2 | 0 | A02071-0026 | 0.1921 |  | 22.95 | 0 | 0
Citizen | SF4-4-3 | Run min Quanties | 0 | 0 |  | 58 | 0.5 | 0.5 | 0 | A02071-0026 | 0.1921 |  | 22.95 | 0 | 0
Citizen | SF4-4-4 | Run min Quanties | 0 | 0 |  | 50 | 4 | 4 | 1 | A02071-0026 | 0.1921 |  | 22.95 | 0 | 0
Okuma-Genos | SF4-4-5 |  | 0 | 0 |  | 14 | 2 | 2 | 0 | A02071-0034 | 0.482 |  | 39.2 | 0 | 0
H1 | SF4-4-B-BLNK |  | 0 | 0 |  | 42 | 1 | 1 | 0 | A02071-0034 | 0.482 |  | 39.2 | 0 | 0
Citizen 3 | SF5-3-3 |  | 0 | 0 | 0 | 50 | 4 | 4 | 1 | A02071-0020 | 0.1006 | 0.058 | 13.56 | 0 | 0
Citizen | SF5-3-8 |  | 0 | 0 | 0 | 50 | 4 | 4 | 1 | A02071-0028 | 0.34 | 0.09 | 26.58 | 0 | 0
4 Way 2X's | SF5001 |  | 0 | 0 |  | 80 | 2 | 2 | 0 | SF5001-10 | NA |  |  | 0
Chamfer-10 Lathe | SF5001-10 |  | 0 | 0 |  | 80 | 2 | 2 | 0 | SF5001-20 | NA |  |  | 0
4 Way 2X's | SF5002 |  | 0 | 0 |  | 102 | 2 | 2 | 0 | SF5002-10 | NA |  |  | 0
Chamfer-10 Lathe | SF5002-10 |  | 0 | 0 |  | 120 | 24 | 24 | 3 | SF5002-20 | NA |  |  | 0
Cobra | SF5005 | Non Stnd-B/U for Davenport | 0 | 0 |  | 45 | 16 | 16 | 2 | A02001-0022 | 0.0498 |  | 16.41 | 0 | 0
H1 | SF504-A-BLNK |  | 0 | 0 | 0 | 49 | 1 | 1 | 0 | A02071-0040 | 0.849 | 0.476 | 54.25 | 0 | 0
Cobra | SF5051 (2/3) |  | 0 | 0 |  | 94 | 3 | 3 | 0 | SF5051 (1/3) | NA |  |  | 0
Hass Vertical Mill VF3 | SF5051 (3/3) |  | 0 | 0 |  | 94 | 3 | 3 | 0 | SF5051 (2/3) | NA |  |  | 0
H1 | SF505-A-BLNK |  | 0 | 0 |  | 49 | 1 | 1 | 0 | A02071-0052 | 1.779 |  | 91.68 | 0 | 0
H1 | SF506-A-BLNK |  | 0 | 0 | 0 | 38 | 2 | 2 | 0 | A02071-0040 | 0.8539 | 0.336 | 54.25 | 0 | 0
Okuma-Genos | SF507-13-3/16 |  | 0 | 0 |  | 14 | 2 | 2 | 0 | A02071-0052 | 1.381 |  | 91.68 | 0 | 0
H1 | SF507-A-BLNK |  | 0 | 0 | 0 | 29 | 1 | 1 | 0 | A02071-0052 | 1.4659 | 0.4395 | 91.68 | 0 | 0
Okuma-Genos | SF5-2.5-15 |  | 0 | 0 |  | 14 | 2 | 2 | 0 | A02071-0040 | 0.6114 |  | 54.25 | 0 | 0
H1 | SF5-2.5-E-BLNK |  | 0 | 0 |  | 49 | 1 | 1 | 0 | A02071-0040 | 0.591 |  | 54.25 | 0 | 0
H1 | SF5-2.5-E-BLNK |  | 0 | 0 |  | 49 | 1 | 1 | 0 | A02071-0040 | 0.591 |  | 54.25 | 0 | 0
Haas Vertical Mill VF3 | SF521-3-1/4 |  | 0 | 0 |  | 16 | 1 | 1 | 0 | SF521-A-BLNK | NA |  |  | 0
Haas Vertical Mill VF3 | SF521-4-3/16 |  | 0 | 0 |  | 15 | 4 | 4 | 1 | SF521-A-BLNK | NA |  |  | 0
Haas Vertical Mill VF3 | SF521-3-3/16 |  | 0 | 0 |  | 12 | 1 | 1 | 0 | SF521-A-BLNK | NA |  |  | 0
Haas Vertical Mill VF3 | SF521-5-1/4 |  | 0 | 0 | 0 | 12 | 1 | 1 | 0 | SF521-A-BLNK | NA |  |  | 0
Haas Vertical Mill VF3 | SF521-6-1/4 |  | 0 | 0 | 0 | 10 | 1 | 1 | 0 | SF521-A-BLNK | NA |  |  | 0
M1 or Citizen | SF521-A-BLNK |  | 0 | 0 | 0 | 35 | 2 | 2 | 0 | A02071-0032 | 0.3431 | 0.1231 | 34.72 | 0 | 0
H1 | SF5-3-B-BLNK |  | 0 | 0 |  | 50 | 1 | 1 | 0 | A02071-0026 | 0.227 |  | 22.95 | 0 | 0
H1 | SF704-A-BLNK |  | 0 | 0 | 0 | 35 | 1 | 1 | 0 | A02071-0064 | 2.354 | 0.7525 | 138.88 | 0 | 0
Okuma-Genos | SF7-2.5-22 |  | 0 | 0 |  | 14 | 2 | 2 | 0 | A02071-0056 | 1.582 |  | 106.33 | 0 | 0
Haas Vertical Mill VF4 | SF7-2.5-30 |  | 0 | 0 | 0 | 4 | 1 | 1 | 0 | SF7-2.5-F-BLNK | NA | 1.286 |  | 0
H1 | SF7-2.5-E-BLNK |  | 0 | 0 |  | 31 | 1 | 1 | 0 | A02071-0056 | 1.582 |  | 106.33 | 0 | 0
H4 or M1 | SF7-2.5-F-BLNK |  | 0 | 0 | 0 | 14 | 2 | 2 | 0 | A02071-0076 | 4.2739 | 1.286 | 195.85 | 0 | 0
Haas CNC Mill VF3 or VF4 | SF9-2.5-34 |  | 0 | 0 | 0 | 4 | 1 | 1 | 0 | SF9-2.5-B-BLNK | NA | 1.91 |  | 0
H4 | SF9-2.5-B-BLNK | Kanban | 0 | 0 | 0 | 18 | 3 | 3 | 0 | A02071-0096 | 8.1782 | 2.11 | 312.49 | 0 | 0
H1 | SF9-2.5-C-BLNK |  | 0 | 0 | 0 | 18 | 3 | 3 | 0 | A02071-0056 | 1.5742 | 54 | 106.33 | 0 | 0 |  |  |  |  | 2018
4 Way X's 2(472/473) | SN5001 |  | 0 | 0 |  | 102 | 0.5 | 0.5 | 0 | SN5001-10 | NA |  |  | 0
Chamfer-10 Lathe | SN5001-10 |  | 0 | 0 |  | 120 | 2 | 2 | 0 | SN5001-20 | NA |  |  | 0
Drill Press | SP2506 | Backup Only | 0 | 0 |  | 120 | 0.25 | 0.25 | 0 | SP2501 | NA |  |  | 0
Drill Press | SP5066 | Backup Only | 0 | 0 |  | 120 | 1 | 1 | 0 | SP5055 | NA |  |  | 0
T42 | SP5062 (1/2) | Non-Stnd | 0 | 0 | 0 | 15 | 16 | 16 | 2 | A02032-0030 | 0.3284 | 0.1478 | 33.65 | 0 | 0
T42 | SP5062 (2/2) | Non-Stnd | 0 | 0 |  | 15 | 16 | 16 | 2 | SP5062 (1/2) | NA |  |  | 0
4 Way #473 | SR2501 |  | 0 | 0 |  | 180 | 40 | 40 | 5 | SR2501-10 | NA |  |  | 0
H4 | SS1103-14-1/4 (1/2) |  | 0 | 0 |  | 5 | 8 | 8 | 1 | A06501-0096 | 6.967 | 1.772 | 288.4 | 0 | 0
Haas Vertical Mill VF4 | SS1103-14-1/4 (2/2) |  | 0 | 0 |  | 5 | 8 | 8 | 1 | SS1103-14-1/4 (1/2) | NA |  |  | 0
H4 | SS1103-16-1/4 (1/2) |  | 0 | 0 |  | 5 | 8 | 8 | 1 | A06501-0096 | 6.967 | 1.772 | 288.4 | 0 | 0
Haas Vertical Mill VF4 | SS1103-16-1/4 (2/2) |  | 0 | 0 |  | 5 | 8 | 8 | 1 | SS1103-16-1/4 (1/2) | NA |  |  | 0
Haas Vertical Mill VF4 | SS1301-16-14(B) |  | 0 | 0 |  | 5 | 1 | 1 | 0 | SS1301-16-1/4(A) | NA |  |  | 0
Haas Vertical Mill VF4 | SS1304-36-1/4(B) |  | 0 | 0 |  | 5 | 2.5 | 2.5 | 0 | SS1304-36-1/4(A) | NA |  |  | 0
H4 | SS1304-36-1/4(A) |  | 0 | 0 |  | 1 | 1 | 1 | 0 | A06501-0128 | 14.328 |  | 512.8 | 0 | 0
Haas Vertical Mill VF4 | SS902-12-1/4 |  | 0 | 0 |  | 2 | 2 | 2 | 0 | SS902-A-BLNK | NA |  |  | 0
Ganesh CNC | SW1001 |  | 0 | 0 |  | 36 | 8 | 8 | 1 | A02042-0052 | 2.6153 |  | 101.1 | 0 | 0 | 2016
Haas Vertical Mill VF3 | SW1001 (2/2) | Stnd | 0 | 0 |  | 15 | 4 | 4 | 1 | SW1001 (1/2) | NA
4 Way | SW1001(4/4) | Non-Stnd | 0 | 0 |  | 94 | 0.75 | 0.75 | 0 | SW1001(3/4) | NA |  |  | 0
4 Way | SW1001(3/4) | Non-Stnd | 0 | 0 |  | 94 | 0.75 | 0.75 | 0 | SW1001(2/4) | NA |  |  | 0
Chamfer-10 Lathe | SW1001(2/4) | Non-Stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SW1001(1/4) | NA |  |  | 0
Drill Press | SW1009(2/2) |  | 0 | 0 |  | 150 | 0.25 | 0.25 | 0 | SW1009(1/2) | NA |  |  | 0
Auto Mill | SW1015 (2/2) |  | 0 | 0 |  | 68 | 0.25 | 0.25 | 0 | SW1015 (1/2) | NA |  |  | 0
4 Way | SW1050(4/4) | Non-Stnd | 0 | 0 |  | 94 | 0.75 | 0.75 | 0 | SW1050(3/4) | NA |  |  | 0
4 Way | SW1050(3/4) | Non-Stnd | 0 | 0 |  | 94 | 0.75 | 0.75 | 0 | SW1050(2/4) | NA |  |  | 0
Chamfer-10 Lathe | SW1050(2/4) | Non-Stnd | 0 | 0 |  | 80 | 2 | 2 | 0 | SW1050(1/4) | NA |  |  | 0
Haas Vertical Mill VF3 | SW1201 (2/2) | Stnd | 0 | 0 |  | 15 | 4 | 4 | 1 | SW1201 (1/2) | NA
Ganesh CNC | SW1201 |  | 0 | 0 |  | 36 | 8 | 8 | 1 | A02091-0056 | 2.656 |  | 106.33 | 0 | 0 | 2016
MS2 | SW1201 |  | 0 | 0 |  | 94 | 0.6 | 0.6 | 0 | SW1201-10 | NA |  |  | 0
Chamfer-10 Lathe | SW1201-10 |  | 0 | 0 |  | 16 | 1 | 1 | 0 | SW1201-20 | NA |  |  | 0
Okuma-Cadet | SW1250 (1/3) |  | 0 | 0 | 0 | 5 | 4 | 4 | 1 | A02042-0056 | 2.6513 | 0.912 | 117.25 | 0 | 0
Cobra | SW1250 (2/3) |  | 0 | 0 |  | 36 | 8 | 8 | 1 | SW1250 (1/3) | NA
Haas Vertical Mill VF3 | SW1250 (3/3) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | SW1250 (2/3) | NA
Haas Vertical Mill VF3 | SW3301 (2/2) | Stnd | 0 | 0 |  | 15 | 4 | 4 | 1 | SW3301 (1/2) | NA
Ganesh CNC | SW3301 |  | 0 | 0 |  | 12 | 48 | 48 | 6 | A02042-0052 | 2.656 |  | 101.1 | 0 | 0 | 2016
4Way | SW3301 |  | 0 | 0 |  | 94 | 0.75 | 0.75 | 0 | SW3301-10 | NA |  |  | 0
Chamfer-10 Lathe | SW3301-10 |  | 0 | 0 |  | 100 | 1 | 1 | 0 | SW3301-20 | NA |  |  | 0
Citizen | T4-4-2 |  | 0 | 0 |  | 65 | 1 | 1 | 0 | A02071-0028 | 0.225 |  | 26.58 | 0 | 0
B&S17 | TC0202 |  | 0 | 0 |  | 133 | 4 | 4 | 1 | TC0202-10 | 1 |  |  | 0
B&S17 | TC0207 |  | 0 | 0 |  | 100 | 4 | 4 | 1 | TC0207-10 | NA |  |  | 0
B&S17 | TC0216 |  | 0 | 0 |  | 385 | 24 | 24 | 3 | TC0216-10 | NA |  |  | 0
B&S17 | TC0217 |  | 0 | 0 | 0 | 288 | 2 | 2 | 0 | TC0211 | NA | 0.03218 |  | 0
B&S17 | TC1280 | NON STND | 0 | 0 |  | 102 | 4 | 4 | 1 | TC1280-10 | NA |  |  | 0
B&S17 | TC1284 | NON STND | 0 | 0 |  | 64 | 4 | 4 | 1 | TC1284-10 | NA |  |  | 0
B/S #3 Ultra Only | TC6301(2/2) |  | 0 | 0 |  | 120 | 4 | 4 | 1 | TC6301(1/2) | NA |  |  | 0
Okuma-Cadet | V1000004 |  | 0 | 0 | 0 | 30 | 2 | 2 | 0 | A02002-0056 | 0.8811 | 0.262 | 117.25 | 0 | 0
Kingbury | VC10071 | Hydromat | 0 | 0 |  | 52 | 3 | 3 | 0 | VC10071-10 | NA |  |  | 0
B&S17 | VC10071-10 | Hydromat | 0 | 0 |  | 99 | 6 | 6 | 1 | VC10071-20 | NA |  |  | 0
Okuma-Cadet | VF7501 |  | 0 | 0 |  | 11 | 3 | 3 | 0 | A02002-0038 | 1.0289 |  | 54.03 | 0 | 0
T42 | VF7502 |  | 0 | 0 |  | 10 | 3 | 3 | 0 | A02001-0032 | 0.2242 |  | 34.72 | 0 | 0
T42 | VF7502-1 |  | 0 | 0 |  | 10 | 3 | 3 | 0 | A02001-0032 | 0.2242 |  | 34.72 | 0 | 0
Okuma-Cadet | VR1001 |  | 0 | 0 | 0 | 6 | 3 | 3 | 0 | A02002-0052 | 2.2679 | 0.647 | 101.1 | 0 | 0
Okuma-Cadet | VR1002 |  | 0 | 0 | 0 | 8 | 3.5 | 3.5 | 0 | A02001-0048 | 1.6384 | 0.645 | 78.12 | 0 | 0
Okuma-Cadet | VR7501 |  | 0 | 0 |  | 12 | 4 | 4 | 1 | A02002-0034 | 0.5868 |  | 43.22 | 0 | 0
T42 | VRG02503 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | A02001-0010 | 0.339 |  | 3.39 | 0 | 0
Haas Vertical Mill VF4 | VRG05001 ( C ) |  | 0 | 0 |  | 32 | 3 | 3 | 0 | VRG05001(B) | NA |  |  | 0
Okuma Cadet | VRG05001(A) |  | 0 | 0 |  | 13 | 4 | 4 | 1 | A02002-0036 | 0.5813 |  | 48.45 | 0 | 0
Cobra | VRG05001(B) |  | 0 | 0 |  | 13 | 2 | 2 | 0 | VRG05001(A) | NA |  |  | 0
Miyano CNC Bar | VRG05003 |  | 0 | 0 |  | 6 | 4 | 4 | 1 | A02001-0016 | 0.1743 |  | 8.68 | 0 | 0
Miyano CNC Bar | VRG05006 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | A02001-0032 | 0.485 |  | 34.72 | 0 | 0
Haas Vertical Mill VF4 | VRG07501 |  | 0 | 0 |  | 32 | 3 | 3 | 0 | VRG07501(B) | NA |  |  | 0
Miyano CNC Bar | VRG07501(A) |  | 0 | 0 |  | 13 | 4 | 4 | 1 | A02002-0036 | 0.5688 |  | 48.45 | 0 | 0
Miyano CNC Bar | VRG07501(B) |  | 0 | 0 |  | 13 | 2 | 2 | 0 | VRG07501(A) | NA |  |  | 0
Okuma-Cadet | VRG10001 (1/3) | STND | 0 | 0 | 0 | 60 | 3 | 3 | 0 | A02002-0044 | 1.1587 | 0.387 | 72.38 | 0 | 0
Cobra | VRG10001 (2/3) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRG10001 (1/3) | NA |  |  | 0
Haas Vertical Mill VF4 | VRG10001 (3/3) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRG10001 (2/3) | NA |  |  | 0
B&S 18 | VRG10002(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0008 | 0.0536 |  | 2.17 | 0 | 0
B&S 18 | VRG10002(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | VRG10002(A) | NA |  |  | 0
Miyano CNC Bar | VRG10005 |  | 0 | 0 |  | 53 | 3 | 3 | 0 | A02001-0024 | 0.0404 |  | 19.53 | 0 | 0
M1 | VRG10006 | STND | 0 | 0 | 0 | 23 | 3 | 3 | 0 | A02001-0032 | 0.7325 | 0.234 | 34.72 | 0 | 0
H3 | VRG10010 |  | 0 | 0 |  | 9 | 3 | 3 | 0 | A02001-0032 | 0.7275 |  | 34.72 | 0 | 0
Haas Vertical Mill VF4 | VRG12501( C ) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRG02501(B) | NA |  |  | 0
Okuma-Cadet | VRG12501(A) |  | 0 | 0 |  | 60 | 3 | 3 | 0 | A02002-0056 | 1.9215 |  | 117.25 | 0 | 0
Cobra | VRG12501(B) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRG02501(A) | NA |  |  | 0
Hass H3 | VRG12505 |  | 0 | 0 |  | 51 | 1.5 | 1.5 | 0 | A02001-0032 | 0.0693 |  | 34.72 | 0 | 0
Miyano Bar Or Haas H3 | VRG12508 |  | 0 | 0 |  | 54 | 1.5 | 1.5 | 0 | A02001-0024 | 0.298 |  | 19.53 | 0 | 0
B&S 18 | VRG15002 |  | 0 | 0 |  | 288 | 0.5 | 0.5 | 0 | A02001-0010 | 0.0942 |  | 3.39 | 0 | 0
Miyano CNC Bar | VRG15005 |  | 0 | 0 |  | 60 | 3 | 3 | 0 | A02001-0040 | 0.1234 |  | 54.25 | 0 | 0
Okuma-Cadet | VRG20001(1/3) |  | 0 | 0 | 0 | 60 | 3 | 3 | 0 | A02002-0080 | 4.819 |  | 239.3 | 0 | 0
Okuma Cadet | VRG20001(2/3) |  | 0 | 0 |  | 60 | 3 | 3 | 0 | VRG20001(1/3) | NA |  |  | 0
Haas Vertical Mill VF4 | VRG20001(3/3) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRG20001(2/3) | NA |  |  | 0
H3 | VRG10008 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | A02001-0024 | 0.0295 |  | 19.53 | 0 | 0
B&S 18 | VRG20002 (1/2) |  | 0 | 0 |  | 34 | 4.5 | 4.5 | 1 | A02001-0010 | 0.1028 |  | 3.39 | 0 | 0
B&S 17 | VRG20002 (2/2) |  | 0 | 0 |  | 288 | 0.5 | 0.5 | 0 | VRG20002 (1/2) | NA |  |  | 0
Okuma-Cadet | VRG20003 |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0044 | 0.161 |  | 65.64 | 0 | 0
H4 | VRG30001 (1/3) |  | 0 | 0 | 0 | 15 | 3 | 3 | 0 | A02001-0112 | 11.0338 | 4.07 | 425.33 | 0 | 0
H4 | VRG30001 (2/3) |  | 0 | 0 |  | 15 | 2 | 2 | 0 | VRG30001 (1/3) | NA |  |  | 0
Haas Vertical Mill VF4 | VRG30001 (3/3) |  | 0 | 0 |  | 15 | 2 | 2 | 0 | VRG30001 (2/3) | NA |  |  | 0
B&S 18 | VRG30002(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A02001-0012 | 0.1705 |  | 4.88 | 0 | 0
B&S 18 | VRG30002(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | VRG30002(A) | NA |  |  | 0
H4 | VRG30003 |  | 0 | 0 |  | 60 | 3 | 3 | 0 | A02001-0068 | 0.5794 |  | 156.79 | 0 | 0
H1 | VRG30005 |  | 0 | 0 |  | 10 | 3 | 3 | 0 | A02001-0072 | 0.456 |  | 175.8 | 0 | 0
H3 | VRG30006 |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | A02001-0044 | 1.6547 | 0.55 | 65.64 | 0 | 0
T42 | VRGSS02501 (1/2) |  | 0 | 0 | 0 | 16 | 3 | 3 | 0 | A06202-0020 | 0.1017 | 0.037 | 13.8 | 0 | 0
T42 | VRGSS02501 (2/2) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS02501 (1/2) | NA |  |  | 0
T42 | VRGSS02503 |  | 0 | 0 | 0 | 30 | 3 | 3 | 0 | A06201-0010 | 0.0319 | 0.007 | 3.23 | 0 | 0
Cobra | VRGSS02506 | NON STND | 0 | 0 |  | 13 | 4 | 4 | 1 | A06201-0020 | 0.1012 |  | 12.9 | 0 | 0
Haas H3 | VRGSS02506 | STND | 0 | 0 |  | 13 | 4 | 4 | 1 | A06201-0020 | 0.1101 |  | 12.9 | 0 | 0
Haas Vertical Mill VF4 | VRGSS05001 ( C ) |  | 0 | 0 |  | 32 | 3 | 3 | 0 | VRGSS05001(B) | NA |  |  | 0
Okuma Cadet | VRGSS05001(A) |  | 0 | 0 |  | 13 | 4 | 4 | 1 | A06202-0036 | 0.3239 |  | 44.72 | 0 | 0
Cobra | VRGSS05001(B) |  | 0 | 0 |  | 13 | 2 | 2 | 0 | VRGSS05001(A) | NA |  |  | 0
Miyano CNC Bar | VRGSS05003 |  | 0 | 0 |  | 2 | 2 | 2 | 0 | A06201-0016 | 0.1641 |  | 8.26 | 0 | 0
Miyano CNC Bar | VRGSS05005 |  | 0 | 0 |  | 3 | 2 | 2 | 0 | A06201-0016 | 0.1641 |  | 8.26 | 0 | 0
Miyano CNC Bar | VRGSS05006 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | A06201-0032 | 0.4566 |  | 32.04 | 0 | 0
H3 | VRGSS05008 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | A06201-0018 | 0.0026 |  | 10.14 | 0 | 0
Haas Vertical Mill VF4 | VRGSS10001 (C) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS10001(B) | NA |  |  | 0
Okuma-Cadet | VRGSS10001(A) |  | 0 | 0 |  | 60 | 3 | 3 | 0 | A06202-0044 | 1.0962 |  | 66.8 | 0 | 0
Okuma-Cadet | VRGSS10001(B) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS10001(A) | NA |  |  | 0
M1 | VRGSS10006 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | A06201-0032 | 0.7276 |  | 32.04 | 0 | 0
Miyano CNC Bar | VRGSS10008 |  | 0 | 0 |  | 30 | 3 | 3 | 0 | A06201-0024 | 0.0277 |  | 18.58 | 0 | 0
Okuma-Cadet | VRGSS12501 (1/3) |  | 0 | 0 | 0 | 60 | 3 | 3 | 0 | A06202-0056 | 1.8283 | 0.579 | 108.5 | 0 | 0
T42 | VRGSS12501 (2/3) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS12501 (1/3) | NA |  |  | 0
Haas Vertical Mill VF3 | VRGSS12501 (3/3) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS12501 (2/3) | NA |  |  | 0
B&S 18 | VRGSS12502 |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A06201-0010 | 0.0767 |  | 3.23 | 0 | 0
Miyano Bar 0r H3 | VRGSS12505 |  | 0 | 0 |  | 26 | 2.5 | 2.5 | 0 | A06201-0032 | 0.0652 |  | 32.04 | 0 | 0
Miyano Bar 0r H3 | VRGSS12508 |  | 0 | 0 |  | 16 | 2 | 2 | 0 | A06201-0024 | 0.028 |  | 18.58 | 0 | 0
Okuma-Cadet | VRGSS20001 (1/3) |  | 0 | 0 | 0 | 16 | 3 | 3 | 0 | A06202-0080 | 4.6177 | 1.663 | 165 | 0 | 0
Okuma-Cadet | VRGSS20001 (2/3) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS20001 (1/3) | NA |  |  | 0
Haas Vertical Mill VF4 | VRGSS20001 (3/3) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS20001 (2/3) | NA |  |  | 0
Miyano Bar 0r H3 | VRGSS20003 |  | 0 | 0 |  | 8 | 2.5 | 2.5 | 0 | A06201-0044 | 0.1517 |  | 60.59 | 0 | 0
H4 | VRGSS30001(A) |  | 0 | 0 |  | 60 | 3 | 3 | 0 | A06201-0112 | 11.0338 |  | 392.5 | 0 | 0
H4 | VRGSS30001(B) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS30001(A) | NA |  |  | 0
Haas Vertical Mill VF4 | VRGSS30001(C) |  | 0 | 0 |  | 16 | 2 | 2 | 0 | VRGSS30001(B) | NA |  |  | 0
B&S 18 | VRGSS30002(A) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | A06201-0012 | 0.1579 |  | 4.65 | 0 | 0
B&S 18 | VRGSS30002(B) |  | 0 | 0 |  | 15 | 4 | 4 | 1 | VRGSS30002(A) | NA |  |  | 0
M1 | VRGSS30003 |  | 0 | 0 |  | 60 | 3 | 3 | 0 | A06201-0072 | 0.6181 |  | 162.2 | 0 | 0
M1 | VRGSS30006 |  | 0 | 0 | 0 | 60 | 3 | 3 | 0 | A06201-0044 | 1.5659 | 0.5 | 60.59 | 0 | 0
M1 | VRG30008 |  | 0 | 0 | 0 | 15 | 8 | 8 | 1 | A02001-0032 | 0.0704 | 0.038 | 34.72 | 0 | 0
Okuma-Cadet | WP2508 (1/2) |  | 0 | 0 | 0 | 12 | 4.5 | 4.5 | 1 | A02001-0028 | 0.31198 | 0.1 | 26.58 | 0 | 0
Cobra or B/S | WP2508 (2/2) |  | 0 | 0 |  | 16 | 4 | 4 | 1 | WP2508 (1/2) | NA |  |  | 0
Okuma-Cadet | WP3808 |  | 0 | 0 | 0 | 12 | 4 | 4 | 1 | A02001-0028 | 0.31198 | 0.09 | 26.58 | 0 | 0
H3 | WP5008 | NON STND | 0 | 0 |  | 30 | 16 | 16 | 2 | A02001-0034 | 0.5594 |  | 39.2 | 0 | 0
Formulas:
SCH'D START DATE = WORKDAY([SCH'D START DATE, row above],ROUNDUP([DAYS, row above],0))
Note on K8: Rob Douglas: 9/4 Thyssen Krupp
Note on K9: Rob Douglas: 9/7 Chase
Note on K10: Rob Douglas: 9/12 Chase
Note on K14: Rob Douglas: 6/28 Alro
Note on B22: Rob Douglas: FS135-10 Reference
Note on K23: Rob Douglas: FS135-10 Reference
Note on K41: Rob Douglas: 9/4 Central
Note on K65: Rob Douglas: 8/31
Note on K67: Rob Douglas: EMJ 9/4
Note on K81: Rob Douglas: 7/5 Chase
Note on L86: Chelsea Garrison: WAITING ON BOM TO ROLLL
Note on L88: Chelsea Garrison: WAITING ON FINAL WEIGHT
Note on L89: Chelsea Garrison: MISSING FINAL WEIGHT
Note on L91: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on L92: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on K104: Rob Douglas: Balance of material 8/15 EMJ
Note on K105: Rob Douglas: 8/15 EMJ
Note on K114: Rob Douglas: EMJ 7/3
Note on L116: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on K124: Rob Douglas: 8/1
Note on K126: Rob Douglas: 8/15 Central
Note on K127: Rob Douglas: 654# on hand 7/27
Note on K128: Rob Douglas: 9/7
Note on K129: Rob Douglas: 9/7
Note on K144: Rob Douglas: 9/7
Note on C145: Jessica Moma: New To Replace 606425
Note on C166: Jessica Moma: Issued 8/15/18 for 1,500pcs
Note on L174: Chelsea Garrison: EDIT IF GOING ON GENOS: SCRAP: -0.8892
Note on L175: Amanda Wadley: EDIT BOM IF GOING ON GENOS SCRAP -1.4528
Note on K184: Rob Douglas: 9/7
Note on K210: Rob Douglas: 6/18 Central
Note on C259: Jessica Moma: New To Replace 602595 & 606076
Note on K259: Rob Douglas: Reference NN38B21-10
Note on K261: Rob Douglas: Reference IF5050B24-10
Note on B265: Rob Douglas: AP7501-10 A Operation
Note on C265: Jessica Moma: New W/O To Replace 600276
Note on K265: Rob Douglas: AP7501-10
Note on K308: Rob Douglas: 42412-10
Note on K310: Rob Douglas: 42412-10
Note on K311: Rob Douglas: CY11101-10
Note on K314: Rob Douglas: 42412-10
Note on B348: Rob Douglas: Reference A5012-10
Note on C369: Jessica Moma: New To Replace 606277
Note on K369: Rob Douglas: IL20014-10
Note on K379: Rob Douglas: M40070-10
Note on K506: Rob Douglas: SB7515-10
Note on K563: Rob Douglas: 42412-10
Note on K567: Rob Douglas: 79390-10
Note on L597: Amanda Wadley: IF RUNNING ON OKUMA GENOS SCRAP -.2074
Note on A643: Rob Douglas: Will also run on the VF3
Note on L1083: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on L1084: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on L1125: Chelsea Garrison: EDIT IF GOING ON GENOS: SCRAP: -0.8892
Note on L1138: Chelsea Garrison: EDIT IF GOING ON GENOS: SCRAP: -0.8892
Note on L1151: Chelsea Garrison: EDIT IF GOING ON GENOS SCRAP: -0.5503
Note on L1157: Chelsea Garrison: EDIT IF GOING ON GENOS SCRAP: -.5308
Note on L1167: Chelsea Garrison: EDIT BOM IF GOING ON GENOS: SCRAP:-1.3286
Note on L1179: Chelsea Garrison: WAITING ON BOM TO BE ROLLED
Note on L1207: Chelsea Garrison: Edit if going on Genos Scrap: -1.2069
Note on L1208: Chelsea Garrison: Edit if going on Genos scrap: -1.2179
Note on L1209: Chelsea Garrison: Edit if going on Genos scrap: -1.2609
Note on L1210: Chelsea Garrison: Edit if going on Genos scrap" -1.2329
Note on L1213: Chelsea Garrison: EDIT IF GOING ON GENOS SCRAP: -1.4533
Note on L1215: Chelsea Garrison: Edit if going on Genos: Scrap: -1.4883
Note on L1217: Amanda Wadley: EDIT BOM IF GOING ON GENOS SCRAP -1.4528
Note on L1255: Chelsea Garrison: MISSING FINAL WEIGHT
Note on L1256: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on L1288: Chelsea Garrison: MISSING FINAL WEIGHT
Note on B1299: Rob Douglas: A48010-10 reference
Note on K1300: Rob Douglas: A48010-10 reference
Note on B1305: Rob Douglas: Reference A5012-10
Note on B1312: Rob Douglas: A5128-10 Reference
Note on K1313: Rob Douglas: A5128-10 Reference
Note on B1316: Rob Douglas: Reference A5129-10
Note on K1317: Rob Douglas: Reference A5129-10
Note on K1331: Rob Douglas: AP7501-20
Note on K1332: Rob Douglas: AP7501-10 A Operation
Note on K1333: Rob Douglas: AP7501-10
Note on B1362: Rob Douglas: Reference B3212-1-10
Note on K1363: Rob Douglas: Reference B3212-1-10
Note on L1394: Chelsea Garrison: WAITING ON BOM TO ROLLL
Note on L1398: Chelsea Garrison: WAITING ON FINAL WEIGHT
Note on L1399: Chelsea Garrison: MISSING FINAL WEIGHT
Note on L1400: Chelsea Garrison: MISSING FINAL WEIGHT
Note on L1403: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on L1404: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on L1448: Chelsea Garrison: EDIT IF GOING ON COBRA: SCRAP: -0.4014
Note on B1451: Rob Douglas: Reference C5038B22-10
Note on K1452: Rob Douglas: Reference C5038B22-10
Note on B1453: Rob Douglas: Reference C5038B22
Note on L1478: Amanda Wadley: EDIT BOM IF GOING ON H3 SCRAP -.9868
Note on L1491: Chelsea Garrison: EDIT BOM IF GOING ON COBRA SCRAP: -0.1233
Note on L1492: Chelsea Garrison: EDIT BOM IF GOING ON H2 SCRAP: -0.6331
Note on L1517: Chelsea Garrison: EDIT IF GOING ON COBRA SCRAP: -0.0378
Note on K1520: Rob Douglas: CY11101-10
Note on L1522: Amanda Wadley: edit bom if going on ganesh sc-1015 -.0462
Note on B1523: Rob Douglas: Look at moving to the Ganesh, next Run
Note on L1549: Chelsea Garrison: WAITING ON BOM TO BE ROLLED Amanda Wadley: EDIT BOM IF GOING ON H1 SCRAP -.0277
Note on L1558: Chelsea Garrison: MISSING FINAL WEIGHT
Note on L1559: Chelsea Garrison: MISSING FINAL WEIGHT
Note on L1566: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on B1591: Rob Douglas: Reference F6250B21 -20
Note on K1592: Rob Douglas: Reference F6250B21 -20
Note on B1602: Rob Douglas: FS135-10 Reference
Note on K1603: Rob Douglas: FS135-10 Reference
Note on L1657: Chelsea Garrison: EDIT BOM IS GOING ON MIYANO SCRAP: -1.6385
Note on L1715: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on L1734: Chelsea Garrison: EDIT IF GOING ON H2 SCRAP:-0.0120
Note on L1839: Chelsea Garrison: EDIT BOM IF GOING ON H2 SCRAP -.0068
Note on L1840: Chelsea Garrison: EDIT BOM IF GOING ON H2 SCRAP:-0.0064
Note on L1890: Chelsea Garrison: WAITING ON BOM TO ROLL
Note on K1899: Rob Douglas: Reference IF5050B24-10
Note on K1909: Rob Douglas: IL20014-10
Note on L1912: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1913: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1914: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1915: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1916: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1917: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1918: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1919: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1920: Chelsea Garrison: NEED FINISHED WEIGHT FOR SCRAP
Note on L1968: Chelsea Garrison: EDIT BOM IF GOING ON CITIZEN SCRAP: -0.0100
Note on K1994: Rob Douglas: M40070-10
Note on B2006: Rob Douglas: Reference NN38B21-10
Note on K2006: Rob Douglas: Reference NN38B21-20
Note on K2007: Rob Douglas: Reference NN38B21-10
Note on B2010: Rob Douglas: Reference P1010001-20
Note on B2011: Rob Douglas: Reference P1010001-10
Note on B2043: Rob Douglas: P3850001-20 Reference
Note on B2044: Rob Douglas: P3850001-10 Reference
Note on K2044: Rob Douglas: P3850001-20 Reference
Note on K2045: Rob Douglas: P3850001-10 Reference
Note on K2108: Rob Douglas: Reference PPV10003-10
Note on A2261: Rob Douglas: Live tooling not required
Note on A2262: Rob Douglas: Live tooling not required
Note on B2278: Rob Douglas: S144S144002
Note on K2278: Rob Douglas: S144S144002-10
Note on K2312: Rob Douglas: SB7515-10
Note on C2317: Rob Douglas: Change Routing Eliminate Cobra Only requires Cadet and VF3
Note on B2369: Rob Douglas: Reference SF5051-10
Note on B2410: Rob Douglas: SW1001 B operation
Note on K2410: Rob Douglas: SW1001-10
Note on B2411: Rob Douglas: SW1001 A operation
Note on K2411: Rob Douglas: SW1001-10
Note on B2412: Rob Douglas: SW1001-10
Note on K2412: Rob Douglas: SW1001-20
Note on K2414: Rob Douglas: Reference SW1015-10
Note on B2415: Rob Douglas: SW1050 B operation
Note on K2415: Rob Douglas: SW1050-10
Note on B2416: Rob Douglas: SW1050 A operation
Note on K2416: Rob Douglas: SW1050-10
Note on B2417: Rob Douglas: SW1050 -10
Note on K2417: Rob Douglas: SW1050 -20
Note on B2422: Rob Douglas: Reference SW1250-20
Note on B2423: Rob Douglas: Reference SW1250-10
Note on K2423: Rob Douglas: Reference SW1250-20
Note on K2424: Rob Douglas: Reference SW1250-10
Note on L2458: Chelsea Garrison: MISSING FINAL WEIGHT
Note on B2523: Rob Douglas: Same as AP5002 Different Stock
Note on L2523: Amanda Wadley: EDIT BOM IF GOING ON H3 SCRAP -.4155 Chelsea Garrison: WAITING ON BOM TO ROLL--- CHANGE WEIGHT TO .5594

## Acme Davenport
Acme Schedule
|  |  |  | Barstock consumption thru | [5 empty] | 2018-09-06
[6 empty] | RATE | [8 empty] | ORIGINAL | SCH'D
MACH | PART | Packet |  | QTY | Routing | PCS | S/U | TOTAL | TOTAL | MAKE FROM | ROUGH | Finished | MATL # |  | start | start | due |  |  | 2018-09-20
NO | NUMBER | Made | Order QTY | BAL DUE | Cards | HR | HRS | HRS | SHIFTS | P/N | WGT EA | Weight | BAL DUE | days | date | date | date | Notes
[19 empty] | Acme Shifts Behind | Acme 2wk Shifts
[16 empty] | 2018-09-06 |  |  | 38 | 203
A1 | SV5A19 | 618640 | 40000 | 38575 | 14.8899 | 381 | 0 | 101.2467 | 13 | A02001-0028 | 0.1743 | 0.05404 | 6723.6225 | 13 | 2018-08-07 | 2018-09-06 | 2018-09-07 | material on A4 setup 8/30 run 9/4 |  | 13
1-1/4" acme | FT11401-0 | new | 5500 | 5500 | 1.6893 | 421 | 16 | 29.0641 | 4 | A02002-0022 | 0.2282 | 0.043 | 1255.1 | 4 | 2018-09-01 | 2018-09-25 | 2018-09-20 |  |  | 4
SHIFTS | BDV10007 | new | 7000 | 7000 | 3.41 | 463 | 16 | 31.1188 | 4 | A02002-0028 | 0.1623 | 0.0682 | 1136.1 | 4 | 2018-09-02 | 2018-10-01 | 2018-10-02 |  |  | 4
1 | BDV10005 | new | 5000 | 5000 | 2.325 | 463 | 16 | 26.7991 | 4 | A02002-0028 | 0.1623 | 0.0651 | 811.5 | 4 | 2018-10-01 | 2018-10-05 | 2018-10-15
2018-10-11
25
2018-09-06
A2 | A3995-1 | 619239 | 8000 | 6300 | 0.423 | 650 | 0 | 9.6923 | 1 | A02032-0026 | 0.0441 | 0.0094 | 277.83 | 1 | 2018-08-01 | 2018-09-06 | 2018-08-13 | setup 9/4 run 9/5 | 1 | 1
1-1/4" acme | TC6301(1/2) | 620550 | 18000 | 18000 | 10.8 | 288 | 16 | 78.5 | 10 | A02002-0022 | 0.2553 | 0.084 | 4595.4 | 10 | 2018-08-07 | 2018-09-07 | 2018-08-27 |  | 10 | 10
SHIFTS | FC2515 | 620366 | 58000 | 58000 | 42.6714 | 642 | 16 | 106.3427 | 14 | A02002-0024 | 0.0473 | 0.103 | 2743.4 | 14 | 2018-09-01 | 2018-09-21 | 2018-09-20 |  |  | 14
1 | M30017 | NON STND | 42000 | 42000 | 4.062 | 747 | 16 | 72.2249 | 10 | A02002-0024 | 0.0424 | 0.01354 | 1780.8 | 10 | 2018-09-10 | 2018-10-11 | 2018-10-01 |  |  | 10
| NK2501 | NON STND | 41500 | 41500 | 9.7584 | 465 | 16 | 105.2473 | 14 | A02002-0020 | 0.1205 | 0.03292 | 5000.75 | 14 | 2018-10-09 | 2018-10-25 | 2018-10-29
| M20017 | NON STND | 77000 | 77000 | 5.885 | 639 | 16 | 136.5008 | 18 | A02002-0028 | 0.05 | 0.0107 | 3850 | 18 | 2018-10-30 | 2018-11-14 | 2018-11-19
2018-12-10
67
2018-09-06
A3 | TRV5020 | 621211 | 16000 | 16000 | 15.7371 | 324 | 0 | 49.3827 | 7 | A02002-0028 | 0.3623 | 0.1377 | 5796.8 | 7 | 2018-10-05 | 2018-09-06 | 2018-10-25 | setup 9/5 run 9/6
1 1/4" Acme | TRV2523 | R&D | [11 empty] | 2 |  | 2018-09-17
Double Threading | AP5005 | 619779 | 100000 | 100000 | 4.9286 | 611 | 16 | 179.6661 | 24 | A02001-0022 | 0.0455 | 0.0069 | 4550 | 24 | 2018-09-15 | 2018-09-19 | 2018-10-01 |  |  | 24
SHIFTS | [15 empty] | 2018-10-23
1
31
2018-09-06
A4 | 106781-1-LF | 616495 | 2000 | 476 | 0.612 | 306 | 0 | 1.5556 | 0 | A03001-0028 | 0.4754 | 0.18 | 226.2904 | 0 | 2018-10-01 | 2018-09-06 | 2018-10-15 | setup 8/1 run 8/29
1 1/4" Acme | 106781-1 | 616223 | 10500 | 10500 | 13.5 | 342 | 16 | 46.7018 | 6 | A02001-0028 | 0.4754 | 0.18 | 4991.7 | 6 | 2018-09-10 | 2018-09-06 | 2018-10-01 |  |  | 6
Back Drill | 106269-1 | 619489 | 13500 | 13500 | 13.5964 | 202 | 16 | 82.8317 | 11 | A02001-0024 | 0.3585 | 0.141 | 4839.75 | 11 | 2018-10-02 | 2018-09-14 | 2018-10-22
SHIFTS | [15 empty] | 2018-10-01
1
17
2018-09-06
A5 | 106-132-2 | 618643 | 12000 | 4863 | 2.9178 | 149 | 0 | 32.6376 | 4 | A02016-0036 | 0.2955 | 0.084 | 1437.0165 | 4 | 2018-08-10 | 2018-09-06 | 2018-09-01 | running 8/24 | 4 | 4
2'ACME | 106-133-2 | 619240 | 10000 | 10000 | 6 | 149 | 4 | 71.1141 | 9 | A02016-0036 | 0.2955 | 0.084 | 2955 | 9 | 2018-09-01 | 2018-09-12 | 2018-10-01 |  |  | 9
SHIFTS | SW1005 | 619780 | 5000 | 5000 | 13.1829 | 227 | 16 | 38.0264 | 5 | A02001-0060 | 1.9036 | 0.36912 | 9518 | 5 | 2018-10-01 | 2018-09-25 | 2018-10-20
1 | 42412(1/2) | new | 16000 | 16000 | 20.1143 | 287 | 16 | 71.7491 | 10 | A04001-0028 | 0.1391 | 0.044 | 2225.6 | 10 | 2018-10-06 | 2018-10-02 | 2018-10-26
2018-10-16
28
2018-09-06
A6 | SB7505 | 616702 | 11000 | 11000 | 6.8357 | 363 | 16 | 46.303 | 6 | A02001-0038 | 0.4454 | 0.087 | 4899.4 | 6 | 2018-09-02 | 2018-09-06 | 2018-09-21 | setup 9/4 |  | 6
2'ACME | WP5008 | 619677 | 11000 | 11000 | 11.2986 | 309 | 16 | 51.5987 | 7 | A02001-0034 | 0.5281 | 0.1438 | 5809.1 | 7 | 2018-09-08 | 2018-09-14 | 2018-10-08 |  |  | 7
SHIFTS | [13 empty] | 0 |  | 2018-09-25
1 | PCV10002 (1/2) | hold | 4000 | 4000 | 11.4286 | 22 | 16 | 197.8182 | 26 | A06101-0042 | 0.4822 | 0.4 | 1928.8 | 26 | 2018-10-01 | 2018-09-25 | 2018-10-15
| 143013-13-C | 616275 | 7500 | 7500 | 4.0714 | 203 | 16 | 52.9458 | 7 | A01101-0042 | 0.2226 | 0.076 | 1669.5 | 7 | 2018-10-01 | 2018-10-31 | 2018-10-30 | setup 8/17 on hold
2018-11-09
13
2018-09-06
A7 | S144S144001 | 618294 | 3000 | 1820 | 12.025 | 75 | 0 | 24.2667 | 3 | A02002-0056 | 2.9613 | 0.925 | 5389.566 | 3 | 2018-09-04 | 2018-09-06 | 2018-09-24 | setup 8/22 run 8/30 |  | 3
2' ACME | M30073 | 619982 | 4000 | 4000 | 4.4 | 338 | 16 | 27.8343 | 4 | A02002-0032 | 0.4107 | 0.154 | 1642.8 | 4 | 2018-09-01 | 2018-09-11 | 2018-09-20 |  |  | 4
Old Conveyor | M40070(1/2) | 621198 | 12000 | 12000 | 10.68 | 359 | 16 | 49.4262 | 7 | A02002-0032 | 0.3715 | 0.1246 | 4458 | 7 | 2018-09-20 | 2018-09-17 | 2018-10-08
SHIFTS | R421-8BK | 614310 | 21500 | 21500 | 2.8226 | 458 | 16 | 62.9432 | 8 | A02002-0032 | 0.094 | 0.01838 | 2021 | 8 | 2018-09-10 | 2018-09-26 | 2018-10-01 |  |  | 8
1 | R421-8BK-LF | 618641 | 3000 | 3000 | 0.39386 | 458 | 16 | 22.5502 | 3 | A03002-0032 | 0.0843 | 0.01838 | 252.9 | 3 | 2018-10-01 | 2018-10-08 | 2018-10-15
2018-10-11
2018-10-11
| M30075 | hold | 12000 | 12000 | 12.6857 | 476 | 16 | 41.2101 | 5 | A02002-0032 | 0.3594 | 0.148 | 4312.8 | 5 | 2018-10-01 | 2018-10-11 | 2018-10-20
30
2018-09-06
A8 | 104532-1 | 619781 | 11000 | 11000 | 8.4857 | 378 | 16 | 45.1005 | 6 | A02001-0020 | 0.2286 | 0.108 | 2514.6 | 6 | 2018-09-01 | 2018-09-06 | 2018-09-20 | setup 9/5 |  | 6
1" Acme | CTM16 | 620404 | 11000 | 11000 | 0.2585 | 735 | 16 | 30.966 | 4 | A02001-0014 | 0.0142 | 0.00329 | 156.2 | 4 | 2018-09-10 | 2018-09-14 | 2018-10-01 |  |  | 4
SHIFTS | BDV20013 | 620879 | 6000 | 6000 | 0.94457 | 506 | 16 | 27.8577 | 4 | A02001-0013 | 0.068 | 0.02204 | 408 | 4 | 2018-09-10 | 2018-09-20 | 2018-10-01 |  |  | 4
1 | DM2504 | 620941 | 140000 | 140000 | 6.8 | 956 | 16 | 162.4435 | 22 | A02001-0020 | 0.0279 | 0.0068 | 3906 | 22 | 2018-10-01 | 2018-09-26 | 2018-10-22
| TC1267 | new | 12000 | 12000 | 3.7714 | 171 | 16 | 86.1754 | 11 | A02001-0024 | 0.2155 | 0.044 | 2586 | 11 | 2018-10-09 | 2018-10-26 | 2018-10-29
2018-11-12
14
2018-09-06
A9 | 426607 | 617848 | 17000 | 0 | 0 | 106 | 0 | 0 | 0 | A06201-0026 | 0.2194 | 0.09154 | 0 | 0 | 1901-12-10 | 2018-09-06 | 2018-08-01 | out 9/5 | 0 | 0
1" Acme | DP2501 | 620091 | 100000 | 100000 | 18.1429 | 648 | 16 | 170.321 | 23 | A02002-0018 | 0.0799 | 0.0254 | 7990 | 11.5 | 2018-08-03 | 2018-09-06 | 2018-09-03 | setup 9/6 | 23 | 23
SHIFTS | VR2501 | 618646 | 18000 | 18000 | 5.4977 | 413 | 16 | 59.5835 | 8 | A02002-0018 | 0.1121 | 0.04276 | 2017.8 | 4 | 2018-09-01 | 2018-09-21 | 2018-09-24 |  |  | 8
2 | 103464-1 | 619782 | 103000 | 103000 | 2.6854 | 933 | 16 | 126.3966 | 17 | A02002-0018 | 0.0161 | 0.00365 | 1658.3 | 8.5 | 2018-09-10 | 2018-09-27 | 2018-10-01 |  |  | 17
| FC2508 | new | 20000 | 20000 | 0.96714 | 705 | 16 | 44.3688 | 6 | A02001-0024 | 0.0473 | 0.00677 | 946 | 3 | 2018-10-01 | 2018-10-09 | 2018-10-26
| M2525091 | new part | 6000 | 6000 | 1.7571 | 540 | 16 | 27.1111 | 4 | A02002-0020 | 0.1119 | 0.041 | 671.4 | 2 | 2018-09-25 | 2018-10-12 | 2018-10-15
2018-10-16
58
2018-09-06
A10 | TRV2523 | 619288 | 30000 | 0 | 0 | 405 | 0 | 0 | 0 | A09302-0020 | 0.0575 | 0.017 | 0 | 0 | 2018-09-01 | 2018-09-06 | 2018-09-15 |  |  | 0 | 745# per day 2 shifts
1" acme | TRV2523 | 621207 | 30000 | 21045 | 2.5555 | 405 | 0 | 51.963 | 7 | A09302-0020 | 0.0575 | 0.017 | 1210.0875 | 3.5 | 2018-09-01 | 2018-09-06 | 2018-09-15 |  |  | 7
SHIFTS | [15 empty] | 2018-09-11
2
0
2018-09-06
A11 | TRV2523 | 619289 | 30000 | 0 | 0 | 405 | 0 | 0 | 0 | A09302-0020 | 0.0575 | 0.017 | 0 | 0 | 2018-09-01 | 2018-09-06 | 2018-09-15 |  |  | 0
1-5/8-8SP | TRV2523 | 621208 | 30000 | 22550 | 2.7382 | 405 | 0 | 55.679 | 7 | A09302-0020 | 0.0575 | 0.017 | 1296.625 | 3.5 | 2018-09-01 | 2018-09-06 | 2018-09-15 |  |  | 7
SHIFTS | [15 empty] | 2018-09-11
2
7
2018-09-06
A12
2-5/8" acme
SHIFTS
0
0
Davenport Schedule
|  |  |  | Barstock consumption thru | [5 empty] | 2018-09-06
[6 empty] | RATE | [8 empty] | ORIGINAL | SCH'D |  |  | Dav Shifts Behind | Dav 2wk Shifts
MACH | PART | Packet |  |  | Routing | PCS | S/U | TOTAL | TOTAL | MAKE FROM | ROUGH | Finished | MATL # |  | start | start | due |  | 170 | 435
NO | NUMBER | Made |  | BAL DUE | Cards | HR | HRS | HRS | SHIFTS | P/N | WGT EA | Weight | BAL DUE | days | date | date | date | Notes
`````````` | [15 empty] | 2018-09-06
ND1 | CY30002 | 619338 | 13000 | 0 | 0 | 172 | 0 | 0 | 0 | A06101-0010 | 0.0207 | 0.0381 | 0 | 0 | 2018-09-01 | 2018-09-06 | 2018-09-15 |  |  | 0
SHIFTS | CY30002 | 621205 | 24000 | 23230 | 6.3219 | 172 | 0 | 135.0581 | 18 | A06101-0010 | 0.0207 | 0.0381 | 480.861 | 9 | 2018-09-15 | 2018-09-06 | 2018-09-30 |  |  | 18
2 | [15 empty] | 2018-09-19
stop spindle
18
`````````` | [15 empty] | 2018-09-06
ND2 | CY12101 | 619986 | 15000 | 0 | 0 | 743 | 0 | 0 | 0 | A02002-0014 | 0.0362 | 0.0502 | 0 | 0 | 2018-06-25 | 2018-09-06 | 2018-07-20 | pulled 9/4 | 0 | 0
SHIFTS | CY11705 | 619993 | 30000 | 30000 | 2.5714 | 389 | 0 | 77.1208 | 10 | A02002-0014 | 0.0298 | 0.012 | 894 | 5 | 2018-08-10 | 2018-09-06 | 2018-09-03 | setup 9/4 run 9/6 | 10 | 10
2 | RCF103 | 619989 | 10000 | 10000 | 0.54286 | 400 | 16 | 41 | 5 | A02001-0016 | 0.0526 | 0.0076 | 526 | 2.5 | 2018-07-20 | 2018-09-13 | 2018-08-17 |  | 5 | 5
stop spindle | CY30005 | 618568 | 10000 | 10000 | 0.089286 | 143 | 16 | 85.9301 | 11 | A06102-0014 | 0.0293 | 0.00125 | 293 | 5.5 | 2018-08-15 | 2018-09-17 | 2018-09-15 |  |  | 11
| NK2515 | new | 40000 | 40000 | 2.4 | 601 | 16 | 82.5557 | 11 | A02001-0018 | 0.0233 | 0.0084 | 932 | 5.5 | 2018-09-25 | 2018-09-24 | 2018-10-15
| B3639-052 | new | 52000 | 52000 | 0.055714 | 261 | 4 | 203.2337 | 27 | A06261-0006 | 0.0028 | 0.00015 | 145.6 | 13.5 | 2018-08-01 | 2018-10-01 | 2018-08-20 |  | 27 | 27
| B3639-156 | new | 8000 | 8000 | 0.10886 | 261 | 16 | 46.6513 | 6 | A06261-0008 | 0.005 | 0.001905 | 40 | 3 | 2018-09-10 | 2018-10-18 | 2018-10-01 |  |  | 6
| B3639-200 | new | 5000 | 5000 | 0.10054 | 261 | 16 | 35.1571 | 5 | A06261-0010 | 0.0078 | 0.002815 | 39 | 2.5 | 2018-09-10 | 2018-10-23 | 2018-10-01 |  |  | 5
| B3639-125 | new | 24000 | 24000 | 0.17177 | 261 | 0 | 91.954 | 12 | A06261-0006 | 0.0028 | 0.001002 | 67.2 | 6 | 2018-09-11 | 2018-10-25 | 2018-10-02 |  |  | 12
| 102263-2 | new | 7500 | 7500 | 0.15986 | 175 | 16 | 58.8571 | 8 | A06202-0010 | 0.0141 | 0.002984 | 105.75 | 4 | 2018-11-01 | 2018-11-02 | 2018-11-17
| M30005 | new | 35000 | 35000 | 4.28 | 490 | 16 | 87.4286 | 12 | A02002-0018 | 0.0773 | 0.01712 | 2705.5 | 6 | 2018-11-01 | 2018-11-08 | 2018-11-19
2018-11-16
107
`````````` | [15 empty] | 2018-09-06
D1 | SP2512 | 620027 | 80000 | 69220 | 2.4721 | 623 | 0 | 111.1075 | 15 | A02001-0013 | 0.0373 | 0.005 | 2581.906 | 7.5 | 2018-08-10 | 2018-09-06 | 2018-09-01 | setup 8/31 run 9/4 | 15 | 15
SHIFTS | SP2513 | 621200 | 80000 | 80000 | 2.8571 | 623 | 0 | 128.4109 | 17 | A02001-0013 | 0.0373 | 0.005 | 2984 | 8.5 | 2018-08-20 | 2018-09-17 | 2018-09-10 |  |  | 17
2 | SP2510 | new | 80000 | 80000 | 4.5714 | 623 | 0 | 128.4109 | 17 | A02001-0013 | 0.0373 | 0.008 | 2984 | 8.5 | 2018-09-04 | 2018-09-27 | 2018-09-24 |  |  | 17
stop spindle | DU2511 | new | 80000 | 80000 | 10.1086 | 310 | 16 | 274.0645 | 37 | A02001-0013 | 0.0537 | 0.01769 | 4296 | 18.5 | 2018-09-08 | 2018-10-09 | 2018-10-08 |  |  | 37
| NK2509 | new | 55000 | 55000 | 4.0307 | 773 | 16 | 87.1514 | 12 | A02001-0013 | 0.0388 | 0.01026 | 2134 | 6 | 2018-10-05 | 2018-11-02 | 2018-11-05
2018-11-12
98
2018-09-06
D2 | CY10222 | 618865 | 80000 | 40780 | 0.37867 | 307 | 0 | 132.8339 | 18 | A09211-0010 | 0.0071 | 0.0013 | 289.538 | 9 | 2018-06-20 | 2018-09-06 | 2018-07-16 | setup 8/23, run 8/24 3rd shift | 18 | 18
SHIFTS | CY10202-0 | 621884 | 80000 | 80000 | 2.2743 | 489 | 16 | 179.5992 | 24 | A02001-0010 | 0.0218 | 0.00398 | 1744 | 12 | 2018-09-15 | 2018-09-19 | 2018-10-01 |  |  | 24
2 | NL2511 | new | 100000 | 100000 | 1.7143 | 765 | 16 | 146.719 | 20 | A02001-0008 | 0.0132 | 0.0024 | 1320 | 10 | 2018-10-01 | 2018-10-05 | 2018-10-20
stop spindle | [15 empty] | 2018-10-19
62
2018-09-06
D3 | CY30004 | 618482 | 80000 | 11950 | 0.11096 | 470 | 0 | 25.4255 | 3 | A06101-0012 | 0.0052 | 0.0013 | 62.14 | 1.5 | 2018-07-01 | 2018-09-06 | 2018-08-05 | setup 8/13 run 8/16 | 3 | 3
SHIFTS | ESV3821 | 616497 | 25000 | 25000 | 0.30357 | 565 | 16 | 60.2478 | 8 | A06101-0012 | 0.0089 | 0.0017 | 222.5 | 4 | 2018-07-15 | 2018-09-07 | 2018-08-01 |  | 8 | 8
2 | A3853-1 | 620305 | 42000 | 42000 | 6.63 | 489 | 16 | 101.8896 | 14 | A02001-0016 | 0.0559 | 0.0221 | 2347.8 | 7 | 2018-06-25 | 2018-09-13 | 2018-07-20 |  | 14 | 14
stop spindle | BF1201 | 618550 | 16000 | 16000 | 4.0777 | 553 | 16 | 44.9331 | 6 | A02002-0014 | 0.051 | 0.03568 | 816 | 3 | 2018-09-01 | 2018-09-17 | 2018-10-01 |  |  | 6
| AP3805 | new | 135000 | 135000 | 4.9371 | 879 | 16 | 169.5836 | 23 | A02001-0016 | 0.028 | 0.00512 | 3780 | 11.5 | 2018-10-01 | 2018-09-20 | 2018-10-22
| CY30007 | 618034 | 4000 | 4000 | 0.42 | 225 | 16 | 33.7778 | 5 | A06101-0014 | 0.0296 | 0.0147 | 118.4 | 2.5 | 2018-10-01 | 2018-10-05 | 2018-11-01
| DM2514 | STND | 90000 | 90000 | 5.5029 | 503 | 16 | 194.9264 | 26 | A02001-0012 | 0.0364 | 0.00856 | 3276 | 13 | 2018-09-22 | 2018-10-09 | 2018-10-22
| CY10221 | new | 169000 | 169000 | 2.6557 | 831 | 16 | 219.3694 | 29 | A02001-0008 | 0.0087 | 0.0022 | 1470.3 | 14.5 | 2018-09-08 | 2018-09-20 | 2018-10-08 |  |  | 29
114
2018-09-06
D9 | TRV11 | 619337 | 80000 | 0 | 0 | 879 | 0 | 0 | 0 | A02002-0014 | 0.0321 | 0.01244 | 0 | 0 | 2018-09-01 | 2018-09-06 | 2018-09-20 |  |  | 0
SHIFTS | TRV11 | 621204 | 80000 | 74300 | 6.6021 | 879 | 0 | 84.5279 | 11 | A02002-0014 | 0.0321 | 0.01244 | 2385.03 | 11 | 2018-09-01 | 2018-09-06 | 2018-09-20 |  |  | 11
1 | [15 empty] | 2018-09-21
0
2018-09-06
D5 | CY13502 | 618483 | 55000 | 39990 | 0.85693 | 225 | 0 | 177.7333 | 24 | A06201-0010 | 0.0113 | 0.003 | 451.887 | 12 | 2018-08-10 | 2018-09-06 | 2018-06-14 | setup 8/8 run 8/15 | 24 | 24
stop spindle | CT5011 | new | 80000 | 80000 | 2.4571 | 906 | 16 | 104.3002 | 14 | A02001-0014 | 0.0135 | 0.0043 | 1080 | 7 | 2018-09-05 | 2018-09-24 | 2018-09-20 |  |  | 14
SHIFTS | [15 empty] | 2018-10-03
2
38
2018-09-06
D6 | LH50004 | 620683 | 3500 | 3500 | 0.24625 | 686 | 0 | 5.102 | 1 | A19101-0022 | 0.0323 | 0.00985 | 113.05 | 0.5 | 2018-09-04 | 2018-09-06 | 2018-09-24 | setup 8/29 run 9/4 |  | 1
SHIFTS | M20065 | 621175 | 7500 | 7500 | 1.4529 | 519 | 16 | 30.4509 | 4 | A02001-0016 | 0.0553 | 0.02712 | 414.75 | 2 | 2018-07-20 | 2018-09-06 | 2018-08-13 |  | 4 | 4
2 | DP2505 | 621176 | 76000 | 76000 | 1.0423 | 995 | 16 | 92.3819 | 12 | A02001-0016 | 0.0083 | 0.00192 | 630.8 | 6 | 2018-07-22 | 2018-09-10 | 2018-08-15 |  | 12 | 12
| LH50011(1/2) | 612376 | 6000 | 6000 | 0.091286 | 395 | 16 | 31.1899 | 4 | A19201-0010 | 0.011 | 0.00213 | 66 | 2 | 2018-08-20 | 2018-09-18 | 2018-09-10 |  |  | 4
| RCF104 | 620028 | 10000 | 10000 | 0.14286 | 900 | 16 | 27.1111 | 4 | A19101-0022 | 0.045 | 0.002 | 450 | 2 | 2018-07-20 | 2018-09-20 | 2018-08-17 |  | 4 | 4
| RCF316 | 620447 | 10000 | 10000 | 0.45714 | 463 | 16 | 37.5983 | 5 | A19101-0020 | 0.0239 | 0.0064 | 239 | 2.5 | 2018-08-20 | 2018-09-24 | 2018-09-10 | Tooling 9/6 |  | 5
| RCF216 | 620554 | 5000 | 5000 | 0.35714 | 463 | 16 | 26.7991 | 4 | A19101-0022 | 0.029 | 0.01 | 145 | 2 | 2018-08-20 | 2018-09-26 | 2018-09-10 | Tooling 9/6 |  | 4
| DU2510 | new | 66000 | 66000 | 13.7469 | 544 | 16 | 137.3235 | 18 | A02002-0018 | 0.0789 | 0.02916 | 5207.4 | 9 | 2018-09-04 | 2018-09-28 | 2018-09-24 |  |  | 18
| DM2513 | STND | 95000 | 95000 | 17.9821 | 823 | 16 | 131.4313 | 18 | A02001-0018 | 0.0284 | 0.0265 | 2698 | 9 | 2018-10-05 | 2018-10-11 | 2018-11-05
| M1212001 | new | 5000 | 5000 | 1.6482 | 336 | 16 | 30.881 | 4 | A02005-0022 | 0.153 | 0.04615 | 765 | 2 | 2018-09-04 | 2018-10-24 | 2018-09-24 |  |  | 4
| NC2505 | new | 27000 | 27000 | 0.62486 | 1199 | 16 | 38.5188 | 5 | A02001-0016 | 0.0184 | 0.00324 | 496.8 | 2.5 | 2018-10-05 | 2018-10-26 | 2018-11-05
2018-10-30
79
2018-09-06
D7 | ST2A03 | 617430 | 30000 | 0 | 0 | 397 | 0 | 0 | 0 | A02001-0020 | 0.0496 | 0.014224 | 0 | 0 | 2018-08-01 | 2018-09-06 | 2018-08-15 | run 8/20 | 0 | 0
SHIFTS | ST2A03 | 621203 | 30000 | 24540 | 9.9731 | 397 | 0 | 61.8136 | 8 | A02001-0020 | 0.0496 | 0.014224 | 1217.184 | 8 | 2018-08-15 | 2018-09-06 | 2018-08-30 |  | 8 | 8
1 | [15 empty] | 2018-09-18
8
2018-09-06
D8 | CY90022 | 620231 | 10000 | 10000 | 0.35714 | 216 | 16 | 62.2963 | 8 | A02001-0012 | 0.0154 | 0.005 | 154 | 4 | 2018-08-20 | 2018-09-06 | 2018-09-10 | setup 8/31 |  | 8
SHIFTS | M40011 | 621177 | 18000 | 18000 | 3.3171 | 667 | 16 | 42.9865 | 6 | A02001-0022 | 0.0878 | 0.0258 | 1580.4 | 3 | 2018-08-03 | 2018-09-12 | 2018-09-03 |  | 6 | 6
2 | TRV15 | 619342 | 80000 | 80000 | 2.5371 | 922 | 16 | 102.7679 | 14 | A02001-0013 | 0.0212 | 0.00444 | 1696 | 7 | 2018-08-20 | 2018-09-17 | 2018-09-10 |  |  | 14
| RCF007 | 619783 | 40000 | 40000 | 2 | 554 | 16 | 88.2022 | 12 | A02001-0010 | 0.0194 | 0.007 | 776 | 6 | 2018-08-10 | 2018-09-26 | 2018-08-30 | tooling eta 9/20 | 12 | 12
2018-10-04
#REF!
Color Codes
New Part
Material in House
Material 1 week
Material 2 weeks
Material partial in house
Hard Orders
Needs Reviewed | [5 empty] | Total Shifts Needed |  |  |  | #REF!
Gross & Scrap Verified- in BOM
Cycle time Verified
Vefication that BOM matches P/N Secondary schedule Only
| 100135-1 |  | 0 | 0 | 0 | 24 | 16 | 16 | 2 | A06201-0024 | 0.1521 | 0.111 | 0 |  |  |  | A8
| 100146-1 |  | 0 | 0 | 0 | 24 | 16 | 16 | 2 | A5550-16 | 0.0316 | 0.025 | 0 |  |  |  | SM
| 101467-19(1/3) |  | 0 | 0 | 0 | 381 | 16 | 16 | 2 | A02002-0024 | 0.1607 | 0.04918 | 0 |  |  |  | A3
| 101467-19-LF(1/3) |  | 0 | 0 | 0 | 277 | 16 | 16 | 2 | A03002-0024 | 0.1607 | 0.06255 | 0 |  |  |  | A3
| 101467-3 |  | 0 | 0 | 0 | 24 | 16 | 16 | 2 | A02002-0024 | 0.2018 | 0.06142 | 0 |  |  |  | A3
| 101467-1(1/3) |  | 0 | 0 | 0 | 277 | 16 | 16 | 2 | A02032-0024 | 0.1607 | 0.04918 | 0 |  |  |  | A3
| 101582-1(1/3) |  | 0 | 0 | 0 | 369 | 16 | 16 | 2 | A02002-0024 | 0.1764 | 0.0736 | 0 |  |  |  | A3 only
| 101728-1(1/3) |  | 0 | 0 | 0 | 300 | 16 | 16 | 2 | A02002-0032 | 0.4083 | 0.1517 | 0 |  |  |  | A3
| 101728-1-LF(1/3) |  | 0 | 0 | 0 | 241 | 16 | 16 | 2 | A03002-0032 | 0.4083 | 0.1517 | 0 |  |  |  | A3
| 101728-2(1/3) |  | 0 | 0 | 0 | 180 | 16 | 16 | 2 | A02002-0032 | 0.3802 | 0.1517 | 0 |  |  |  | A3
| 101729-1(1/3) |  | 0 | 0 | 0 | 326 | 16 | 16 | 2 | A02002-0032 | 0.4799 | 0.1699 | 0 |  |  |  | A3
| 102095-2(1/3) | B/S Alternative | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02002-0024 | 0.1734 | 0.065 | 0 |  |  |  | A3
| 102100-1 | STND | 0 | 0 | 0 | 595 | 16 | 16 | 2 | A02002-0022 | 0.0283 | 0.00466 | 0 |  |  |  | A4 | jam nut
| 102100-1-LF |  | 0 | 0 | 0 | 505 | 16 | 16 | 2 | A03002-0022 | 0.0283 | 0.00481 | 0 |  |  |  | A4
| 102263-1 |  | 0 | 0 | 0 | 163 | 16 | 16 | 2 | A02002-0010 | 0.0137 | 0.003268 | 0 |  |  |  | D7
| 102263-2 |  | 0 | 0 | 0 | 175 | 16 | 16 | 2 | A06202-0010 | 0.0141 | 0.002984 | 0 |  |  |  | Dav
new rate | 103464-1 |  | 0 | 0 | 0 | 933 | 16 | 16 | 2 | A02002-0018 | 0.0161 | 0.00365 | 0 | Jam Nut |  |  | A9
| 103464-1-LF |  | 0 | 0 | 0 | 279 | 16 | 16 | 2 | A03002-0018 | 0.016 | 0.00365 | 0 | Jam Nut |  |  | A9
| 104114-3(1/3) | Hydromat | 0 | 0 | 0 | 257 | 16 | 16 | 2 | A02002-0022 | 0.2005 | 0.06844 | 0 |  | moved to hydro
| 104114-1(1/3) | Hydromat | 0 | 0 | 0 | 257 | 16 | 16 | 2 | A02002-0022 | 0.1741 | 0.05619 | 0 |  | moved to hydro
| 104115-3 |  | 0 | 0 | 0 | 180 | 16 | 16 | 2 | A06202-0008 | 0.0101 | 0.0053 | 0 |  |  |  | Dav
| 104115-4 |  | 0 | 0 | 0 | 180 | 16 | 16 | 2 | A06202-0008 | 0.0101 | 0.0053 | 0 |  |  |  | Dav
| 104532-1 |  | 0 | 0 | 0 | 378 | 16 | 16 | 2 | A02001-0020 | 0.2286 | 0.108 | 0 |  |  |  | A8
| 104532-1-LF |  | 0 | 0 | 0 | 378 | 16 | 16 | 2 | A03001-0020 | 0.2286 | 0.108 | 0 |  |  |  | A8
| 105140-2(1/3) |  | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02002-0028 | 0.387 | 0.1074 | 0
| 105950-1 |  | 0 | 0 | 0 | 704 | 16 | 16 | 2 | A02001-0012 | 0.0324 | 0.01628 | 0 |  |  |  | Dav
| 105950-1-LF |  | 0 | 0 | 0 | 437 | 16 | 16 | 2 | A03001-0012 | 0.0324 | 0.1314 | 0 |  |  |  | Dav
| 105950-2 |  | 0 | 0 | 0 | 600 | 16 | 16 | 2 | A02001-0012 | 0.0308 | 0.1314 | 0 |  |  |  | Dav
| 105991-1 |  | 0 | 0 | 0 | 2 | 16 | 16 | 2 | 105991U-1 | 1 | 0.0622 | 0 |  |  |  | SM
| 105991-4(1/3) |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0024 | 0.2318 | 0.084 | 0 |  |  |  | SM
| 105991-1(1/3) |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0024 | 0.3156 | 0.0622 | 0 |  |  |  | SM
| 106-132-2 |  | 0 | 0 | 0 | 149 | 4 | 4 | 1 | A02016-0036 | 0.2955 | 0.084 | 0 |  |  |  | A5/A7 Only
| 106-133-2 |  | 0 | 0 | 0 | 149 | 4 | 4 | 1 | A02016-0036 | 0.2955 | 0.084 | 0 |  |  |  | A5/A7 Only
| 106148-1(1/3) | Hydromat | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0022 | 0.1741 | 0.05236 | 0 |  | A15 |  | SM
| 106238-1(1/3) | Hydromat | 0 | 0 | 0 | 40 | 16 | 16 | 2 | A06202-0024 | 0.1635 | 0.06025 | 0 |  | Acme |  | A3
| 106267-1 |  | 0 | 0 | 0 | 281 | 16 | 16 | 2 | A02002-0022 | 0.3277 | 0.13192 | 0 |  |  |  | A3
new rate | 106269-1 |  | 0 | 0 | 0 | 202 | 16 | 16 | 2 | A02001-0024 | 0.3585 | 0.141 | 0 |  | Acme |  | A3
| 106269-1-LF |  | 0 | 0 | 0 | 343 | 16 | 16 | 2 | A03001-0024 | 0.3585 | 0.141 | 0 |  | Acme |  | A3
| 106273-1 |  | 0 | 0 | 0 | 90 | 16 | 16 | 2 | A06202-0022 | 0.1276 | 0.089 | 0 |  | Acme/B&S |  | SM
| 106273-2 |  | 0 | 0 | 0 | 60 | 16 | 16 | 2 | A06202-0028 | 0.2434 | 0.152 | 0 |  | Acme/B&S |  | SM
| 106781-1 | stnd | 0 | 0 | 0 | 342 | 16 | 16 | 2 | A02001-0028 | 0.4754 | 0.18 | 0 |  | Acme |  | A3
| 106781-1-LF | stnd | 0 | 0 | 0 | 306 | 16 | 16 | 2 | A03001-0028 | 0.4754 | 0.18 | 0 |  | Acme |  | A3
| 106782-1 | stnd | 0 | 0 | 0 | 320 | 16 | 16 | 2 | A02001-0016 | 0.1271 | 0.05808 | 0 |  | B&S |  | A3
| 106782-1-LF | stnd | 0 | 0 | 0 | 320 | 16 | 16 | 2 | A03001-0016 | 0.1271 | 0.05808 | 0 |  | B&S |  | A3
| 109784-10 |  | 0 | 0 | 0 | 262 | 16 | 16 | 2 | A02002-0034 | 0.8586 | 0.621 | 0 |  |  |  | A5
| 143003-02-C(1/2) | Hydromat | 0 | 0 | 0 | 88 | 16 | 16 | 2 | A01102-0052 | 2.3347 | 1.008 | 0 |  |  |  | A12
| 143011-13-C |  | 0 | 0 | 0 | 452 | 16 | 16 | 2 | A01101-0026 | 0.0606 | 0.023 | 0 |  |  |  | A2
| 143012-13-C |  | 0 | 0 | 0 | 296 | 16 | 16 | 2 | A01101-0034 | 0.1244 | 0.041 | 0 |  |  |  | A6
| 143013-13-C |  | 0 | 0 | 0 | 203 | 16 | 16 | 2 | A01101-0042 | 0.2226 | 0.076 | 0 |  |  |  | A6
| 143102-C |  | 0 | 0 | 0 | 152 | 16 | 16 | 2 | A01102-0034 | 0.2357 | 0.0682 | 0 |  |  |  | A6
| 143126-2-C(1/2) | Hydromat | 0 | 0 | 0 | 88 | 16 | 16 | 2 | A01102-0052 | 1.8933 | 0.905 | 0 |  |  |  | A6
F4 | 143131-1-C |  | 0 | 0 | 0 | 300 | 16 | 16 | 2 | A01102-0030 | 0.1858 | 0.09 | 0 |  |  |  | A2
F4 | 143132-1-C |  | 0 | 0 | 0 | 300 | 16 | 16 | 2 | A01102-0030 | 0.1829 | 0.07208 | 0 |  |  |  | A2
| 143133-1-C |  | 0 | 0 | 0 | 181 | 16 | 16 | 2 | A01102-0034 | 0.2618 | 0.08045 | 0 |  |  |  | A6
| 143134-1-C |  | 0 | 0 | 0 | 163 | 16 | 16 | 2 | A01102-0044 | 0.5184 | 0.1809 | 0 |  |  |  | A6
| 143139-1-C(1/2) |  | 0 | 5000 | 57.2143 | 76 | 16 | 81.7895 | 11 | A01102-0064 | 3.4589 | 1.602 | 17294.5 |  |  |  | A12
| 143140-1-C |  | 0 | 0 | 0 | 131 | 16 | 16 | 2 | A01102-0056 | 0.9208 | 0.282 | 0 |  |  |  | A6
| 143176-1-C(1/2) |  | 0 | 0 | 0 | 80 | 16 | 16 | 2 | A01102-0064 | 3.4075 | 1.575 | 0 |  |  |  | A12
| 143177-1-C |  | 0 | 0 | 0 | 80 | 16 | 16 | 2 | A01102-0056 | 0.9938 | 0.3422 | 0 |  |  |  | A6
F4 | 143181-1-CP(1/2) |  | 0 | 0 | 0 | 182 | 16 | 16 | 2 | A01102-0030 | 0.1858 | 0.093 | 0 |  |  |  | A2
F4 | 143182-1-C |  | 0 | 0 | 0 | 152 | 16 | 16 | 2 | A01102-0030 | 0.0243 | 0.093 | 0 |  |  |  | A6
| 143183-1-C |  | 0 | 0 | 0 | 160 | 16 | 16 | 2 | A01102-0034 | 0.3006 | 0.0916 | 0 |  |  |  | A6
| 143304-01-C(1/2) |  | 0 | 0 | 0 | 81 | 16 | 16 | 2 | A01102-0060 | 3.1045 | 1.546 | 0 |  |  |  | A6
| 143313-01-C |  | 0 | 0 | 0 | 98 | 16 | 16 | 2 | A01102-0040 | 0.4905 | 0.4269 | 0 |  |  |  | A6
| 143314-01-C(1/2) |  | 0 | 0 | 0 | 131 | 16 | 16 | 2 | A01102-0052 | 1.085 | 0.461 | 0 |  |  |  | A6
| 143315-01-C |  | 0 | 0 | 0 | 60 | 16 | 16 | 2 | A01102-0068 | 2.7143 | 0.8562 | 0 |  |  |  | A6
| 143344-01-C(1/2) |  | 0 | 0 | 0 | 81 | 16 | 16 | 2 | A01102-0060 | 3.1045 | 1.51 | 0 |  |  |  | A6
| 143351-01-C |  | 0 | 0 | 0 | 182 | 16 | 16 | 2 | A01102-0030 | 0.1932 | 0.0959 | 0 |  |  |  | A2
| 143352-1-C |  | 0 | 0 | 0 | 300 | 16 | 16 | 2 | A01102-0030 | 0.1829 | 0.8072 | 0 |  |  |  | A2
| 143353-01-C |  | 0 | 0 | 0 | 98 | 16 | 16 | 2 | A01102-0040 | 0.5402 | 0.2982 | 0 |  |  |  | A6
| 143354-01-C(1/2) |  | 0 | 0 | 0 | 98 | 16 | 16 | 2 | A01102-0052 | 1.2401 | 0.49965 | 0 |  |  |  | A6
| 143356-01-C(1/2) | Hydromat | 0 | 0 | 0 | 88 | 16 | 16 | 2 | A01102-0052 | 1.8679 | 1.066 | 0 |  |  |  | A5
| 143357-01-C(1/2) |  | 0 | 0 | 0 | 134 | 16 | 16 | 2 | A01102-0040 | 0.5037 | 0.172 | 0 |  |  |  | A6
| 143358-01-C(1/2) | Hydromat | 0 | 0 | 0 | 88 | 16 | 16 | 2 | A01102-0052 | 1.8404 | 1.1916 | 0 |  |  |  | A6
| 143359-01-C(1/2) |  | 0 | 0 | 0 | 164 | 16 | 16 | 2 | A01102-0040 | 0.5527 | 0.239 | 0 |  |  |  | A6
| 144041-2-C |  | 0 | 0 | 0 | 266 | 16 | 16 | 2 | A06202-0016 | 0.0233 | 0.007 | 0 | new rate |  |  | A9
| 144043-1-C |  | 0 | 0 | 0 | 249 | 16 | 16 | 2 | A01102-0026 | 0.1085 | 0.03415 | 0 |  |  |  | A2
| 144043-2-C |  | 0 | 0 | 0 | 180 | 16 | 16 | 2 | A06202-0026 | 0.1075 | 0.03415 | 0 |  |  |  | A2
2014 | 14542-C |  | 0 | 0 | 0 | 485 | 16 | 16 | 2 | A19102-0014 | 0.02 | 0.009375 | 0 |  |  |  | D6
| 17262-0C |  | 0 | 0 | 0 | 376 | 16 | 16 | 2 | A02001-0032 | 0.2547 | 0.06166 | 0 |  |  |  | A1
| 17263-0C |  | 0 | 0 | 0 | 444 | 16 | 16 | 2 | A02001-0032 | 0.2547 | 0.06154 | 0 |  |  |  | A2
| 192115-C |  | 0 | 0 | 0 | 451 | 16 | 16 | 2 | A06101-0007 | 0.0126 | 0.005 | 0 |  |  |  | D6
| 21256A(1/2) | Hydromat | 0 | 0 | 0 | 87 | 16 | 16 | 2 | A06102-0024 | 0.4267 | 0.2 | 0 |  |  | new rate+90/hr | A6 | A6 only
F5 | 22186688-C |  | 0 | 0 | 0 | 250 | 16 | 16 | 2 | A02002-0048 | 0.9953 | 0.564 | 0 |  |  |  | A5
F5 | 23289374-C |  | 0 | 0 | 0 | 248 | 16 | 16 | 2 | A02002-0048 | 1.0694 | 0.574 | 0 |  |  |  | A5
F1 | 293138-10 | Hydromat | 0 | 0 | 0 | 221 | 16 | 16 | 2 | A02002-0044 | 1.0319 | 0.49315 | 0 |  |  |  | A5
F1 | 293546-10 | Hydromat | 0 | 0 | 0 | 221 | 16 | 16 | 2 | A02002-0044 | 1.0319 | 0.4274 | 0 |  |  |  | A5
same as H2098 | 300800 |  | 0 | 0 | 0 | 462 | 16 | 16 | 2 | A02002-0018 | 0.1127 | 0.0447 | 0 |  |  |  | D6
A3 only | 300900 |  | 0 | 0 | 0 | 426 | 16 | 16 | 2 | A02002-0028 | 0.3498 | 0.1321 | 0 |  |  |  | A3
F4 | 301783-1-C |  | 0 | 0 | 0 | 137 | 16 | 16 | 2 | A01102-0030 | 0.1942 | 0.0898 | 0 |  |  |  | A2
2016 | 301869-1-C |  | 0 | 0 | 0 | 290 | 16 | 16 | 2 | A01102-0030 | 0.1858 | 0.0723 | 0 |  |  |  | A2
2015 | 305052-C |  | 0 | 0 | 0 | 294 | 16 | 16 | 2 | A02002-0036 | 0.3831 | 0.14145 | 0 |  |  |  | A6
2013 | 314605-C-10 |  | 0 | 0 | 0 | 260 | 16 | 16 | 2 | A02002-0032 | 0.3629 | 0.159 | 0 |  |  |  | A5
2014 | 419969 |  | 0 | 0 | 0 | 973 | 16 | 16 | 2 | A02001-0008 | 0.0056 | 0.001362 | 0 |  |  |  | D6
| 42395-10 |  | 0 | 0 | 0 | 671 | 16 | 16 | 2 | A02001-0016 | 0.0238 | 0.00375 | 0 |  |  |  | D6
| 42396 |  | 0 | 0 | 0 | 324 | 16 | 16 | 2 | A06101-0005 | 0.0034 | 0.001592 | 0 |  |  |  | D4
| 42412(1/2) |  | 0 | 0 | 0 | 287 | 16 | 16 | 2 | A04001-0028 | 0.1391 | 0.044 | 0 |  |  |  | A5
| 426607 |  | 0 | 0 | 0 | 106 | 16 | 16 | 2 | A06201-0026 | 0.2194 | 0.09154 | 0 | new rate | 1905-07-05 |  | A9only
2014 | 427178 (1/2) |  | 0 | 0 | 0 | 563 | 16 | 16 | 2 | A02002-0014 | 0.0607 | 0.031 | 0 |  |  |  | D6
| 5008291-10-C | C/C Part | 0 | 0 | 0 | 302 | 16 | 16 | 2 | A01001-0034 | 0.1769 | 0.0452 | 0 |  |  |  | A2 only
| 60-4ABK |  | 0 | 0 | 0 | 100 | 16 | 16 | 2 | 60-4BK | 1 | 0.0018 | 0 |  |  |  | SM
| 60-4BK |  | 0 | 0 | 0 | 994 | 16 | 16 | 2 | A02001-0012 | 0.011 | 0.00178 | 0 |  | Dav |  | SM
| 60-4BK-LF |  | 0 | 0 | 0 | 994 | 16 | 16 | 2 | A03001-0012 | 0.011 | 0.0018 | 0 |  | Dav |  | SM
| 60-6BK |  | 0 | 0 | 0 | 900 | 16 | 16 | 2 | A02001-0013 | 0.0239 | 0.2192 | 0 |  | Dav |  | SM
| 60-6BK-LF |  | 0 | 0 | 0 | 900 | 16 | 16 | 2 | A03001-0013 | 0.0239 | 0.2192 | 0 |  | Dav |  | SM
| 61-4BK |  | 0 | 0 | 0 | 812 | 16 | 16 | 2 | A02002-0016 | 0.0362 | 0.01268 | 0 | new rate | Dav |  | SM
| 61-4BK-LF |  | 0 | 0 | 0 | 100 | 16 | 16 | 2 | A03002-0016 | 0.0365 | 0.02598 | 0 | new rate | Dav |  | SM
| 61-6BK |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0020 | 0.0618 | 0.0246 | 0 |  | Dav/Acme |  | A8
| 61-6BK-LF |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A03002-0020 | 0.0618 | 0.0246 | 0 |  | Dav/Acme |  | A8
| 79390(1/2) |  | 0 | 0 | 0 | 489 | 16 | 16 | 2 | A02001-0036 | 0.1363 | 0.03648 | 0 |  |  |  | A2
| A06651-C |  | 0 | 0 | 0 | 350 | 16 | 16 | 2 | A06101-0018 | 0.0413 | 0.012 | 0 | obsolete |  |  | A9
| A06652-C |  | 0 | 0 | 0 | 308 | 16 | 16 | 2 | A06101-0024 | 0.0807 | 0.0257 | 0 | obsolete |  |  | A9
| A24010(1/2) |  | 0 | 0 | 0 | 372 | 16 | 16 | 2 | A02001-0022 | 0.2352 | 0.0411 | 0 |  |  |  | A2
| A3098-1 |  | 0 | 0 | 0 | 300 | 16 | 16 | 2 | A02002-0034 | 0.3885 | 0.0931 | 0 |  |  |  | SM
| A3192-1 |  | 0 | 0 | 0 | 240 | 16 | 16 | 2 | A02001-0016 | 0.0338 | 0.0088 | 0 |  |  |  | SM
2014 moved | A3193-1 |  | 0 | 0 | 0 | 594 | 16 | 16 | 2 | A02001-0024 | 0.0829 | 0.0931 | 0 |  | B&S as backup |  | D6
| A3194-1 |  | 0 | 0 | 0 | 354 | 16 | 16 | 2 | A02001-0036 | 0.2303 | 0.06718 | 0 |  |  |  | A4
| A3198-1 |  | 0 | 0 | 0 | 36 | 16 | 16 | 2 | A06202-0032 | 0.2147 | 0.119 | 0 |  |  |  | SM
| A3293-1 |  | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02001-0026 | 0.1154 | 0.0283 | 0 |  |  |  | SM
| A3389-2 |  | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02001-0016 | 0.0563 | 0.0367 | 0 |  |  |  | SM
| A3612-1 |  | 0 | 0 | 0 | 200 | 16 | 16 | 2 | A02001-0026 | 0.1249 | 0.0273 | 0 |  |  |  | SM
| A3813-1 |  | 0 | 0 | 0 | 699 | 16 | 16 | 2 | A02002-0026 | 0.0506 | 0.011 | 0 |  | Acme |  | SM
| A3813-1-LF |  | 0 | 0 | 0 | 493 | 16 | 16 | 2 | A03002-0026 | 0.0544 | 0.011 | 0 |  | Acme |  | SM
| A3389-1 |  | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02001-0013 | 0.0455 | 0.01923 | 0 |  |  |  | SM
| A3853-1 |  | 0 | 0 | 0 | 489 | 16 | 16 | 2 | A02001-0016 | 0.0559 | 0.0221 | 0 |  | Dav |  | D9
| A3864-1 |  | 0 | 0 | 0 | 553 | 16 | 16 | 2 | A02001-0010 | 0.0377 | 0.0143 | 0 |  |  |  | SM
| A3923-1 |  | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02002-0016 | 0.0783 | 0.027 | 0 |  |  |  | SM
| A3942-1(1/2) |  | 0 | 0 | 0 | 85 | 16 | 16 | 2 | A06201-0016 | 0.0472 | 0.03425 | 0 |  |  |  | A8
| A3949-1 |  | 0 | 0 | 0 | 300 | 16 | 16 | 2 | A02002-0028 | 0.0611 | 0.0112 | 0 |  |  |  | Dav
| A3983-1 |  | 0 | 0 | 0 | 645 | 16 | 16 | 2 | A02002-0022 | 0.0369 | 0.00816 | 0 |  |  |  | A1 | jam nut
| A3983-1-LF |  | 0 | 0 | 0 | 559 | 16 | 16 | 2 | A03002-0022 | 0.0369 | 0.00816 | 0 |  |  |  | A1
| A3995-1 | stnd | 0 | 0 | 0 | 650 | 16 | 16 | 2 | A02002-0026 | 0.0441 | 0.0094 | 0 |  | Acme |  | A1 | jam nut
| A3995-1-LF | stnd | 0 | 0 | 0 | 650 | 16 | 16 | 2 | A03002-0026 | 0.0441 | 0.0094 | 0 |  | Acme |  | A1 | jam nut
| A4077-1 |  | 0 | 0 | 0 | 2 | 16 | 16 | 2 | A02001-0005 | 0.0019 |  | 0 |  |  |  | SM
| A5006 |  | 0 | 0 | 0 | 125 | 16 | 16 | 2 | A06202-0016 | 0.0598 |  | 0 |  |  |  | A8
| A5007 | Citizen | 0 | 0 | 0 | 115 | 16 | 16 | 2 | A06201-0012 | 0.0834 |  | 0 |  |  |  | A2
| A5010 |  | 0 | 0 | 0 | 294 | 16 | 16 | 2 | A06201-0008 | 0.0318 | 0.0283 | 0 |  |  |  | D8
| A5103 | stnd | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A02001-0022 | 0.0622 |  | 0 |  | Acme/Dav |  | D8
| A5103 | non-stnd | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A02001-0022 | 0.0588 |  | 0 |  |  |  | A1
| A5103-LF |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A03001-0022 | 0.0622 |  | 0 |  | Acme/Dav |  | D8
| A5171 |  | 0 | 0 | 0 | 511 | 16 | 16 | 2 | A06201-0003 | 0.0008 | 0.00054 | 0 |  | DAV/B&S |  | D8
| A5185 |  | 0 | 0 | 0 | 2 | 16 | 16 | 2 | A06202-0048 | 1.26 |  | 0 |  |  |  | SM
| A5202-1-LF |  | 0 | 0 | 0 | 600 | 16 | 16 | 2 | A03001-0016 | 0.008 |  | 0 |  |  |  | SM
| A5437SR |  | 0 | 0 | 0 | 134 | 16 | 16 | 2 | A04002-0030 | 0.1731 |  | 0 |  |  |  | A1
| AP2502 |  | 0 | 0 | 0 | 404 | 16 | 16 | 2 | A02002-0026 | 0.3092 |  | 0 |  |  |  | A1
| AP2503(1/2) | Hydromat | 0 | 0 | 0 | 361 | 16 | 16 | 2 | A02002-0026 | 0.3092 |  | 0 |  |  |  | #A2
| AP2504 | purchased | 0 | 0 | 0 | 255 | 16 | 16 | 2 | A02002-0026 | 0.298 |  | 0 |  |  |  | A2
| AP3802 |  | 0 | 0 | 0 | 404 | 16 | 16 | 2 | A02002-0026 | 0.3092 |  | 0 |  |  |  | A1 | A1 only
| AP3805 |  | 0 | 0 | 0 | 879 | 16 | 16 | 2 | A02001-0016 | 0.028 | 0.00512 | 0 |  |  |  | D6
F6 | AP5002 |  | 0 | 0 | 0 | 308 | 16 | 16 | 2 | A02002-0032 | 0.5158 |  | 0 |  |  |  | A5
| AP5003(1/2) |  | 0 | 0 | 0 | 332 | 16 | 16 | 2 | A02002-0032 | 0.5158 |  | 0 |  |  |  | A5
| AP5005 | STND | 0 | 0 | 0 | 800 | 16 | 16 | 2 | A02001-0022 | 0.0414 | 0.00693 | 0 | Can run on A2- but only in a complete emergency situation |  |  | D6
| AP5005 | NON STND | 0 |  | 0 | 611 | 16 | 16 | 2 | A02001-0022 | 0.0455 | 0.0069 | 0 |  |  |  | A2
| AP7501(1/4) |  | 0 | 0 | 0 | 251 | 16 | 16 | 2 | A02002-0038 | 0.9879 |  | 0 |  |  |  | A5
| AP7502(1/2) |  | 0 | 0 | 0 | 272 | 16 | 16 | 2 | A02002-0038 | 0.8665 |  | 0 |  |  |  | A5
| B1001-1(1/2) |  | 0 | 0 | 0 | 264 | 16 | 16 | 2 | A02001-0036 | 0.9396 |  | 0 |  |  |  | A1
| B1001-1-LF(1/2) |  | 0 | 0 | 0 | 217 | 16 | 16 | 2 | A02001-0036 | 0.9396 |  | 0 |  |  |  | A1
| B3222-1 |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A02001-0016 | 0.0427 |  | 0 |  | B&S/Acme |  | SM
| B3222-2 |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A02001-0020 | 0.0812 |  | 0 |  | B&S/Acme |  | SM
| B3222-3 |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A02001-0024 | 0.1426 |  | 0 |  | B&S/Acme |  | SM
| B3222-3-LF |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A03001-0024 | 0.1426 |  | 0 |  | B&S/Acme |  | SM
| B3222-4 |  | 0 | 0 | 0 | 144 | 16 | 16 | 2 | A02001-0028 | 0.2111 |  | 0 |  | B&S/Acme |  | SM
| B3222-4-LF |  | 0 | 0 | 0 | 144 | 16 | 16 | 2 | A03001-0028 | 0.2111 |  | 0 |  | B&S/Acme |  | SM
| B3451-1 |  | 0 | 0 | 0 | 144 | 16 | 16 | 2 | A02002-0014 | 0.0801 |  | 0 |  |  |  | SM
| B3454-1 |  | 0 | 0 | 0 | 144 | 16 | 16 | 2 | A02002-0026 | 0.2897 |  | 0 |  |  |  | Acme
| B3639-052 |  | 0 | 0 | 0 | 261 | 4 | 4 | 1 | A06261-0006 | 0.0028 | 0.00015 | 0 |  |  |  | Dav
| B3639-052SR |  | 0 | 0 | 0 | 180 | 16 | 16 | 2 | A06261-0006 | 0.0028 | 0.00015 | 0 |  |  |  | Dav
| B3639-062 |  | 0 | 0 | 0 | 261 | 16 | 16 | 2 | A06261-0006 | 0.0028 | 0.001422 | 0 |  |  |  | Dav
| B3639-093 |  | 0 | 0 | 0 | 180 | 16 | 16 | 2 | A06261-0006 | 0.0031 | 0.0006 | 0 |  |  |  | Dav
| B3639-125 |  | 0 | 0 | 0 | 261 | 16 | 16 | 2 | A06261-0006 | 0.0028 | 0.001002 | 0 |  |  |  | Dav
| B3639-156 |  | 0 | 0 | 0 | 261 | 16 | 16 | 2 | A06261-0008 | 0.005 | 0.001905 | 0 |  |  |  | Dav
| B3639-200 |  | 0 | 0 | 0 | 261 | 16 | 16 | 2 | A06261-0010 | 0.0078 | 0.002815 | 0 |  |  |  | Dav
| B3687-5(1/3) |  | 0 | 0 | 0 | 351 | 16 | 16 | 2 | A02002-0026 | 0.3177 |  | 0 |  |  |  | A1
| B3687-5-LF(1/3) |  | 0 | 0 | 0 | 245 | 16 | 16 | 2 | A03002-0026 | 0.3177 |  | 0 |  |  |  | A1
| BDV10004 |  | 0 | 0 | 0 | 412 | 16 | 16 | 2 | A02001-0026 | 0.0802 |  | 0 |  |  |  | A2
| BDV10005 | STND | 0 | 0 | 0 | 463 | 16 | 16 | 2 | A02002-0028 | 0.1623 | 0.0651 | 0 |  |  |  | A1
F2 | BDV10005 | NON STND | 0 | 0 | 0 | 410 | 16 | 16 | 2 | A02002-0028 | 0.1704 | 0.0651 | 0 |  |  |  | A5
| BDV10007 | STND | 0 | 0 | 0 | 463 | 16 | 16 | 2 | A02002-0028 | 0.1623 | 0.0682 | 0 |  |  |  | A2
F2 | BDV10007 | NON STND | 0 | 0 | 0 | 410 | 16 | 16 | 2 | A02002-0028 | 0.1704 | 0.06818 | 0 |  |  |  | A5
| BDV20002 |  | 0 | 0 | 0 | 803 | 16 | 16 | 2 | A02001-0024 | 0.0726 | 0.025 | 0 |  |  |  | A9
2014 | BDV20003 |  | 0 | 0 | 0 | 528 | 16 | 16 | 2 | A02001-0013 | 0.0632 |  | 0 |  |  |  | A9
2014 | BDV20012 |  | 0 | 0 | 0 | 474 | 16 | 16 | 2 | A02003-0020 | 0.0772 |  | 0 |  |  |  | A9
2014 | BDV20013 |  | 0 | 0 | 0 | 506 | 16 | 16 | 2 | A02001-0013 | 0.068 | 0.02204 | 0 |  |  |  | A9
2014 | BDV20014 |  | 0 | 0 | 0 | 721 | 16 | 16 | 2 | A02001-0013 | 0.0208 |  | 0 |  |  |  | A9
2014 | BDV20015(1/2) | obsolete | 0 | 0 | 0 | 366 | 16 | 16 | 2 | A02002-0028 | 0.2366 | 0.114 | 0 |  |  |  | A5
2015 | BDV20016(1/2) |  | 0 | 0 | 0 | 357 | 16 | 16 | 2 | A02002-0028 | 0.2383 | 0.1473 | 0 |  |  |  | A5
| BF1201 |  | 0 | 0 | 0 | 553 | 16 | 16 | 2 | A02002-0014 | 0.051 |  | 0 |  |  |  | D6
2014 | BV1201 |  | 0 | 0 | 0 | 697 | 16 | 16 | 2 | A02002-0014 | 0.0418 | 0.018 | 0 |  |  |  | D6
| BV1001 |  | 0 | 0 | 0 | 512 | 16 | 16 | 2 | A02002-0014 | 0.0417 |  | 0 |  |  |  | D6
2013 | C3838016 |  | 0 | 0 | 0 | 1023 | 16 | 16 | 2 | A02001-0014 | 0.0117 |  | 0 |  |  |  | D6
| C3850001(1/4) |  | 0 | 0 | 0 | 255 | 16 | 16 | 2 | A02002-0028 | 0.6611 |  | 0 |  |  |  | A5
| C5038009 |  | 0 | 0 | 0 | 489 | 16 | 16 | 2 | A02002-0014 | 0.0445 |  | 0 |  |  |  | D6
| C5038010 |  | 0 | 0 | 0 | 442 | 16 | 24 | 3 | A02002-0024 | 0.1733 |  | 0 |  |  |  | A2
2014 | C5038019 | obsolete | 0 | 0 | 0 | 439 | 16 | 16 | 2 | A02002-0014 | 0.0769 |  | 0 |  |  |  | D6
| C5050001(1/4) |  | 0 | 0 | 0 | 220 | 16 | 16 | 2 | A02002-0028 | 0.667 |  | 0 |  |  |  | A5
2014 | C5050005 |  | 0 | 0 | 0 | 729 | 16 | 16 | 2 | A02001-0018 | 0.0247 |  | 0 |  |  |  | D6
| C5050071(1/4) |  | 0 | 0 | 0 | 189 | 16 | 16 | 2 | A01002-0028 | 0.6047 |  | 0 |  |  |  | L1/A6
| C5050B21(1/4) |  | 0 | 0 | 0 | 220 | 16 | 16 | 2 | A02002-0028 | 0.4961 |  | 0 |  |  |  | L1/A4
| C5050B2L7(1/4) |  | 0 | 0 | 0 | 210 | 16 | 16 | 2 | A02002-0028 | 0.6043 |  | 0 |  |  |  | A7
| C5050B2L8(1/4) |  | 0 | 0 | 0 | 210 | 16 | 16 | 2 | A02002-0028 | 0.6043 |  | 0 |  |  |  | A7
F7 | C7510001(1/4) |  | 0 | 0 | 0 | 184 | 16 | 16 | 2 | A02002-0042 | 1.9915 |  | 0 |  |  |  | A7
F7 | C7575001(1/4) |  | 0 | 0 | 0 | 186 | 16 | 16 | 2 | A02002-0036 | 1.3668 |  | 0 |  |  |  | A7
| CH-101 |  | 0 | 0 | 0 | 738 | 16 | 16 | 2 | A02001-0022 | 0.0612 |  | 0 |  |  |  | D5
| CH-301 |  | 0 | 0 | 0 | 508 | 16 | 16 | 2 | A02002-0026 | 0.118 |  | 0 |  |  |  | A4
| CJ2203 |  | 0 | 0 | 0 | 440 | 16 | 16 | 2 | A02001-0016 | 0.0823 |  | 0 |  |  |  | D4
| CJ2205 |  | 0 | 0 | 0 | 392 | 16 | 16 | 2 | A02001-0024 | 0.1786 |  | 0 |  |  |  | A9
| CJ3809 |  | 0 | 0 | 0 | 650 | 16 | 16 | 2 | A02032-0012 | 0.0449 |  | 0 |  |  |  | #D6
| CS1201 |  | 0 | 0 | 0 | 693 | 16 | 16 | 2 | A02002-0014 | 0.0402 |  | 0 |  |  |  | D6
| CS2501 |  | 0 | 0 | 0 | 544 | 16 | 16 | 2 | A02002-0018 | 0.0785 | 0.03275 | 0 | 2013 |  |  | D6
| CT5011 |  | 0 | 0 | 0 | 906 | 16 | 16 | 2 | A02001-0014 | 0.0135 | 0.0043 | 0 |  |  |  | D2
| CTM16 |  | 0 | 0 | 0 | 735 | 16 | 16 | 2 | A02001-0014 | 0.0142 | 0.00329 | 0 |  |  |  | A9
F22-1 | CY10002-0 |  | 0 | 0 | 0 | 489 | 16 | 16 | 2 | A02001-0010 | 0.0219 |  | 0 |  |  |  | D3
F44 | CY10104(1/2) | obsolete | 0 | 0 | 0 | 560 | 16 | 16 | 2 | A02001-0036 | 0.1985 |  | 0 |  |  |  | A1 only
2017 | CY10110 |  | 0 | 0 | 0 | 489 | 16 | 16 | 2 | A02001-0010 | 0.0218 |  | 0 | 2017 |  |  | D2
2017 | CY10111 |  | 0 | 0 | 0 | 270 | 16 | 16 | 2 | A02001-0014 | 0.0281 |  | 0 | 2017 |  |  | D6
2017 | CY10112 |  | 0 | 0 | 0 | 270 | 16 | 16 | 2 | A02001-0008 | 0.006 |  | 0 | 2017 |  |  | D6
2017 | CY10115 |  | 0 | 0 | 0 | 270 | 16 | 16 | 2 | A02001-0010 | 0.009 |  | 0 | 2017 |  |  | D2
F22-2/3 | CY10202-0 |  | 0 | 0 | 0 | 489 | 16 | 16 | 2 | A02001-0010 | 0.0218 | 0.00398 | 0 |  |  |  | D3
| CY10203-0 |  | 0 | 0 | 0 | 846 | 16 | 16 | 2 | A02001-0012 | 0.0099 |  | 0 |  |  |  | D6
| CY10204-0 |  | 0 | 0 | 0 | 1304 | 16 | 16 | 2 | A02001-0012 | 0.0047 | 0.0015 | 0 |  |  |  | D2/D3 Only
| CY10221 |  | 0 | 0 | 0 | 831 | 16 | 16 | 2 | A02001-0008 | 0.0087 | 0.0022 | 0 |  |  |  | D4
F22-3/2 | CY10222 |  | 0 | 0 | 0 | 307 | 16 | 16 | 2 | A09211-0010 | 0.0071 | 0.0013 | 0 |  |  |  | D3
| CY10223 |  | 0 | 0 | 0 | 1025 | 16 | 16 | 2 | A09201-0012 | 0.0032 | 0.00145 | 0 |  | material | Changed | D3
2014 | CY10605-0 |  | 0 | 0 | 0 | 1125 | 16 | 16 | 2 | A02002-0012 | 0.0158 |  | 0 |  |  |  | D6
F44 | CY11101(1/2) |  | 0 | 0 | 0 | 611 | 16 | 16 | 2 | A02001-0036 | 0.1881 |  | 0 |  |  |  | A1 only
| CY11705 |  | 0 | 0 | 0 | 389 | 16 | 16 | 2 | A02002-0014 | 0.0298 | 0.012 | 0 |  |  |  | #D4
| CY11705-NP |  | 0 | 0 | 0 | 389 | 16 | 16 | 2 | A02002-0014 | 0.0298 | 0.012 | 0 |  |  |  | #D4
| CY11706 |  | 0 | 0 | 0 | 1112 | 16 | 16 | 2 | A02001-0012 | 0.0109 | 0.0027 | 0 |  |  |  | #D6
| CY11712 |  | 0 | 0 | 0 | 898 | 16 | 16 | 2 | A19101-0012 | 0.0075 | 0.00515 | 0 |  |  |  | D3
F22-3/2 | CY11722 |  | 0 | 0 | 0 | 563 | 16 | 16 | 2 | A09201-0010 | 0.0071 |  | 0 |  |  |  | D3
| CY12001(1/2) | Ganesh | 0 | 0 | 0 | 245 | 16 | 16 | 2 | A02002-0042 | 0.6504 |  | 0 |  |  |  | A7
| CY12003 | STND | 0 | 0 | 0 | 449 | 16 | 16 | 2 | A02001-0028 | 0.2236 |  | 0 |  |  |  | A1
| CY12003 | NON STND | 0 | 0 | 0 | 493 | 16 | 16 | 2 | A02001-0028 | 0.222 |  | 0 |  |  |  | A9
| CY12003 |  | 0 | 0 | 0 | 743 | 16 | 16 | 2 | A02002-0014 | 0.0362 |  | 0 |  |  |  | D6
| CY12101 |  | 0 | 0 | 0 | 743 | 16 | 16 | 2 | A02002-0014 | 0.0362 | 0.0502 | 0 |  |  |  | D6
2014 | CY12301 |  | 0 | 0 | 0 | 413 | 16 | 16 | 2 | A09331-0038 | 0.1059 | 0.0453 | 0 |  |  |  | A6
2014 | CY12402 |  | 0 | 0 | 0 | 1125 | 16 | 16 | 2 | A02002-0008 | 0.007 |  | 0 |  |  |  | D6
2017 | CY13502 |  | 0 | 0 | 0 | 225 | 16 | 16 | 2 | A06201-0010 | 0.0113 | 0.003 | 0 |  |  |  | D4
2014 | CY20002 | obsolete | 0 | 0 | 0 | 856 | 16 | 16 | 2 | A02001-0014 | 0.0185 |  | 0 | obsolete per Dan Lammers |  |  | D6
2015 | CY20003 |  | 0 | 0 | 0 | 717 | 16 | 16 | 2 | A02002-0014 | 0.0298 |  | 0 |  |  |  | D4
2015 | CY20004 |  | 0 | 0 | 0 | 170 | 24 | 24 | 3 | A06102-0014 | 0.0283 |  | 0 |  |  |  | D3
2015 | CY30002 |  | 0 | 0 | 0 | 172 | 16 | 16 | 2 | A06101-0010 | 0.0207 |  | 0 |  |  |  | D3
2016 | CY30002-LFB | new | 0 | 0 | 0 | 172 | 0 | 0 | 0 | A03001-0010 | 0.0207 |  | 0
2015 | CY30003 |  | 0 | 0 | 0 | 254 | 16 | 16 | 2 | A06101-0014 | 0.013 |  | 0 |  |  |  | D5
2015 | CY30004 |  | 0 | 0 | 0 | 470 | 16 | 16 | 2 | A06101-0012 | 0.0052 | 0.0013 | 0 |  |  |  | D5
2015 | CY30005 |  | 0 | 0 | 0 | 143 | 16 | 16 | 2 | A06102-0014 | 0.0293 | 0.00125 | 0 |  |  |  | D6
2015 | CY30006 |  | 0 | 0 | 0 | 523 | 16 | 16 | 2 | A06101-0012 | 0.0105 |  | 0 |  |  |  | D6
2015 | CY30007 |  | 0 | 0 | 0 | 225 | 16 | 16 | 2 | A06101-0014 | 0.0296 | 0.0147 | 0 |  |  |  | D6
2016 | CY30011 |  | 0 | 0 | 0 | 687 | 16 | 16 | 2 | A09002-0020 | 0.0304 |  | 0 |  |  |  | A9
2016 | CY30012 |  | 0 | 0 | 0 | 260 | 0 | 0 | 0 | A06101-0008 | 0.0104 |  | 0 |  |  |  | D2
2016 | CY30014 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A06101-0012 | 0.0045 |  | 0 |  |  |  | D6
2016 | CY90021 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A02002-0008 | 0.0127 |  | 0 |  |  |  | D5
2016 | CY90022 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A02001-0012 | 0.0154 | 0.005 | 0 |  |  |  | D6
2016 | CY90032 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A09001-0012 | 0.0032 |  | 0 |  |  |  | D6
| D26889-C | purchased | 0 | 0 | 0 | 388 | 16 | 16 | 2 | A02002-0018 | 0.1295 |  | 0 |  |  |  | D6
| D30198-C |  | 0 | 0 | 0 | 299 | 16 | 16 | 2 | A02002-0020 | 0.2875 |  | 0 |  |  |  | A7
| DA5001 |  | 0 | 0 | 0 | 325 | 16 | 16 | 2 | A02002-0028 | 0.1909 |  | 0 |  |  |  | #A2
| DA5002(1/2) |  | 0 | 0 | 0 | 257 | 24 | 24 | 3 | A02001-0018 | 0.076 |  | 0 |  |  |  | A9
| DC1202 |  | 0 | 0 | 0 | 425 | 16 | 16 | 2 | A02001-0013 | 0.0414 |  | 0 |  |  |  | #D1
F50 | DM1201 | new part | 0 | 0 | 0 | 401 | 16 | 16 | 2 | A02002-0020 | 0.1574 | 0.038 | 0 | 2017 |  |  | A9
F50 | DM1203 | Stnd | 0 | 0 | 0 | 401 | 16 | 16 | 2 | A02002-0020 | 0.1574 | 0.044 | 0 | 2018 |  |  | A9
F50 | DM2501 | STND | 0 | 0 | 0 | 401 | 16 | 16 | 2 | A02002-0020 | 0.1574 |  | 0 |  |  |  | A9
2015 | DM2202 | Stnd | 0 | 0 | 0 | 276 | 16 | 16 | 2 | A02002-0034 | 0.5111 | 0.17 | 0 |  |  |  | A7
| DM2501 | NON STND | 0 | 0 | 0 | 391 | 16 | 16 | 2 | A02002-0020 | 0.1586 |  | 0 |  |  |  | A1
| DM2504 | NON STND | 0 | 0 | 0 | 617 | 16 | 16 | 2 | A02001-0020 | 0.0281 | 0.0068 | 0 |  |  |  | A1
| DM2504 | STND | 0 | 0 | 0 | 956 | 16 | 16 | 2 | A02001-0020 | 0.0279 | 0.0068 | 0 |  |  |  | A9
| DM2513 | STND | 0 | 0 | 0 | 823 | 16 | 16 | 2 | A02001-0018 | 0.0284 | 0.0265 | 0 |  |  |  | D6
| DM2514 | STND | 0 | 0 | 0 | 503 | 16 | 16 | 2 | A02001-0012 | 0.0364 | 0.00856 | 0 |  |  |  | D3
| DP2501 | STND | 0 | 0 | 0 | 405 | 16 | 16 | 2 | A02002-0018 | 0.0772 | 0.0254 | 0 |  |  |  | D8/D6
| DP2501 | NON STND | 0 | 0 | 0 | 648 | 16 | 16 | 2 | A02002-0018 | 0.0799 | 0.0254 | 0 |  |  |  | A9
| DP2505 |  | 0 | 0 | 0 | 995 | 16 | 16 | 2 | A02001-0016 | 0.0083 | 0.00192 | 0 |  |  |  | D6
| DP2509 |  | 0 | 0 | 0 | 1095 | 16 | 16 | 2 | A02001-0013 | 0.0254 | 0.005 | 0 |  |  |  | D1
F30 | DU2510 |  | 0 | 0 | 0 | 544 | 16 | 16 | 2 | A02002-0018 | 0.0789 | 0.02916 | 0 |  |  |  | #D6
F31 | DU2511 |  | 0 | 0 | 0 | 310 | 16 | 16 | 2 | A02001-0013 | 0.0537 | 0.01769 | 0 |  |  |  | D1
F30 | DW2501 |  | 0 | 0 | 0 | 554 | 16 | 16 | 2 | A02007-0018 | 0.0733 |  | 0 |  |  |  | D6
F31 | DW2502 |  | 0 | 0 | 0 | 506 | 16 | 16 | 2 | A02001-0013 | 0.0493 |  | 0 |  |  |  | D1
2013 | E5009 |  | 0 | 0 | 0 | 572 | 16 | 16 | 2 | A02001-0018 | 0.0599 |  | 0 |  |  |  | D6
2014 | E5011(1/2) | purchased | 0 | 0 | 0 | 151 | 16 | 16 | 2 | A09001-0022 | 0.084 |  | 0 |  |  |  | A11
2014 | ESV3821 |  | 0 | 0 | 0 | 565 | 16 | 16 | 2 | A06101-0012 | 0.0089 | 0.0017 | 0 |  |  |  | D6
2013 | ELM385001(1/2) |  | 0 | 0 | 0 | 349 | 16 | 16 | 2 | A02002-0028 | 0.3224 |  | 0 |  |  |  | A1
| ESV3820(1/2) |  | 0 | 0 | 0 | 335 | 16 | 16 | 2 | A02002-0024 | 0.2848 |  | 0 |  |  |  | A2
| ESV3830 |  | 0 | 0 | 0 | 274 | 16 | 16 | 2 | A02002-0022 | 0.2514 |  | 0 |  |  |  | #A2 | A2 Only
| F504W | obsolete | 0 | 0 | 0 | 307 | 16 | 16 | 2 | A02002-0028 | 0.2853 |  | 0 | obsolete |  |  | A7
| F6250B21(1/3) |  | 0 | 0 | 0 | 293 | 16 | 16 | 2 | A02002-0032 | 0.9114 |  | 0 |  |  |  | A7
| F6250B72-P(1/3) |  | 0 | 0 | 0 | 228 | 16 | 16 | 2 | A01002-0030 | 0.7953 |  | 0 |  |  |  | A7
| F6424-C |  | 0 | 0 | 0 | 512 | 16 | 16 | 2 | A02001-0016 | 0.0067 |  | 0 |  |  |  | D2
| FC2504 |  | 0 | 0 | 0 | 475 | 16 | 16 | 2 | A02002-0034 | 0.1902 |  | 0 |  |  |  | A7
| FC2508 |  | 0 | 0 | 0 | 705 | 16 | 16 | 2 | A02001-0024 | 0.0473 | 0.00677 | 0 |  |  |  | A9
2013 | FC2509 |  | 0 | 0 | 0 | 1331 | 16 | 16 | 2 | A02002-0016 | 0.0166 |  | 0 | Jam Nut |  |  | D6
| FC2515 | stnd | 0 | 0 | 0 | 642 | 16 | 16 | 2 | A02002-0024 | 0.0473 | 0.103 | 0 | Jam Nut |  |  | A2
| FC2574 |  | 0 | 0 | 0 | 167 | 16 | 16 | 2 | A02002-0032 | 0.5193 |  | 0 |  |  |  | A7
Family 4 | FC7504(1/2) |  | 0 | 0 | 0 | 228 | 16 | 16 | 2 | A02002-0052 | 1.0722 | 0.35 | 0 |  |  |  | A7
2014 | FC7508 |  | 0 | 0 | 0 | 637 | 16 | 16 | 2 | A02001-0036 | 0.137 |  | 0 |  |  |  | A2
Family 4 | FC7514 |  | 0 | 0 | 0 | 199 | 8 | 8 | 1 | A02002-0052 | 0.9014 | 0.269 | 0 |  |  |  | A7
| FC7515 |  | 0 | 0 | 0 | 638 | 16 | 16 | 2 | A02002-0028 | 0.0711 |  | 0 |  |  |  | A2
2014 | FS01 |  | 0 | 0 | 0 | 361 | 16 | 16 | 2 | A01005-0016 | 0.077 | 0.02314 | 0 |  |  |  | D6
2013/14 | FS12-(1/2) |  | 0 | 0 | 0 | 300 | 16 | 16 | 2 | A01005-0024 | 0.2121 |  | 0 | 2013 |  |  | A8 ONLY | A8 Only
2014 | FS14 |  | 0 | 0 | 0 | 317 | 16 | 16 | 2 | A01001-0016 | 0.0746 |  | 0 |  |  |  | D6
2013 | FS18 |  | 0 | 0 | 0 | 486 | 16 | 16 | 2 | A01002-0020 | 0.0466 | 0.0207 | 0 | 2013 |  |  | A9
2013 | FS22-10(1/2) |  | 0 | 0 | 0 | 477 | 16 | 16 | 2 | A01002-0020 | 0.1507 |  | 0 | 2013 |  |  | A9
| FT10001 |  | 0 | 0 | 0 | 268 | 16 | 16 | 2 | A02002-0032 | 0.2893 |  | 0 |  |  |  | A1
| FT10002 |  | 0 | 0 | 0 | 383 | 16 | 16 | 2 | A02002-0038 | 0.3381 | 0.0836 | 0 |  |  |  | A7
| FT10006 |  | 0 | 0 | 0 | 404 | 16 | 16 | 2 | A02001-0032 | 0.2684 | 0.0689 | 0 |  |  |  | A1
| FT10101(1/2) |  | 0 | 0 | 0 | 321 | 16 | 16 | 2 | A02002-0032 | 0.727 |  | 0 |  |  |  | A7
| FT10501(1/2) |  | 0 | 0 | 0 | 335 | 16 | 16 | 2 | A02002-0036 | 0.7078 | 0.33625 | 0 |  |  |  | A7
| FT10701 |  | 0 | 0 | 0 | 268 | 16 | 16 | 2 | A02002-0032 | 0.2893 |  | 0 |  |  |  | A2
F66 | FT10802 |  | 0 | 0 | 0 | 379 | 16 | 16 | 2 | A02001-0036 | 0.2498 |  | 0 |  |  |  | A2
F66 | FT10802-1 |  | 0 | 0 | 0 | 360 | 4 | 4 | 1 | A02001-0036 | 0.2864 |  | 0 |  |  |  | A2
F66 | FT10802-2 |  | 0 | 0 | 0 | 360 | 4 | 4 | 1 | A02001-0036 | 0.2864 |  | 0 |  |  |  | A2
| FT10902 |  | 0 | 0 | 0 | 231 | 16 | 16 | 2 | A01002-0026 | 0.3013 |  | 0 |  |  |  | A2
2014 | FT11401-0 |  | 0 | 0 | 0 | 421 | 4 | 4 | 1 | A02002-0022 | 0.2282 | 0.043 | 0 |  |  |  | A2
2014 | FT11401-3(1/2) |  | 0 | 0 | 0 | 421 | 4 | 4 | 1 | A02002-0022 | 0.2282 |  | 0 |  |  |  | A2
2014 | FT11401-4(1/2) |  | 0 | 0 | 0 | 421 | 4 | 4 | 1 | A02002-0022 | 0.2282 |  | 0 |  |  |  | A2
F71/2014 | FT12001 |  | 0 | 0 | 0 | 291 | 32 | 32 | 4 | A01001-0020 | 0.2187 |  | 0 |  |  |  | A11
F71/2014 | FT12101 |  | 0 | 0 | 0 | 293 | 16 | 16 | 2 | A01001-0020 | 0.21 |  | 0 |  |  |  | A11
| FT12401 | Stnd | 0 | 0 | 0 | 472 | 16 | 16 | 2 | A02001-0032 | 0.2629 | 0.06545 | 0 |  |  |  | A2
| FT13401(1/2) | STND | 0 | 0 | 0 | 374 | 16 | 16 | 2 | A02002-0024 | 0.2409 |  | 0 | 2013 |  |  | A2
| FT13401(1/2) | NON STND | 0 | 0 | 0 | 403 | 16 | 16 | 2 | A02002-0024 | 0.2392 |  | 0 |  |  |  | A9
2014 | FT13501(1/2) |  | 0 | 0 | 0 | 680 | 16 | 16 | 2 | A02001-0010 | 0.0193 |  | 0 |  |  |  | D3
| FT13501 |  | 0 | 0 | 0 | 60 | 4 | 4 | 1 | FT13501-10 | 1 |  | 0 |  |  |  | DRILL
F10 | G200-17 | STND | 0 | 0 | 0 | 680 | 16 | 16 | 2 | A02001-0010 | 0.0331 |  | 0 | 2016 |  |  | D5
F11 | G50-12 |  | 0 | 0 | 0 | 500 | 4 | 4 | 1 | A02002-0036 | 0.1414 |  | 0 | 2017 |  |  | A7
F11 | G50-12SS |  | 0 | 0 | 0 | 100 | 4 | 4 | 1 | A06202-0036 | 0.1492 |  | 0 | 2017 |  |  | A7
F10 | G50-17 |  | 0 | 0 | 0 | 615 | 16 | 16 | 2 | A02001-0008 | 0.0172 | 0.013 | 0 | 2016 |  |  | D5
F10 | G50-17SS | STND | 0 | 0 | 0 | 184 | 16 | 16 | 2 | A06201-0008 | 0.0163 | 0.013 | 0 | 2016 |  |  | D5
| GA750-C |  | 0 | 0 | 0 | 391 | 16 | 16 | 2 | A09001-0024 | 0.033 |  | 0 |  |  |  | A2
2016 | GA875-C |  | 0 | 0 | 0 | 378 | 16 | 16 | 2 | A09001-0028 | 0.045 | 0.012 | 0 |  |  |  | A2
| IC75001-20 |  | 0 | 0 | 0 | 251 | 16 | 16 | 2 | A02002-0038 | 1.0921 |  | 0 |  |  |  | A7
2014 | IF6275B30 |  | 0 | 0 | 0 | 620 | 16 | 16 | 2 | A02001-0028 | 0.0732 | 0.0107 | 0 |  |  |  | A9
F33 | IL10014 |  | 0 | 0 | 0 | 358 | 16 | 16 | 2 | A19102-0056 | 0.1961 |  | 0 |  |  |  | A5
F33 | IL20014(1/2) |  | 0 | 0 | 0 | 236 | 8 | 8 | 1 | A19102-0056 | 0.4772 | 0.3403 | 0 |  |  |  | A5
2016 | L1/2 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L1-1/2 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L3/4 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L1 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2017 | L1/3 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L2 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L2-1/2 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L3 |  | 0 | 0 | 0 | 585 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L3/4 |  | 0 | 0 | 0 | 623 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L4 |  | 0 | 0 | 0 | 623 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2016 | L6 |  | 0 | 0 | 0 | 623 | 8 | 8 | 1 | A02001-0013 | 0.0112 |  | 0 |  |  |  | D1
2013 | LH50004 |  | 0 | 0 | 0 | 686 | 16 | 16 | 2 | A19101-0022 | 0.0323 | 0.00985 | 0 | 2013 |  |  | D6
2013 | LH50005 |  | 0 | 0 | 0 | 865 | 16 | 16 | 2 | A19101-0008 | 0.0007 |  | 0 | 2013 |  |  | D6
2013 | LH50010 |  | 0 | 0 | 0 | 501 | 16 | 16 | 2 | A19101-0012 | 0.012 | 0.0041 | 0 | 2013 |  |  | D3
2013 | LH50011(1/2) |  | 0 | 0 | 0 | 395 | 16 | 16 | 2 | A19201-0010 | 0.011 | 0.00213 | 0 | 2013 |  |  | D6
| LH50027 |  | 0 | 0 | 0 | 505 | 16 | 16 | 2 | A09001-0020 | 0.0469 |  | 0 |  |  |  | A9
2015 | M1212001 |  | 0 | 0 | 0 | 336 | 16 | 16 | 2 | A02005-0022 | 0.153 | 0.04615 | 0 |  |  |  | D6
2015 | M1212003 |  | 0 | 0 | 0 | 383 | 16 | 16 | 2 | A02002-0022 | 0.1349 |  | 0 |  |  |  | D6
| M20005 |  | 0 | 0 | 0 | 448 | 16 | 16 | 2 | A02002-0018 | 0.1004 |  | 0 |  |  |  | D6
| M20011 | stnd | 0 | 0 | 0 | 1060 | 16 | 16 | 2 | A02002-0020 | 0.022 | 0.0052 | 0 | Jam Nut |  |  | D6
| M20011 | NON STND | 0 | 0 | 0 | 578 | 16 | 16 | 2 | A02002-0020 | 0.022 | 0.0052 | 0 | Jam Nut |  |  | A3
| M20017 | STND | 0 | 0 | 0 | 639 | 16 | 16 | 2 | A02002-0028 | 0.0497 | 0.0107 | 0 | 2013 |  |  | A9
| M20017 | NON STND | 0 | 0 | 0 | 639 | 16 | 16 | 2 | A02002-0028 | 0.05 | 0.0107 | 0 | Jam Nut |  |  | A1
| M20045 |  | 0 | 0 | 0 | 432 | 16 | 16 | 2 | A02002-0040 | 0.4103 |  | 0 |  |  |  | A7
| M20055 |  | 0 | 0 | 0 | 982 | 16 | 16 | 2 | A02001-0010 | 0.0119 |  | 0 |  |  |  | D6
| M20058 |  | 0 |  | 0 | [7 empty] | 0
| M20065 |  | 0 | 0 | 0 | 519 | 16 | 16 | 2 | A02001-0016 | 0.0553 | 0.02712 | 0 |  |  |  | #D4
| M20066-10 |  | 0 | 0 | 0 | 385 | 16 | 16 | 2 | A02001-0022 | 0.1756 |  | 0 |  |  |  | #D6
| M2525050 |  | 0 | 0 | 0 | 271 | 16 | 16 | 2 | A02002-0018 | 0.1832 |  | 0 |  |  |  | A2
| M2525081(1/2) |  | 0 | 0 | 0 | 258 | 16 | 16 | 2 | A02002-0024 | 0.2694 |  | 0 |  |  |  | A2
| M2525091 | new part | 0 | 0 | 0 | 540 | 16 | 16 | 2 | A02002-0020 | 0.1119 | 0.041 | 0 |  |  |  | A8
| M2525083-0 |  | 0 | 0 | 0 | 563 | 16 | 16 | 2 | A02001-0013 | 0.0235 |  | 0 |  |  |  | D6
2014 | M30003 |  | 0 | 0 | 0 | 317 | 16 | 16 | 2 | A02001-0008 | 0.0318 |  | 0 |  |  |  | D4
| M30005 |  | 0 | 0 | 0 | 490 | 16 | 16 | 2 | A02002-0018 | 0.0773 | 0.01712 | 0 |  |  |  | #D6
| M30009 |  | 0 | 0 | 0 | 15 | 16 | 16 | 2 | A02001-0016 | 0.0813 |  | 0 |  |  |  | A7
2014 | M30011 |  | 0 | 0 | 0 | 852 | 16 | 16 | 2 | A02002-0016 | 0.0166 |  | 0 |  |  |  | D6
2013 | M30017 | STND | 0 | 0 | 0 | 862 | 16 | 16 | 2 | A02002-0024 | 0.0421 | 0.01354 | 0 | 2013 | jam nut |  | A9
| M30017 | NON STND | 0 | 0 | 0 | 747 | 16 | 16 | 2 | A02002-0024 | 0.0424 | 0.01354 | 0 |  | jam nut |  | A1
| M30017 | NON STND 2" | 0 | 0 | 0 | 589 | 16 | 16 | 2 | A02002-0024 | 0.0427 | 0.0135 | 0 |  |  |  | A5
F13 | M30029-P |  | 0 | 0 | 0 | 261 | 16 | 16 | 2 | A01001-0016 | 0.0866 |  | 0 |  | change to 333/hr |  | D6
F13 | M30030-P |  | 0 | 0 | 0 | 580 | 16 | 16 | 2 | A01001-0016 | 0.0229 |  | 0 |  |  |  | D6
F88 | M30045 |  | 0 | 0 | 0 | 539 | 16 | 16 | 2 | A02001-0024 | 0.0688 | 0.0193 | 0 |  |  |  | A2
F88 | M31045 |  | 0 | 0 | 0 | 539 | 16 | 16 | 2 | A09001-0024 | 0.0205 | 0.006 | 0 |  |  |  | A2
F75-2014 | M20059 |  | 0 |  | 0 | 449 | 16 | 16 | 2 | A09201-0012 | 0.0141 |  | 0 | 2013 |  |  | D3
F75 | M30059 |  | 0 | 0 | 0 | 463 | 16 | 16 | 2 | A09201-0012 | 0.0127 |  | 0 | 2013 |  |  | D3
| M30072 | STND | 0 | 0 | 0 | 378 | 16 | 16 | 2 | A02002-0032 | 0.3704 |  | 0 |  | A2/ 414 pcs/ hr |  | A7
| M30072 | NON STND | 0 | 0 | 0 | 432 | 16 | 16 | 2 | A02002-0032 | 0.3677 |  | 0 |  |  |  | A2
| M30073 |  | 0 | 0 | 0 | 338 | 16 | 16 | 2 | A02002-0032 | 0.4107 | 0.154 | 0 |  |  |  | A7
| M30076 |  | 0 | 0 | 0 | 327 | 16 | 16 | 2 | A02002-0032 | 0.2946 |  | 0 |  |  |  | A7
| M30088 |  | 0 | 0 | 0 | 307 | 16 | 16 | 2 | A02002-0032 | 0.4386 |  | 0 |  |  |  | A7
2016 | M30090 |  | 0 | 0 | 0 | 253 | 16 | 16 | 2 | A02002-0032 | 0.4406 | 0.1516 | 0 |  |  |  | A6
2016 | M30092 |  | 0 | 0 | 0 | 374 | 16 | 16 | 2 | A02002-0038 | 0.2456 |  | 0 |  |  |  | A6
2017 | M31029 |  | 0 | 0 | 0 | 261 | 16 | 16 | 2 | A01001-0016 | 0.0866 | 0.0264 | 0 |  |  |  | D6
2017 | M31078 |  | 0 | 0 | 0 | 338 | 16 | 16 | 2 | A02002-0032 | 0.2717 | 0.111 | 0 |  |  |  | A7
| M40011 |  | 0 | 0 | 0 | 667 | 16 | 16 | 2 | A02001-0022 | 0.0878 | 0.0258 | 0 |  |  |  | D6
2018 | M30075 |  | 0 | 0 | 0 | 476 | 16 | 16 | 2 | A02002-0032 | 0.3594 | 0.148 | 0 |  |  |  | A7
2014 | M40070(1/2) |  | 0 | 0 | 0 | 359 | 16 | 16 | 2 | A02002-0032 | 0.3715 | 0.1246 | 0 |  |  |  | A7
| M40071 |  | 0 | 0 | 0 | 365 | 16 | 16 | 2 | A02002-0032 | 0.4176 | 0.1109 | 0 |  |  |  | A7
| MPC20003 |  | 0 | 0 | 0 | 443 | 16 | 16 | 2 | A19002-0028 | 0.0339 |  | 0 |  |  |  | A7
| MPC40001(1/2) | CNC | 0 | 0 | 0 | 154 | 16 | 16 | 2 | A02001-0042 | 1.3214 |  | 0 |  |  |  | A7
| ND3809 |  | 0 | 0 | 0 | 530 | 16 | 16 | 2 | A02001-0013 | 0.0399 |  | 0 |  |  |  | D1
| ND6215(1/2) |  | 0 | 0 | 0 | 933 | 16 | 16 | 2 | A02001-0014 | 0.0233 |  | 0 |  |  |  | #D6
2014 | NC2505 |  | 0 | 0 | 0 | 1199 | 16 | 16 | 2 | A02001-0016 | 0.0184 | 0.00324 | 0 |  |  |  | D6
| NK2501 | STND | 0 | 0 | 0 | 463 | 16 | 16 | 2 | A02002-0020 | 0.1231 | 0.03292 | 0 |  |  |  | A8 only
| NK2501 | NON STND | 0 | 0 | 0 | 465 | 16 | 16 | 2 | A02002-0020 | 0.1205 | 0.03292 | 0 |  |  |  | A2
| NK2509 |  | 0 | 0 | 0 | 773 | 16 | 16 | 2 | A02001-0013 | 0.0388 | 0.01026 | 0 |  |  |  | #D1
F88 | NK2515 |  | 0 | 0 | 0 | 601 | 16 | 16 | 2 | A02001-0018 | 0.0233 | 0.0084 | 0 |  |  |  | D3
F21 | NK5001 |  | 0 | 0 | 0 | 346 | 16 | 16 | 2 | A02002-0028 | 0.2295 |  | 0 |  |  |  | A7
F21 | NK5020 | STND | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02002-0030 | 0.2635 |  | 0 |  |  |  | #A7
| NK5020 | NON STND | 0 | 0 | 0 | 344 | 16 | 16 | 2 | A02002-0030 | 0.2536 |  | 0 |  |  |  | A1
A9 only | NL2503 |  | 0 | 0 | 0 | 543 | 16 | 16 | 2 | A02002-0018 | 0.0808 | 0.02592 | 0 |  |  |  | A9
| NL2511 |  | 0 | 0 | 0 | 765 | 16 | 16 | 2 | A02001-0008 | 0.0132 | 0.0024 | 0 |  |  |  | D6
F88 | NL2515 |  | 0 | 0 | 0 | 958 | 16 | 16 | 2 | A02001-0014 | 0.019 | 0.005 | 0 |  |  |  | D3
| NN38B21(1/3) |  | 0 | 0 | 0 | 404 | 16 | 16 | 2 | A02001-0022 | 0.1817 | 0.0549 | 0 |  |  |  | A2
2014 | NP3005 |  | 0 | 0 | 0 | 1060 | 16 | 16 | 2 | A02002-0020 | 0.0171 |  | 0 | jam nut |  |  | D6
| P1010001(1/4) |  | 0 | 0 | 0 | 166 | 16 | 16 | 2 | A02002-0048 | 2.7867 |  | 0 |  |  |  | A7
| P1212005 |  | 0 | 0 | 0 | 360 | 16 | 16 | 2 | A02001-0038 | 0.3577 |  | 0 |  |  |  | A7
| P2575B21(1/4) |  | 0 | 0 | 0 | 374 | 16 | 16 | 2 | A02002-0036 | 0.7571 |  | 0 |  |  |  | A7
| P3850001(1/4) |  | 0 | 0 | 0 | 267 | 16 | 16 | 2 | A02002-0028 | 0.6352 |  | 0 |  |  |  | A7
| P3850B21(1/4) |  | 0 | 0 | 0 | 289 | 16 | 16 | 2 | A02002-0028 | 0.5341 |  | 0 |  |  |  | A5
| P5050001(1/4) |  | 0 | 0 | 0 | 190 | 16 | 16 | 2 | A02002-0032 | 0.898 |  | 0 |  |  |  | A5
| P5050B21(1/4) |  | 0 | 0 | 0 | 326 | 16 | 16 | 2 | A02002-0032 | 0.8096 |  | 0 |  |  |  | A5
Ganesh | P7510001(1/4) |  | 0 | 0 | 0 | 183 | 16 | 16 | 2 | A02002-0042 | 1.9194 |  | 0 |  |  |  | A5
| P7575001(1/4) |  | 0 | 0 | 0 | 154 | 16 | 16 | 2 | A02002-0038 | 1.455 |  | 0 |  |  |  | A5
| P7575002(1/4) |  | 0 | 0 | 0 | 154 | 16 | 16 | 2 | A02002-0038 | 1.455 |  | 0 |  |  |  | A5
| P7575030(1/4) |  | 0 | 0 | 0 | 154 | 16 | 16 | 2 | A02002-0038 | 1.455 |  | 0 |  |  |  | A5
F44 | P7575B31(1/4) |  | 0 | 0 | 0 | 280 | 16 | 16 | 2 | A02002-0038 | 1.2 |  | 0 |  |  |  | A5
F44 | P7575B71-P(1/4) |  | 0 | 0 | 0 | 185 | 16 | 16 | 2 | A01002-0038 | 1.0852 |  | 0 |  |  |  | A5
| PJ-P032-C |  | 0 | 0 | 0 | 412 | 16 | 16 | 2 | A06031-0016 | 0.0591 |  | 0 |  |  |  | #D5
2018 | PCV10002 (1/2) | Larry Hawkins | 0 | 0 | 0 | 22 | 16 | 16 | 2 | A06101-0042 | 0.4822 | 0.4 | 0 |  |  |  | A5
2018 | PCV10009 |  | 0 | 0 | 0 | 101 | 16 | 16 | 2 | A01001-0034 | 0.0567 |  | 0 |  |  |  | A2
2015 | PPV10002 |  | 0 | 0 | 0 | 367 | 16 | 16 | 2 | A02001-0026 | 0.265 | 0.8175 | 0 |  |  |  | A2
2015 | PPV10003(1/2) |  | 0 | 0 | 0 | 316 | 16 | 16 | 2 | A02002-0036 | 0.4702 | 0.1207 | 0 |  |  |  | A5
F99 | PR2561 |  | 0 | 0 | 0 | 241 | 16 | 16 | 2 | A02002-0018 | 0.1492 |  | 0 |  |  |  | A9
| PR7602 |  | 0 | 0 | 0 | 623 | 16 | 16 | 2 | A02001-0013 | 0.053 | 0.01501 | 0 |  |  |  | #D1
or S5 | PWN00100-B | STND | 0 | 0 | 0 | 431 | 16 | 16 | 2 | A02001-0016 | 0.0775 |  | 0 |  |  |  | D3
or S5 | PWN00400-B | STND | 0 | 0 | 0 | 431 | 16 | 16 | 2 | A02001-0016 | 0.0775 |  | 0 |  |  |  | #D6
| PWN2005 |  | 0 | 0 | 0 | 235 | 16 | 16 | 2 | A02001-0020 | 0.259 | 0.0624 | 0 |  |  |  | A2
| PWN2025 |  | 0 | 0 | 0 | 229 | 16 | 16 | 2 | A09001-0020 | 0.0723 | 0.0164 | 0 |  |  |  | A2
| PWN2020 |  | 0 | 0 | 0 | 434 | 16 | 16 | 2 | A02001-0032 | 0.1963 | 0.0519 | 0 |  |  |  | A2
| PWN2020-1 |  | 0 | 0 | 0 | 491 | 16 | 16 | 2 | A02001-0032 | 0.1963 | 0.0519 | 0 |  |  |  | A2
| PWN2028-B |  | 0 | 0 | 0 | 464 | 16 | 16 | 2 | A02001-0016 | 0.0796 |  | 0 |  |  |  | D4
2013 | PWN4004 |  | 0 | 0 | 0 | 269 | 16 | 16 | 2 | A02001-0018 | 0.0531 |  | 0 |  |  |  | D6
2014 | PWN4016A |  | 0 | 0 | 0 | 840 | 16 | 16 | 2 | A02061-0008 | 0.0086 |  | 0 |  |  |  | D5
2014 | PWN4016 |  | 0 | 0 | 0 | 840 | 8 | 8 | 1 | A02061-0008 | 0.0086 |  | 0 |  |  |  | D5
F38 | PWN65400 |  | 0 | 0 | 0 | 462 | 16 | 16 | 2 | A02001-0016 | 0.079 |  | 0 |  |  |  | D5
F38 | PWN65400-A |  | 0 | 0 | 0 | 462 | 16 | 16 | 2 | A09301-0016 | 0.0258 |  | 0 |  |  |  | D5
2013 | PWR1201 |  | 0 | 0 | 0 | 256 | 16 | 16 | 2 | A02002-0024 | 0.2056 |  | 0 |  |  |  | A2
2017 | RCF004 |  | 0 | 0 | 0 | 738 | 16 | 16 | 2 | A02002-0016 | 0.0454 | 0.019 | 0 |  |  |  | D6
2017 | RCF005 |  | 0 | 0 | 0 | 692 | 16 | 16 | 2 | A02001-0010 | 0.025 | 0.00795 | 0 |  |  |  | D6
2017 | RCF006 |  | 0 | 0 | 0 | 463 | 16 | 16 | 2 | A19101-0024 | 0.0285 | 0.02 | 0 |  |  |  | A8
2017 | RCF007 |  | 0 | 0 | 0 | 554 | 16 | 16 | 2 | A02001-0010 | 0.0194 | 0.007 | 0 |  |  |  | D5
2018 | RCF103 |  | 0 | 0 | 0 | 400 | 16 | 16 | 2 | A02001-0016 | 0.0526 | 0.0076 | 0 |  |  |  | D6
2018 | RCF104 |  | 0 | 0 | 0 | 900 | 16 | 16 | 2 | A19101-0022 | 0.045 | 0.002 | 0 |  |  |  | D6
2018 | RCF216 |  | 0 | 0 | 0 | 463 | 16 | 16 | 2 | A19101-0022 | 0.029 | 0.01 | 0 |  |  |  | D6
2018 | RCF304 |  | 0 | 0 | 0 | 277 | 16 | 16 | 2 | A06202-0016 | 0.0432 | 0.02 | 0 |  |  |  | D6
2018 | RCF305 |  | 0 | 0 | 0 | 257 | 16 | 16 | 2 | A06201-0010 | 0.0244 | 0.01 | 0 |  |  |  | D6
2018 | RCF316 |  | 0 | 0 | 0 | 463 | 16 | 16 | 2 | A19101-0020 | 0.0239 | 0.0064 | 0 |  |  |  | A8
| R421-12BK |  | 0 | 0 | 0 | 586 | 16 | 16 | 2 | A02002-0038 | 0.1189 |  | 0 |  |  |  | A6
| R421-12BK-LF | STND | 0 | 0 | 0 | 240 | 16 | 16 | 2 | A03002-0038 | 0.1268 |  | 0 |  |  |  | A6
| R421-2-5BK |  | 0 | 0 | 0 | 240 | 16 | 16 | 2 | A02002-0020 | 0.0298 |  | 0 |  |  |  | SM
| R421-2BK |  | 0 | 0 | 0 | 240 | 16 | 16 | 2 | A02002-0018 | 0.0241 |  | 0 |  |  |  | SM
| R421-6BK |  | 0 | 0 | 0 | 645 | 16 | 16 | 2 | A02002-0026 | 0.0506 |  | 0 |  |  |  | A3
| R421-6BK-LF |  | 0 | 0 | 0 | 493 | 16 | 16 | 2 | A03002-0026 | 0.0565 |  | 0 |  |  |  | A3
| R421-8BK | STND | 0 | 0 | 0 | 458 | 16 | 16 | 2 | A02002-0032 | 0.0843 | 0.01838 | 0 |  |  |  | A3
| R421-8BK | NON STND | 0 | 0 | 0 | 458 | 16 | 16 | 2 | A02002-0032 | 0.094 | 0.01838 | 0 |  |  |  | A6
| R421-8BK-LF |  | 0 | 0 | 0 | 458 | 16 | 16 | 2 | A03002-0032 | 0.0843 | 0.01838 | 0 |  |  |  | A3
f20 | R434-0 |  | 0 | 0 | 0 | 647 | 16 | 16 | 2 | A02002-0022 | 0.1082 | 0.0638 | 0 |  |  |  | A3
f20 | R434-1 |  | 0 | 0 | 0 | 580 | 16 | 16 | 2 | A02002-0022 | 0.1082 | 0.05905 | 0 |  |  |  | A3
f20 | R434-3 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0028 | 0.1629 | 0.12 | 0 |  |  |  | A3
f20 | R434-11 |  | 0 | 0 | 0 | 647 | 16 | 16 | 2 | A02002-0022 | 0.1082 | 0.05192 | 0 |  |  |  | A3
f20 | R434-13 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0028 | 0.1629 | 0.10785 | 0 |  |  |  | A3
f20 | R434-15 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0034 | 0.3153 | 0.1577 | 0 |  |  |  | A3
f20 | R434-17 |  | 0 | 0 | 0 | 701 | 16 | 16 | 2 | A02002-0018 | 0.0657 | 0.03304 | 0 |  |  |  | A3
f20 | R434-5 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0034 | 0.3153 | 0.1545 | 0 |  |  |  | A3
f20 | R434-7 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0028 | 0.1629 | 0.1009 | 0 |  |  |  | A3
f20 | R434-9 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0034 | 0.3153 | 0.1542 | 0 |  |  |  | A3
f21 | R435-1 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0020 | 0.1179 |  | 0 |  |  |  | SM
f21 | R435-2 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0024 | 0.2131 |  | 0 |  |  |  | SM
f21 | R435-3 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0024 | 0.2318 |  | 0 |  |  |  | SM
f21 | R435-4 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0014 | 0.0613 |  | 0 |  |  |  | SM
f21 | R435-5 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0018 | 0.1048 |  | 0 |  |  |  | SM
f21 | R435-6 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0012 | 0.0367 |  | 0 |  |  |  | SM
f21 | R435-8 |  | 0 | 0 | 0 | 450 | 16 | 16 | 2 | A02002-0012 | 0.0309 |  | 0 |  |  |  | SM
| RMB003 |  | 0 | 0 | 0 | 1025 | 8 | 8 | 1 | A02001-0012 | 0.0039 |  | 0 |  |  |  | D6
| RP1200 |  | 0 | 0 | 0 | 369 | 16 | 16 | 2 | A02001-0044 | 0.3842 |  | 0 |  |  |  | A5
| RS191-2(1/2) |  | 0 | 0 | 0 | 147 | 16 | 16 | 2 | A06202-0012 | 0.0297 |  | 0 |  |  |  | A8
2014 | S119S119001(1/2) |  | 0 | 0 | 0 | 176 | 16 | 16 | 2 | A02002-0040 | 1.3152 |  | 0 |  |  |  | A7
2014 | S119S119002(1/2) |  | 0 | 0 | 0 | 266 | 16 | 16 | 2 | A02002-0040 | 0.7286 |  | 0 |  |  |  | A7
2014 | S119S119003(1/2) |  | 0 | 0 | 0 | 324 | 16 | 16 | 2 | A02001-0032 | 0.4157 |  | 0 |  |  |  | A2
2014 | S144S144001 |  | 0 | 0 | 0 | 75 | 16 | 16 | 2 | A02002-0056 | 2.9613 | 0.925 | 0 |  |  |  | A7
2014 | S144S144002(1/2) |  | 0 | 0 | 0 | 119 | 16 | 16 | 2 | A02002-0056 | 1.6852 |  | 0 |  |  |  | A7
2014 | S144S144003(1/2) |  | 0 | 0 | 0 | 243 | 16 | 16 | 2 | A02001-0046 | 1.0046 | 0.221 | 0 |  |  |  | A7
2014 | S169S169001(1/3) |  | 0 | 0 | 0 | 136 | 16 | 16 | 2 | A02002-0064 | 3.7336 |  | 0 |  |  |  | A12
2014 | S169S169002(1/3) |  | 0 | 0 | 0 | 146 | 16 | 16 | 2 | A02002-0064 | 2.281 |  | 0 |  |  |  | A12
2014 | S169S169003(1/2) |  | 0 | 0 | 0 | 221 | 16 | 16 | 2 | A02001-0052 | 1.4285 |  | 0 |  |  |  | A7
2014 | S20S20001(1/3) |  | 0 | 0 | 0 | 115 | 24 | 24 | 3 | A02002-0068 | 4.3031 |  | 0 |  |  |  | A12
2014 | S20S20002(1/3) |  | 0 | 0 | 0 | 123 | 24 | 24 | 3 | A02002-0068 | 2.3305 |  | 0 |  |  |  | A12
2014 | S20S20003(1/2) |  | 0 | 0 | 0 | 217 | 24 | 24 | 3 | A02001-0060 | 1.76 |  | 0 |  |  |  | A7
2015 | SA2511 |  | 0 | 0 | 0 | 359 | 16 | 16 | 2 | A02002-0034 | 0.319 |  | 0 |  |  |  | A7
F14-4 | SB2201(1/3) | tooling | 0 | 0 | 0 | 218 | 8 | 8 | 1 | A02042-0034 | 0.9831 |  | 0 |  |  |  | A7
F14-1 | SB5001(1/2) |  | 0 | 0 | 0 | 218 | 16 | 16 | 2 | A02042-0034 | 0.9831 | 0.245 | 0 |  |  |  | A7
F14-2 | SB5050(1/2) |  | 0 | 0 | 0 | 218 | 8 | 8 | 1 | A02042-0034 | 0.9831 | 0.24415 | 0 |  |  |  | A7
F14-3 | SB7501(1/2) |  | 0 | 0 | 0 | 218 | 16 | 16 | 2 | A02042-0034 | 0.9831 | 0.2445 | 0 |  |  |  | A7
| SB7505 |  | 0 | 0 | 0 | 363 | 16 | 16 | 2 | A02001-0038 | 0.4454 | 0.087 | 0 |  |  |  | A7
| SB7550(1/2) |  | 0 | 0 | 0 | 163 | 16 | 16 | 2 | A02042-0034 | 0.9934 | 0.2445 | 0 |  |  |  | A7
F3-1 (or 3) | SF5001(1/4) | hydromat | 0 | 0 | 0 | 273 | 16 | 16 | 2 | A02042-0028 | 0.5229 |  | 0 |  |  |  | A7
F3-2 | SF5002(1/4) | hydromat | 0 | 0 | 0 | 273 | 16 | 16 | 2 | A02042-0028 | 0.5229 |  | 0 |  |  |  | A7
F3-3 (or 1) | SF1601(1/4) | from cnc | 0 | 0 | 0 | 273 | 16 | 16 | 2 | A02042-0028 | 0.5229 |  | 0 |  |  |  | A7
F3-3 (or 1) | SF5051(1/3) |  | 0 | 0 | 0 | 273 | 16 | 16 | 2 | A02042-0028 | 0.5229 | 0.1878 | 0 | same as SF1601-20 |  |  | A7
| SF5005 |  | 0 | 0 | 0 | 707 | 16 | 16 | 2 | A02001-0022 | 0.0498 |  | 0 |  |  |  | D6
| SB7515(1/2) |  | 0 | 0 | 0 | 354 | 16 | 16 | 2 | A02001-0032 | 0.2655 |  | 0 |  |  |  | A1
| SF5015 | STND | 0 | 0 | 0 | 406 | 16 | 16 | 2 | A02001-0024 | 0.1457 | 0.0447 | 0 | 1"357 pc/ 1 1/4"388pc |  |  | A1
| SF5015 | NON STND | 0 | 0 | 0 | 443 | 16 | 16 | 2 | A02001-0024 | 0.1447 |  | 0 |  |  |  | A9
| SH2501(1/2) |  | 0 | 0 | 0 | 189 | 16 | 16 | 2 | A02002-0022 | 0.2627 |  | 0 |  |  |  | A2
F3-4 | SN5001(1/4) | hydromat | 0 | 0 | 0 | 267 | 8 | 8 | 1 | A02042-0028 | 0.5554 |  | 0 |  |  |  | A7
| SP2510 |  | 0 | 0 | 0 | 623 | 8 | 8 | 1 | A02001-0013 | 0.0373 | 0.008 | 0 |  |  |  | #D1
| SP2511 |  | 0 | 0 | 0 | 411 | 8 | 8 | 1 | A02001-0013 | 0.0479 | 0.008 | 0 | new rate |  |  | #D1
| SP2512 |  | 0 | 0 | 0 | 623 | 8 | 8 | 1 | A02001-0013 | 0.0373 | 0.005 | 0 |  |  |  | #D1
| SP2513 |  | 0 | 0 | 0 | 623 | 8 | 8 | 1 | A02001-0013 | 0.0373 | 0.005 | 0 |  |  |  | #D1
2016 | SP2515 |  | 0 | 0 | 0 | 623 | 8 | 8 | 1 | A02001-0013 | 0.0373 | 0.005 | 0
| ST1607 |  | 0 | 0 | 0 | 479 | 8 | 8 | 1 | A02001-0020 | 0.0774 |  | 0 |  |  |  | D5
| ST1609 |  | 0 | 0 | 0 | 342 | 14 | 14 | 2 | A02001-0018 | 0.0741 |  | 0 |  |  |  | D3
| ST1610 |  | 0 | 0 | 0 | 396 | 16 | 16 | 2 | A02001-0018 | 0.0741 |  | 0 |  |  |  | D3
prefer S3 | ST2A02 |  | 0 | 0 | 0 | 479 | 16 | 16 | 2 | A02001-0018 | 0.1328 |  | 0 |  |  |  | D3
new rate | ST2A03 |  | 0 | 0 | 0 | 397 | 16 | 16 | 2 | A02001-0020 | 0.0496 | 0.0142 | 0 |  |  |  | D9
| ST2A03-10 |  | 0 | 0 | 0 | 415 | 16 | 16 | 2 | A02001-0020 | 0.0501 | 0.0139 | 0
| ST2A07 |  | 0 | 0 | 0 | 535 | 16 | 16 | 2 | A02001-0020 | 0.0501 | 0.0179 | 0 |  |  |  | D9
| ST2A09 |  | 0 | 0 | 0 | 486 | 16 | 16 | 2 | A02001-0018 | 0.072 | 0.01058 | 0 |  |  |  | D3
| SV2A07(1/2) |  | 0 | 0 | 0 | 250 | 16 | 16 | 2 | A02001-0008 | 0.028 |  | 0 |  |  |  | A9
| SV2A15-1 |  | 0 | 0 | 0 | 472 | 16 | 16 | 2 | A02001-0020 | 0.09 |  | 0 |  |  |  | A2
| SV5A19 | STND | 0 | 0 | 0 | 422 | 16 | 16 | 2 | A02001-0028 | 0.1731 | 0.05404 | 0 |  |  |  | A9
| SV5A19 | NON STND | 0 | 0 | 0 | 381 | 16 | 16 | 2 | A02001-0028 | 0.1743 | 0.05404 | 0 |  |  |  | A2
| SW1005 |  | 0 | 0 | 0 | 227 | 16 | 16 | 2 | A02001-0060 | 1.9036 | 0.36912 | 0 |  |  |  | A5
| SW1009(1/2) |  | 0 | 0 | 0 | 201 | 16 | 16 | 2 | A02001-0024 | 0.5567 | 0.1562 | 0 |  |  |  | A1
| SW1010 |  | 0 | 0 | 0 | 293 | 16 | 16 | 2 | A02001-0042 | 0.4863 | 0.1334 | 0 |  |  |  | A7
| SW1015(1/2) |  | 0 | 0 | 0 | 191 | 16 | 16 | 2 | A02001-0044 | 0.7036 | 0.165 | 0 |  |  |  | A5
F15-1 | SW1001(1/4) |  | 0 | 0 | 0 | 170 | 16 | 16 | 2 | A02042-0052 | 2.6513 |  | 0 |  |  |  | A5
F15-2 | SW1050(1/4) |  | 0 | 0 | 0 | 140 | 8 | 8 | 1 | A02042-0052 | 2.6513 |  | 0 |  |  |  | A5
F15-4 | SW1201(1/4) |  | 0 | 0 | 0 | 140 | 8 | 8 | 1 | A02042-0052 | 2.6513 |  | 0 |  |  |  | A5
F15-3 | SW1250(1/4) |  | 0 | 0 | 0 | 140 | 8 | 8 | 1 | A02042-0056 | 2.6827 |  | 0 | we ran on CNC…..not sure this is correct |  |  | A5
F15-4 | SW3301(1/4) | Ganesh | 0 | 0 | 0 | 140 | 8 | 8 | 1 | A02042-0052 | 2.656 |  | 0 |  |  |  | A5
| TC0202(1/2) |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A02001-0020 | 0.1644 |  | 0 |  |  |  | A9-B&S
| TC0203 |  | 0 | 0 | 0 | 834 | 16 | 16 | 2 | A02001-0022 | 0.0397 |  | 0 |  |  |  | D6
| TC0207(1/2) |  | 0 | 0 | 0 | 480 | 16 | 16 | 2 | A02001-0020 | 0.1743 |  | 0 |  |  |  | A9
2013 | TC0213 |  | 0 | 0 | 0 | 715 | 16 | 16 | 2 | A02001-0006 | 0.007 |  | 0 |  |  |  | D3
| TC0214 |  | 0 | 0 | 0 | 885 | 16 | 16 | 2 | A02001-0020 | 0.0153 |  | 0 |  |  |  | D9
2014 | TC1206 |  | 0 | 0 | 0 | 632 | 16 | 16 | 2 | A02001-0020 | 0.0736 |  | 0 |  |  |  | D6
2015 | TC1210 |  | 0 | 0 | 0 | 634 | 16 | 16 | 2 | A02001-0016 | 0.0634 |  | 0 |  |  |  | D6
2014 | TC1266 |  | 0 | 0 | 0 | 565 | 16 | 16 | 2 | A02001-0026 | 0.1347 | 0.0302 | 0 |  |  |  | A9
2014 | TC1267 |  | 0 | 0 | 0 | 171 | 16 | 16 | 2 | A02001-0024 | 0.2155 | 0.044 | 0 |  |  |  | A8 Only
| TC1280(1/2) | Hydromat | 0 | 0 | 0 | 105 | 16 | 16 | 2 | A02002-0032 | 1.1008 |  | 0 |  |  |  | A5 Only
| TC1284(1/2) |  | 0 | 0 | 0 | 110 | 8 | 8 | 1 | A02002-0032 | 1.1008 |  | 0 |  |  |  | A5 Only
2014 | TC1602 | obsolete | 0 | 0 | 0 | 488 | 16 | 16 | 2 | A02001-0016 | 0.0605 |  | 0 |  |  |  | D6
2014 | TC1603 | obsolete | 0 | 0 | 0 | 363 | 16 | 16 | 2 | A02001-0018 | 0.1226 |  | 0 |  |  |  | D6
2014 | TC6301(1/2) |  | 0 | 0 | 0 | 288 | 16 | 16 | 2 | A02002-0022 | 0.2553 | 0.084 | 0 |  |  |  | A2 only
2014 | TC6303 |  | 0 | 0 | 0 | 1225 | 16 | 16 | 2 | A02001-0016 | 0.0159 | 0.006912 | 0 |  |  |  | D6
| TP30001 | STND | 0 | 0 | 0 | 512 | 16 | 16 | 2 | A02002-0018 | 0.0863 | 0.0356 | 0 | TP300-0A325 |  |  | A9
| TP30002 | STND | 0 | 0 | 0 | 440 | 16 | 16 | 2 | A02002-0022 | 0.1301 | 0.046 | 0 |  |  |  | A9
| TP30002 | NON STND | 0 | 0 | 0 | 428 | 16 | 16 | 2 | A02002-0022 | 0.131 | 0.046 | 0 | TP303-0A325 |  |  | A1
| TP30003 |  | 0 | 0 | 0 | 733 | 16 | 16 | 2 | A02001-0006 | 0.0074 | 0.0009 | 0 |  |  |  | D3
| TRV11 | STND | 0 | 0 | 0 | 879 | 16 | 16 | 2 | A02002-0014 | 0.0321 |  | 0 |  |  |  | D6
| TRV11 | NON STND | 0 |  | 0 | 808 | 16 | 16 | 2 | A02002-0014 | 0.0338
2013 | TRV1201 |  | 0 | 0 | 0 | 279 | 16 | 16 | 2 | A09002-0020 | 0.0659 | 0.017 | 0 |  |  |  | A10
| TRV15 |  | 0 | 0 | 0 | 922 | 16 | 16 | 2 | A02001-0013 | 0.0212 | 0.00444 | 0 |  |  |  | D6
| TRV2523 |  | 0 | 0 | 0 | 405 | 16 | 16 | 2 | A09002-0020 | 0.0575 | 0.017 | 0 |  |  |  | A10
| TRV2523 |  | 0 | 0 | 0 | 405 | 16 | 16 | 2 | A09002-0020 | 0.0575 | 0.017 | 0 |  |  |  | A10
| TRV2523 |  | 0 | 0 | 0 | 405 | 24 | 24 | 3 | A09002-0020 | 0.0575 | 0.017 | 0 |  |  |  | A11
| TRV2523-R |  | 0 | 0 | 0 | 405 | 24 | 24 | 3 | A09302-0020 | 0.0575 | 0.017 | 0 |  |  |  | A3
F88 | TRV3820 |  | 0 | 0 | 0 | 362 | 16 | 16 | 2 | A02002-0022 | 0.2194 |  | 0 |  |  |  | #A2
F88 | TRV3821 |  | 0 | 0 | 0 | 256 | 16 | 16 | 2 | A19102-0022 | 0.0697 |  | 0 |  |  |  | A10
F88 | TRV5020 |  | 0 | 0 | 0 | 324 | 16 | 16 | 2 | A02002-0028 | 0.3623 | 0.1377 | 0 |  |  |  | A2
F88 | TRV5021 | NON STND | 0 | 0 | 0 | 411 | 16 | 16 | 2 | A09002-0028 | 0.115 | [5 empty] | A9
F88 | TRV5021 | STND | 0 | 0 | 0 | 324 | 16 | 16 | 2 | A09002-0028 | 0.1159 |  | 0 |  |  |  | A2
F88 | TRV5026 |  | 0 | 0 | 0 | 359 | 16 | 16 | 2 | A02002-0028 | 0.3528 |  | 0 |  |  |  | A9
| ULV30003 |  | 0 | 0 | 0 | 510 | 16 | 16 | 2 | A02031-0016 | 0.0549 |  | 0 |  |  |  | A10
| ULV30004 |  | 0 | 0 | 0 | 423 | 16 | 16 | 2 | A02001-0024 | 0.1505 |  | 0 |  |  |  | A1
| VC10001(1/3) |  | 0 | 0 | 0 | 125 | 16 | 16 | 2 | A02002-0038 | 1.8518 |  | 0 |  |  |  | A5
| VC10071-P(1/3) | Hydromat | 0 | 0 | 0 | 101 | 16 | 16 | 2 | A01002-0038 | 1.678 |  | 0 |  |  |  | A5
F99 | VR2501 |  | 0 | 0 | 0 | 413 | 16 | 16 | 2 | A02002-0018 | 0.1121 | 0.04276 | 0 |  |  |  | A9
2016 | VR7501 |  | 0 | 0 | 0 | 336 | 16 | 16 | 2 | A02002-0034 | 0.5954 |  | 0 |  |  |  | A5
F6 | WP5008 |  | 0 | 0 | 0 | 309 | 16 | 16 | 2 | A02001-0034 | 0.5281 | 0.1438 | 0 |  |  |  | A7
PARTS IN PLANNING / OBSOLETE / OLD PURCHASED
| 101467-7 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0024 | 0.2479 |  | 0 |  | A15 |  | SM
| 101626-1 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0024 | 0.1767 |  | 0 |  | A15 |  | SM
| 101627-1 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0016 | 0.0374 |  | 0 |  | A15 |  | SM
| 102095-1 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | 102095-1U | 1 |  | 0 |  | A15 |  | SM
| 102525-1 |  |  | 0 |  | 500 | 16 | 16 | 2 | A02001-0010 | 0.0256 |  | 0 |  |  |  | SM
| 103464-6 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0018 | 0.0309 |  | 0 |  |  |  | A11
| 103772-1 |  |  | 0 |  | 360 | 16 | 16 | 2 | 103772U-1 | 1 |  | 0 |  |  |  | SM
| 103772-2 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0024 | 0.3097 |  | 0 |  | 2nd OP |  | SM
| 103772U-1 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0024 | 0.2887 |  | 0 |  | A15 |  | SM
| 103795-1 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0016 | 0.0191 |  | 0 |  |  |  | SM
| 103820-1 |  |  | 0 |  | 240 | 16 | 16 | 2 | A02002-0024 | 0.04111 |  | 0 |  |  |  | SM
| 104115-2 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0008 | 0.0121 |  | 0 |  | Dav |  | SM
| 105140-2 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | 105140-2U | 1 |  | 0 |  |  |  | SM
| 105991-4 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | 105991U-4 | 1 |  | 0 |  |  |  | SM
| 106272-4 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | 106273-2 | 1 |  | 0 |  | B&S |  | SM
| 106272-8 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | 106273-3 | 1 |  | 0 |  | B&S |  | SM
| 106272-9 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | 106273-3 | 1 |  | 0 |  | B&S |  | SM
106464
| 14-0248-C |  |  | 0 |  | 179 | 16 | 16 | 2 | A02001-0032 | 0.622 |  | 0 |  |  |  | A3
| 143303-01-C | OBSOLETE |  | 0 |  | 88 | 16 | 16 | 2 | A01102-0052 | 1.7975 |  | 0 |  |  |  | A5
| 17727- C |  |  | 0 |  | 304 | 16 | 16 | 2 | A02002-0036 | 0.5133 |  | 0
| 678090002 |  |  | 0 |  | 259 | 16 | 16 | 2 | A01002-0024 | 0.2968 |  | 0 |  |  |  | A2
| A3192-2 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02001-0016 | 0.0338 |  | 0 |  |  |  | SM
| A3558-2 |  |  | 0 |  | 42 | 16 | 16 | 2 | A06202-0014 | 0.0282 |  | 0 |  | B&S |  | B18
| A3558-3 |  |  | 0 |  | 42 | 16 | 16 | 2 | A06202-0014 | 0.0282 |  | 0 |  | B&S |  | SM
| A3938-1 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0022 | 0.0407 |  | 0 |  | Dav/Acme |  | SM
| A5186 |  |  | 0 |  | 0 | 16 | #DIV/0! | #DIV/0! | A02002-0028 | 0.3506 |  | 0 |  |  |  | SM
| C5038008 |  |  | 0 |  | 489 | 16 | 16 | 2 | A02002-0014 | 0.0436 |  | 0 |  |  |  | #D4 MUST
| CY10807 |  |  | 0 |  | 525 | 16 | 16 | 2 | A02032-0012 | 0.0253 |  | 0 |  |  |  | D3
| D22975-C |  |  | 0 |  | 297 | 16 | 16 | 2 | A02002-0028 | 0.301 |  | 0
| D28804-C |  |  | 0 |  | 490 | 16 | 16 | 2 | A02002-0018 | 0.0502 |  | 0 |  |  |  | #D4
| DC2501 |  |  | 0 |  | 501 | 16 | 16 | 2 | A02002-0018 | 0.0634 |  | 0 |  |  |  | D4
| DC2504 |  |  | 0 |  | 295 | 16 | 16 | 2 | A02001-0013 | 0.0502 |  | 0 |  |  |  | D1
| DC2512 |  |  | 0 |  | 416 | 16 | 16 | 2 | A02001-0013 | 0.0516 |  | 0 |  |  |  | D1
| DC5002-10 |  |  | 0 |  | 131 | 16 | 16 | 2 | A02001-0020 | 0.17911 |  | 0
| DT2501 |  |  | 0 |  | 458 | 16 | 16 | 2 | A02002-0018 | 0.0711 |  | 0 |  |  |  | #D4
| DT2502 |  |  | 0 |  | 488 | 16 | 16 | 2 | A02001-0014 | 0.0548 |  | 0 |  |  |  | #A3
| ESV2501 |  |  | 0 |  | 326 | 16 | 16 | 2 | A02002-0018 | 0.188 |  | 0
F66 | FT10802-3 |  |  | 0 |  | 360 | 4 | 4 | 1 | A02001-0036 | 0.2864 |  | 0 |  |  |  | A2
| H2099-C | OBSOLETE |  | 0 |  | 388 | 16 | 16 | 2 | A02002-0018 | 0.117 |  | 0 |  |  |  | A2
| IC50001-20 | [6 empty] | #DIV/0! | #DIV/0! |  |  |  | 0
| M20003 |  |  | 0
| M30070-0 |  |  | 0 |  | 270 | 16 | 16 | 2 | A02002-0032 | 0.4447 |  | 0 |  |  |  | A4
| M40092 |  |  | 0 |  | 329 | 16 | 16 | 2 | A02002-0034 | 0.4551 |  | 0 |  |  |  | #A7
| NK2201 |  |  | 0 |  | 280 | 16 | 16 | 2 | A02002-0034 | 0.3394 |  | 0 |  |  |  | #A4
| P5050001-10 |  |  | 0 |  | 133 | 4 | 4 | 1 | P5050001-20 | 1 |  | 0 |  |  |  | CHUCKER
| RS211-1 |  |  | 0 |  | 450 | 16 | 16 | 2 | A02002-0008 | 0.0076 |  | 0 |  |  |  | SM
| SA2510 |  |  | 0 |  | 320 | 16 | 16 | 2 | A02002-0028 | 0.2482 |  | 0 |  |  |  | A4
2013/f89 | TC0211-10 | hydro |  | 0 |  | 393 | 16 | 16 | 2 | A02001-0020 | 0.1804 |  | 0 |  |  |  | A9-B&S
2014/F89 | TC0216-20 |  |  | 0 |  | 203 | 16 | 16 | 2 | A02001-0020 | 0.2001 |  | 0 |  |  |  | A11
| TRV2520 |  |  | 0 |  | 400 | 16 | 16 | 2 | A02002-0020 | 0.1773 |  | 0 |  |  |  | #A9
| TRV5025 |  |  | 0 |  | 325 | 16 | 16 | 2 | A02002-0028 | 0.3677 |  | 0 |  |  |  | #A2
| ULV30004-1 |  |  | 0 |  | 423 | 16 | 16 | 2 | A02001-0024 | 0.1505 |  | 0 |  |  |  | #A3
| ULV30004-2 |  |  | 0 |  | 423 | 16 | 16 | 2 | A02001-0024 | 0.1505 |  | 0 |  |  |  | #A3
Formulas:
SCH'D = WORKDAY([SCH'D, row above],[days, row above])
Note on R19: Rob Douglas: We have -LF on hand if needed in emergency
Note on K20: Rob Douglas: 9/12
Note on K32: Rob Douglas: 9/7 Chase
Note on R32: Rob Douglas: was 10/25
Note on K43: Rob Douglas: 7/18 Chase
Note on K44: Rob Douglas: 7/18 Chase
Note on K53: Rob Douglas: 8/6 Chicago Extruded
Note on K54: Rob Douglas: 8/6 Chicago Extruded
Note on B56: Rob Douglas: Do Not Run on A7 OLD conveyor Reference 42412-10
Note on K63: Rob Douglas: 9/7
Note on R67: Rob Douglas: 10/1
Note on K74: Rob Douglas: 900# on hand 8/3 5k 8/22
Note on B76: Rob Douglas: Run with M30075
Note on B81: Rob Douglas: Run With M40070
Note on K100: Rob Douglas: 8/3 EMJ Rob Douglas: Balance 8/28
Note on R100: Rob Douglas: was 5/16
Note on K101: Rob Douglas: 2k 8/22 Chase Rob Douglas: 2k 9/12
Note on C114: Jessica Moma: Issued 8/15/18 for 30,000pcs
Note on C123: Jessica Moma: Issued 8/15/18 for 30,000pcs
Note on K147: Rob Douglas: Tri-Star Metals 9/5
Note on K192: Rob Douglas: Central 8/21
Note on R196: Rob Douglas: was 8/6
Note on K212: Rob Douglas: EMJ 250# 8/15 Rob Douglas: Balance Tri-star 8/24
Note on R213: Rob Douglas: Tentative--will need to keep an eye on the open PO's from KKSP
Note on R223: Rob Douglas: 9/3
Note on C237: Jessica Moma: Issued 8/1/18 for 30,000pcs
Note on C245: Jessica Moma: Continuous Run Issued 8/15/18 for 80,000pcs
Note on K246: Rob Douglas: 8/31 Chase
Note on B364: Rob Douglas: Do Not Run on A7 OLD conveyor Reference 42412-10
Note on B525: Rob Douglas: Reference DA5002-10
Note on B527: Rob Douglas: Similar to DM2501
Note on B528: Rob Douglas: Similar to DM2501
Note on B531: Rob Douglas: Similar to DM1201 and DM1203
Note on B654: Rob Douglas: Run With M40070
Note on B655: Rob Douglas: Run with M30075
Note on B672: Rob Douglas: Reference NN38B21-20
Note on B691: Rob Douglas: Reference PPV10003-10
Note on B751: Rob Douglas: Reference S144S14403-10
Note on B768: Rob Douglas: Reference SF5051-20
Note on B795: Rob Douglas: Reference SW1015-10

## Hydromat
| Hydromat Production Schedule | [6 empty] | 2018-09-06
[6 empty] | RATE | [8 empty] | ORIG |  | ORIG
MACH | PART | Packet |  | QTY | Number | PCS | S/U | TOTAL | TOTAL | MAKE FROM | ROUGH | Finished | MATL # |  | start | START | DUE |  |  | 2018-09-20
NO | NUMBER | Made | Order Qty | BAL DUE | Routings | HR | HRS | HRS | SHIFTS | P/N | WGT EA | Weight | BAL DUE | DAYS | date | DATE | date | Notes
[19 empty] | Hyd Shifts Behind | Hyd 2wk Shifts
[16 empty] | 2018-09-06 |  |  | 229 | 461
L1 | C5050071-10 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.5891 | 0.22265 | 0 | 0
SHIFTS | C5050071 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.5891 | 0.2132 | 0 | 0
3 | C5050072 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.5891 | 0.212 | 0 | 0
QBE | C5050001 |  | 10000 | 10000 | 16.5714 | 324 | 0 | 30.8642 | 4 | A02032-0028 | 0.6412 | 0.232 | 6412 | 1.3333 | 2018-11-01 |  | 2018-11-15
| C5050001-00 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A02032-0028 | 0.6412 | 0.24335 | 0 | 0
| C5050001-10 |  | 0 | 0 | 0 | 270 | 0 | 0 | 0 | A02032-0028 | 0.6412 | 0.244 | 0 | 0
| C5050B2L2-10 |  | 0 | 0 | 0 | 300 | 0 | 0 | 0 | A02032-0028 | 0.5297 | 0.2053 | 0 | 0
| C5050B2L2 |  | 0 | 0 | 0 | 300 | 0 | 0 | 0 | A02032-0028 | 0.5297 | 0.19233 | 0 | 0
| C5050B2L3-10 |  | 0 | 0 | 0 | 300 | 0 | 0 | 0 | A02032-0028 | 0.5297 | 0.2992 | 0 | 0
| C5050B21 | 625479 | 32000 | 32000 | 31.04 | 324 | 0 | 98.7654 | 13 | A02032-0028 | 0.4746 | 0.1358 | 15187.2 | 4.3333 | 2018-10-09 | 2018-09-06 | 2018-10-29
| C5050B7L1 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.4867 | 0.1505 | 0 | 0
| C5050B7L1-00 |  | 14000 | 14000 | 15.71 | 231 | 0 | 60.6061 | 8 | A01032-0028 | 0.4867 | 0.1571 | 6813.8 | 2.6667 | 2018-09-25 |  | 2018-10-15
| C5050B7L2 | 620371 | 29500 | 29500 | 37.4439 | 231 | 32 | 159.7056 | 21 | A01032-0028 | 0.4867 | 0.1777 | 14357.65 | 7 | 2018-08-10 |  | 2018-09-03 |  | 21 | 21
| C5050B2L6-00 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A02032-0028 | 0.6259 | 0.2992 | 0 | 0
| C3850B22 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A02032-0028 | 0.5341 | 0.21085 | 0 | 0
| C3850B71 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.4908 | 0.18156 | 0 | 0
| C3850B72 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.4908 | 0.19275 | 0 | 0
| C3850B72-5 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.4908 | 0.20145 | 0 | 0
| C7575001 |  | 0 | 0 | 0 | 270 | 0 | 0 | 0 | A02032-0036 | 1.3159 | 0.681 | 0 | 0
| C7575001-00 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0036 | 1.3226 | 0.471 | 0 | 0
| C7575B22 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0036 | 1.0878 | 0.385 | 0 | 0 |  | 2018-09-06
| S5650B72 | 615573 | 22000 | 0 | 0 | 231 | 0 | 0 | 0 | A01032-0028 | 0.4019 | 0.17 | 0 | 0 | 2018-08-10 | 2018-09-06 | 2018-09-01 | out 8/31 | 0 | 0
| P5075001 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0038 | 1.4125 | 0.456 | 0 | 0
| P5075001-00 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0038 | 1.4125 | 0.465 | 0 | 0
| P7575001 |  | 7000 | 7000 | 20.15 | 231 | 0 | 30.303 | 4 | A02032-0038 | 1.4125 | 0.403 | 9887.5 | 1.3333 | 2018-10-31 |  | 2018-11-19
| P7575001-00 |  | 0 | 0 | 0 | 180 | 0 | 0 | 0 | A02032-0038 | 1.4125 | 0.40845 | 0 | 0
| P7575002 |  | 3000 | 3000 | 8.7225 | 231 | 0 | 12.987 | 2 | A02032-0038 | 1.4137 | 0.40705 | 4241.1 | 0.66667 | 2018-10-31 |  | 2018-11-19
| P7575030 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0038 | 1.4125 | 0.40325 | 0 | 0
| P7575B21 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0038 | 1.1499 | 0.326 | 0 | 0
| P7575B21-00 |  | 1000 | 1000 | 2.8286 | 231 | 0 | 4.329 | 1 | A02032-0038 | 1.1499 | 0.396 | 1149.9 | 0.33333
| P7575B25 |  | 3000 | 3000 | 7.1143 | 231 | 0 | 12.987 | 2 | A02032-0038 | 1.1499 | 0.332 | 3449.7 | 0.66667 | 2018-09-04 |  | 2018-10-04 |  |  | 2
| P7575B31 |  | 2000 | 2000 | 18.8 | 231 | 0 | 8.658 | 1 | A02032-0038 | 1.1499 | 0.329 | 2299.8 | 0.33333 | 2018-09-04 |  | 2018-10-04 |  |  | 1
| IC75001 |  | 3000 | 3000 | 8.2232 | 231 | 32 | 44.987 | 6 | A02032-0038 | 1.0431 | 0.38375 | 3129.3 | 2 | 2018-08-20 |  | 2018-09-05 |  | 6 | 6
| P7575B71 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A01032-0038 | 1.0628 | 0.29805 | 0 | 0
| P7575B71-00 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A01032-0038 | 1.0628 | 0.306 | 0 | 0
| P5050B21 |  | 0 | 0 | 0 | 270 | 0 | 0 | 0 | A02032-0032 | 0.7324 | 0.396 | 0 | 0
| P5050B21-10 |  | 2000 | 2000 | 5.6857 | 324 | 0 | 6.1728 | 1 | A02032-0032 | 0.7324 | 0.398 | 1464.8 | 0.33333
| P5050B25 |  | 0 | 0 | 0 | 270 | 0 | 0 | 0 | A02032-0032 | 0.7324 | 0.2545 | 0 | 0
| P5050001 |  | 0 | 0 | 0 | 270 | 0 | 0 | 0 | A02032-0032 | 0.8639 | 0.2741 | 0 | 0
| P5050001-00 |  | 0 | 0 | 0 | 270 | 0 | 0 | 0 | A02032-0032 | 0.8639 | 0.2741 | 0 | 0
| IF5050B24(1/2) |  | 9000 | 9000 | 18.8614 | 216 | 1 | 42.6667 | 6 | A02032-0032 | 0.8102 | 0.2934 | 7291.8 | 2 | 2018-10-09 |  | 2018-10-29
| IF5050B26 (1/2) |  | 100 | 100 | 0.20957 | 216 | 16 | 16.463 | 2 | A02032-0032 | 0.8102 | 0.2934 | 81.02 | 0.66667
| IF6275B25--3 | 621115 | 18000 | 18000 | 54.7714 | 240 | 32 | 107 | 14 | A02032-0038 | 1.1343 | 0.426 | 20417.4 | 4.6667 | 2018-08-20 | 2018-09-13 | 2018-09-01 |  | 14 | 14
| IF6275B26 |  | 0 | 0 | 0 | 240 | 0 | 0 | 0 | A02032-0038 | 1.1343 | 0.426 | 0 | 0
| IF7575B22 |  | 0 | 0 | 0 | 216 | 1 | 1 | 0 | A02032-0040 | 1.32 | 0.43175 | 0 | 0
| IF7575B27 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A02032-0040 | 1.32 | 0.43175 | 0 | 0
| IF7575B26 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A02032-0040 | 1.32 | 0.435 | 0 | 0
| IF7575B24 |  | 0 | 0 | 0 | 216 | 0 | 0 | 0 | A02032-0040 | 1.32 | 0.434 | 0 | 0
| M3800B24 | hold | 33000 | 33000 | 61.4507 | 324 | 0 | 101.8519 | 14 | A02032-0028 | 0.3792 | 0.13035 | 12513.6 | 4.6667 | 2018-11-01 |  | 2018-11-19
| RSC1001--1 | 619678 | 10000 | 0 | 0 | 540 | 0 | 0 | 0 | A09032-0036 | 0.1802 | 0.103 | 0 | 0 | 2018-07-01 | 2018-09-06 | 2018-07-23 | out 9/6 | 0 | 0
| RSC1004--2 | 619679 | 10000 | 10000 | 54.0286 | 270 | 32 | 69.037 | 10 | A02032-0036 | 0.6979 | 0.1891 | 6979 | 5 | 2018-08-25 | 2018-09-06 | 2018-09-17 | setup 9/6 |  | 10
2018-09-13
109
2018-09-06
L2 | RCF002 | 620320 | 20000 | 0 | 0 | 360 | 0 | 0 | 0 | A02001-0032 | 0.301 | 0.088 | 0 | 0 | 2018-07-07 | 2018-09-06 | 2018-07-27 | out 8/31 | 0 | 0
SHIFTS | RDF001 | 618648 | 10000 | 10000 | 81.1429 | 300 | 50 | 83.3333 | 12 | A02031-0032 | 0.5542 | 0.284 | 5542 | 6 | 2018-06-28 | 2018-09-06 | 2018-07-18 | setup 8/31 | 12 | 12
2 | RCF201 | 620192 | 10000 | 10000 | 68.5714 | 240 | 50 | 91.6667 | 13 | A02001-0032 | 0.5034 | 0.24 | 5034 | 6.5 | 2018-07-25 | 2018-09-14 | 2018-08-17 |  | 13 | 13
| RCF402 | new | 10000 | 10000 | 40 | 240 | 50 | 91.6667 | 13 | A02031-0035 | 0.3278 | 0.14 | 3278 | 6.5 | 2018-07-25 | 2018-10-04 | 2018-08-17 | tooling 9/12 | 13 | 13
| RDF901 | new | 10000 | 10000 | 140 | 216 | 50 | 96.2963 | 13 | A02001-0040 | 0.8882 | 0.49 | 8882 | 6.5 |  | 2018-09-25 |  | tooling 10/2
2018-10-15
51
2018-09-06
L3 | SF5001 | 620408 | 18000 | 18000 | 97.2514 | 231 | 32 | 109.9221 | 15 | A02042-0028 | 0.4999 | 0.1891 | 8998.2 | 5 | 2018-07-10 | 2018-09-06 | 2018-08-06 | Setup 9/6 | 15 | 15
SHIFTS | SF5051 | 621457 | 1000 | 1000 | 5.3714 | 231 | 4 | 8.329 | 1 | A02042-0028 | 0.4999 | 0.188 | 499.9 | 0.33333 | 2018-08-10 | 2018-09-13 | 2018-08-15 |  | 1 | 1
3 | TC1280 | 621438 | 12000 | 12000 | 151.5429 | 240 | 32 | 82 | 11 | A02032-0032 | 0.7615 | 0.442 | 9138 | 3.6667 | 2018-08-10 | 2018-09-14 | 2018-09-07 |  |  | 11
QBE | PWN2004 | 621717 | 7850 | 7850 | 30.8617 | 348 | 32 | 54.5575 | 8 | A02032-0022 | 0.2599 | 0.1376 | 2040.215 | 2.6667 | 2018-08-21 | 2018-09-20 | 2018-09-21 |  |  | 8
| PWN2024 | new | 29000 | 29000 | 37.2029 | 324 | 32 | 121.5062 | 17 | A09032-0022 | 0.0848 | 0.0449 | 2459.2 | 5.6667 | 2018-10-05 | 2018-09-25 | 2018-11-05
| AP5003 | new | 4000 | 4000 | 18.1257 | 405 | 32 | 41.8765 | 6 | A02032-0032 | 0.4889 | 0.1586 | 1955.6 | 2 | 2018-08-25 | 2018-10-03 | 2018-09-17 |  |  | 6
| AP3802 | new | 6000 | 6000 | 16.08 | 432 | 32 | 45.8889 | 6 | A02032-0026 | 0.3004 | 0.0938 | 1802.4 | 2 | 2018-09-10 | 2018-10-05 | 2018-10-01 |  |  | 6
| AP2503 | new | 6000 | 6000 | 21.528 | 360 | 32 | 48.6667 | 6 | A02032-0026 | 0.3004 | 0.12558 | 1802.4 | 2 | 2018-10-01 | 2018-10-09 | 2018-10-22
| AP3801 | new | 18000 | 18000 | 43.2 | 405 | 32 | 76.4444 | 10 | A02032-0026 | 0.293 | 0.084 | 5274 | 3.3333 | 2018-09-08 | 2018-10-11 | 2018-09-28 |  |  | 10
| AP5001 | new | 48000 | 48000 | 207.0857 | 360 | 32 | 165.3333 | 22 | A02032-0032 | 0.4727 | 0.151 | 22689.6 | 7.3333 | 2018-09-04 | 2018-10-17 | 2018-09-24 |  |  | 22
| 419996 | new | 27000 | 27000 | 71.3571 | 463 | 32 | 90.3153 | 12 | A02031-7877 | 0.2485 | 0.0925 | 6709.5 | 4 | 2018-11-01 | 2018-10-29 | 2018-11-20
2018-11-02
114
2018-09-06
L4 | CY12401 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A09031-0038 | 0.143 | 0.0802 | 0 | 0
SHIFTS | CY13501 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A09331-0038 | 0.1405 | 0.081 | 0 | 0
2 | CY20001 |  | 0 | 0 | 0 | 360 | 0 | 0 | 0 | A09331-0038 | 0.143 | 0.081 | 0 | 0
| CY10220 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A09331-0038 | 0.1405 | 0.0817 | 0 | 0
| CY10201-0 |  | 11000 | 11000 | 20.1143 | 324 | 0 | 33.9506 | 5 | A02031-0038 | 0.4387 | 0.256 | 4825.7 | 2.5 | 2018-11-01 |  | 2018-11-15
| CY11901-0 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A02031-0038 | 0.4357 | 0.2576 | 0 | 0
| CY30015 |  | 0 | 0 | 0 | 231 | 0 | 0 | 0 | A06131-0038 | 0.54 | 0.304 | 0 | 0
| CY30009 |  | 0 | 0 | 0 | 295 | 0 | 0 | 0 | A06131-0038 | 0.54 | 0.3287 | 0 | 0
| CY11701 |  | 0 | 0 | 0 | 295 | 0 | 0 | 0 | A09331-0038 | 0.1837 | 0.1118 | 0 | 0
| CY11702 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A19131-0038 | 0.1839 | 0.1118 | 0 | 0
| CY11711 | 620680 | 28000 | 0 | 0 | 324 | 0 | 0 | 0 | A09331-0038 | 0.1837 | 0.11306 | 0 | 0 |  | 2018-09-06
| CY10035 |  | 0 | 0 | 0 | 250 | 0 | 0 | 0 | A06201-0032 | 0.2953 | 0.106 | 0 | 0
| CY10021 |  | 0 | 0 | 0 | 405 | 0 | 0 | 0 | A02031-0032 | 0.3103 | 0.1129 | 0 | 0
| CY10025 |  | 0 | 0 | 0 | 360 | 0 | 0 | 0 | A09031-0032 | 0.1012 | 0.03588 | 0 | 0
| CY10030-ISO-1 | 620232 | 45000 | 45000 | 14.0143 | 270 | 0 | 166.6667 | 22 | A09331-0032 | 0.1012 | 0.0436 | 4554 | 11 | 2018-09-10 | 2018-09-06 | 2018-10-01 | setup 9/4 run 9/5 |  | 22
| CY20020 |  | 0 | 0 | 0 | 324 | 0 | 0 | 0 | A09031-0038 | 0.145 | 0.04785 | 0 | 0
| CY12201--2 |  | 15000 | 15000 | 15.7929 | 324 | 16 | 62.2963 | 8 | A02032-0040 | 0.5434 | 0.1474 | 8151 | 4 | 2018-10-06 | 2018-10-01 | 2018-10-26
| CY10620--3 | 620193 | 18000 | 18000 | 38.9379 | 309 | 32 | 90.2524 | 12 | A02032-0040 | 0.527 | 0.30285 | 9486 | 6 | 2018-10-10 | 2018-09-21 | 2018-11-01
| CY30001 |  | 0 | 0 | 0 | 180 | 0 | 0 | 0 | A06101-0040 | 0.4625 | 0.2582 | 0 | 0
2018-10-05
47
2018-09-06
L5 | 428062 | 619334 | 80000 | 80000 | 137.7143 | 375 | 16 | 229.3333 | 31 | 427926 | 0.4769 | 0.241 | 38152 | 10.3333 | 2018-08-01 | 2018-09-06 | 2018-08-15 | run 5/23 | 31 | 31
SHIFTS | 428062 | 621202 | 80000 | 80000 | 137.7143 | 375 | 16 | 229.3333 | 31 | 427926 | 0.4769 | 0.241 | 38152 | 10.3333 | 2018-08-15 | 2018-09-21 | 2018-08-30 |  | 31 | 31
3 | [15 empty] | 2018-10-08 |  | 427926 Ship Dates
2018-10-05
2018-11-02
2018-11-28
31
2018-09-06
S1 | SP2502 |  | 0 | 0 | 0 | 810 | 0 | 0 | 0 | A02022-0018 | 0.1197 | 0.0506 | 0 | 0 |  | 2018-09-06
SHIFTS | SP2501--8 |  | 180000 | 180000 | 274.8857 | 810 | 12 | 234.2222 | 31 | A02022-0018 | 0.1197 | 0.05345 | 21546 | 10.3333 | 2018-08-11 | 2018-09-25 | 2018-08-31 |  | 31 | 31
3 | SP2505--1 | 620291 | 30000 | 0 | 0 | 810 | 0 | 0 | 0 | A02022-0018 | 0.1197 | 0.04888 | 0 | 0 | 2018-08-07 | 2018-09-06 | 2018-08-27 |  | 0 | 0
| SP1201-1--2 | 620293 | 20000 | 20000 | 28.5714 | 810 | 0 | 24.6914 | 3 | A02022-0018 | 0.1102 | 0.05 | 2204 | 1 | 2018-10-09 | 2018-09-06 | 2018-10-29 | out 9/6
| SP2550 |  | 0 | 0 | 0 | 810 | 0 | 0 | 0 | A02022-0018 | 0.1197 | 0.05 | 0 | 0
| SA1201--5 | 620440 | 23000 | 23000 | 44.16 | 498 | 4 | 50.1847 | 7 | A02022-0022 | 0.235 | 0.0672 | 5405 | 2.3333 | 2018-10-09 | 2018-09-18 | 2018-10-29
| SA2501-4 | 620555 | 22000 | 22000 | 21.12 | 498 | 4 | 48.1767 | 6 | A02022-0022 | 0.235 | 0.0672 | 5170 | 2 | 2018-08-07 | 2018-09-14 | 2018-08-27 |  | 6 | 6
| ST2A01F--3 | 620880 | 50000 | 50000 | 82.8571 | 498 | 12 | 112.4016 | 15 | A02022-0022 | 0.2143 | 0.058 | 10715 | 5 | 2018-08-20 | 2018-09-07 | 2018-09-10 | setup 9/6 |  | 15
| ST1A01 |  | 0 | 0 | 0 | 498 | 0 | 0 | 0 | A02022-0022 | 0.2143 | 0.04638 | 0 | 0
| ST3A01 |  | 0 | 0 | 0 | 498 | 0 | 0 | 0 | A02022-0022 | 0.2143 | 0.07455 | 0 | 0
| SA3801--6 |  | 3000 | 3000 | 5.76 | 498 | 4 | 10.0241 | 1 | A02022-0022 | 0.235 | 0.0672 | 705 | 0.33333 | 2018-09-15 | 2018-09-21 | 2018-10-01 |  |  | 1
| ST2A01B |  | 0 | 0 | 0 | 540 | 0 | 0 | 0 | A02022-0022 | 0.2143 | 0.05552 | 0 | 0
| ST2A01G |  | 0 | 0 | 0 | 498 | 0 | 0 | 0 | A02022-0022 | 0.2143 | 0.0569 | 0 | 0
| SP2506--7 |  | 10000 | 10000 | 15.0286 | 810 | 0 | 12.3457 | 2 | A02022-0018 | 0.1197 | 0.0526 | 1197 | 0.66667 | 2018-09-20 | 2018-09-24 | 2018-10-08
2018-10-10
65
2018-09-06
S2 | SP2509 | 619491 | 100000 | 49490 | 11.312 | 810 | 0 | 61.0988 | 8 | A02001-0013 | 0.0532 | 0.008 | 2632.868 | 8 | 2018-08-30 | 2018-09-06 | 2018-09-10 |  |  | 8
SHIFTS | SP2509 | 621719 | 100000 | 100000 | 22.8571 | 810 | 0 | 123.4568 | 16 | A02001-0013 | 0.0532 | 0.008 | 5320 | 16 | 2018-09-10 | 2018-09-18 | 2018-09-30 |  |  | 16
1 | [15 empty] | 2018-10-10
Collet
24
2018-09-06
S3 | EB2555 | 618039 | 120000 | 65590 | 62.3292 | 360 | 0 | 182.1944 | 24 | A09332-0028 | 0.1204 | 0.03326 | 7897.036 | 24 | 2018-09-01 | 2018-09-06 | 2018-09-21 | setup 8/14 ru n 8/15 |  | 24
SHIFTS | EB2550 | hold | 20000 | 20000 | 19.0057 | 360 | 24 | 79.5556 | 11 | A02032-0028 | 0.3664 | 0.03326 | 7328 | 11 | 2018-09-20 | 2018-10-10 | 2018-10-12
1 | M1212002 | new | 5000 | 5000 | 5.9071 | 360 | 16 | 29.8889 | 4 | A02032-0022 | 0.1773 | 0.04135 | 886.5 | 4 | 2018-10-20 | 2018-10-25 | 2018-11-12
2018-10-31
A09332-0028
10k on 10/5
35
2018-09-06
S4 | ST2A02 | 616499 | 80000 | 12205 | 5.1958 | 498 | 0 | 24.508 | 3 | A02031-0018 | 0.1347 | 0.0149 | 1644.0135 | 3 | 2018-07-15 | 2018-09-06 | 2018-07-30 | setup 8/3 run 8/7 | 3 | 3
SHIFTS | RCF015-X | R&D | [11 empty] | 0 |  | 2018-09-11
1 | 104114-4 | 620195 | 39000 | 39000 | 74.6571 | 324 | 24 | 144.3704 | 19 | A02032-0022 | 0.2031 | 0.067 | 7920.9 | 19 | 2018-09-15 | 2018-09-11 | 2018-10-15 |  |  | 19
| 104114-2 | new | 13600 | 13600 | 20.9595 | 324 | 8 | 49.9753 | 7 | A02032-0022 | 0.1753 | 0.05394 | 2384.08 | 7 | 2018-10-01 | 2018-10-08 | 2018-10-20
| FT13801 | new | 13000 | 13000 | 12.9629 | 405 | 24 | 56.0988 | 7 | A02002-0020 | 0.0926 | 0.0349 | 1203.8 | 7 | 2018-10-02 | 2018-10-17 | 2018-10-21 | verify tooling
| SR2501 | new | 13000 | 13000 | 33.0051 | 450 | 24 | 52.8889 | 7 | A02002-0020 | 0.2199 | 0.08886 | 2858.7 | 7 | 2018-10-20 | 2018-10-26 | 2018-11-12 | verify tooling
| PWN65400 | new | 100000 | 100000 | 91.4286 | 505 | 24 | 222.0198 | 30 | A02001-0016 | 0.0778 | 0.032 | 7780 | 30 | 2018-10-25 | 2018-11-06 | 2018-11-16
2018-12-18
29
2018-09-06
S5 | PWN00030-H | 618570 | 15000 | 0 | 0 | 330 | 0 | 0 | 0 | A06021-0016 | 0.0708 | 0.0271 | 0 | 0 | 2018-08-01 | 2018-09-06 | 2018-08-17 | job out | 0 | 0
SHIFTS | PWN00032-H | 621885 | 9000 | 9000 | 6.9686 | 330 | 0 | 27.2727 | 4 | A06021-0016 | 0.0708 | 0.0271 | 637.2 | 1.3333 | 2018-09-06 | 2018-09-06 | 2018-09-20 | setup 9/6 |  | 4
3 | PWN00032-HT | 621339 | 15000 | 15000 | 11.6143 | 330 | 4 | 49.4545 | 7 | A06021-0016 | 0.0708 | 0.0271 | 1062 | 2.3333 | 1974-09-01 | 2018-09-10 | 2018-09-24 |  |  | 7
| PWN15045-H | 619791 | 3000 | 3000 | 2.3229 | 330 | 4 | 13.0909 | 2 | A06021-0016 | 0.0708 | 0.0271 | 212.4 | 0.66667 | 2018-08-03 | 2018-09-13 | 2018-08-23 |  | 2 | 2
| PWN15040-H | 619795 | 6000 | 6000 | 4.6457 | 330 | 4 | 22.1818 | 3 | A06021-0016 | 0.0708 | 0.0271 | 424.8 | 1 | 2018-08-12 | 2018-09-14 | 2018-09-03 |  | 3 | 3
| PWN15032-HT | new | 15000 | 15000 | 11.6143 | 330 | 4 | 49.4545 | 7 | A06021-0016 | 0.0708 | 0.0271 | 1062 | 2.3333 | 2018-08-20 | 2018-09-17 | 2018-09-05 |  | 7 | 7
| PWN15030-H | 620196 | 15000 | 15000 | 11.6143 | 330 | 4 | 49.4545 | 7 | A06021-0016 | 0.0708 | 0.0271 | 1062 | 2.3333 | 2018-08-17 | 2018-09-20 | 2018-09-07 |  |  | 7
| PWN15033-H | 621285 | 6000 | 6000 | 4.6457 | 330 | 4 | 22.1818 | 3 | A06021-0016 | 0.0708 | 0.0271 | 424.8 | 1 | 2018-09-10 | 2018-09-25 | 2018-10-01 |  |  | 3
| PWN15027-H | new | 15000 | 15000 | 11.6143 | 330 | 24 | 69.4545 | 10 | A06021-0016 | 0.0708 | 0.0271 | 1062 | 3.3333 | 1974-09-01 | 2018-09-26 | 2018-09-24 |  |  | 10
| RSC1016 | new | 6000 | 6000 | 5.7017 | 341 | 24 | 41.5953 | 6 | A02031-0016 | 0.1077 | 0.03326 | 646.2 | 2 | 2018-09-17 | 2018-10-02 | 2018-10-17 |  |  | 6
| PWN15035-H | new | 15000 | 15000 | 11.6143 | 330 | 4 | 49.4545 | 7 | A06021-0016 | 0.0708 | 0.0271 | 1062 | 2.3333 | 2018-10-01 | 2018-10-04 | 2018-10-20
| PWN40032-H | new | 15000 | 15000 | 11.6143 | 330 | 4 | 49.4545 | 7 | A06021-0016 | 0.0708 | 0.0271 | 1062 | 2.3333 | 2018-09-10 | 2018-10-09 | 2018-10-01 |  |  | 7
| PWN40037-H | new | 3000 | 3000 | 2.3229 | 330 | 4 | 13.0909 | 2 | A06021-0016 | 0.0708 | 0.0271 | 212.4 | 0.66667 | 2018-10-02 | 2018-10-12 | 2018-10-22
| PWN40035-H | new | 9000 | 9000 | 6.9686 | 330 | 4 | 31.2727 | 5 | A06021-0016 | 0.0708 | 0.0271 | 637.2 | 1.6667 | 2018-10-09 | 2018-10-15 | 2018-10-29
| PWN40029-H | new | 24000 | 24000 | 18.5829 | 330 | 4 | 76.7273 | 11 | A06021-0016 | 0.0708 | 0.0271 | 1699.2 | 3.6667 | 2018-10-01 | 2018-10-17 | 2018-11-01
2018-10-23
81
2018-09-06
S6 | PWN25032-HT | 620296 | 15000 | 15000 | 11.6143 | 330 | 4 | 49.4545 | 7 | A06021-0016 | 0.0708 | 0.0271 | 1062 | 3.5 | 2018-08-01 | 2018-09-06 | 2018-08-20 | setup 8/30 run 9/5 | 7 | 7
SHIFTS | PWN25035-H | 621201 | 12000 | 12000 | 9.2914 | 330 | 4 | 40.3636 | 6 | A06021-0016 | 0.0708 | 0.0271 | 849.6 | 3 | 2018-08-10 | 2018-09-12 | 2018-09-03 |  | 6 | 6
2 | PWN25060-H | new | 3000 | 3000 | 2.3229 | 330 | 4 | 13.0909 | 2 | A06021-0016 | 0.0708 | 0.0271 | 212.4 | 1 | 2018-09-04 | 2018-09-17 | 2018-09-24 |  |  | 2
| PWN40030-H | 618866 | 9000 | 9000 | 6.9686 | 330 | 4 | 31.2727 | 5 | A06021-0016 | 0.0708 | 0.0271 | 637.2 | 2.5 | 2018-07-20 | 2018-09-18 | 2018-08-10 |  | 5 | 5
| PWN40040-H | 619787 | 3000 | 3000 | 2.3229 | 330 | 4 | 13.0909 | 2 | A06021-0016 | 0.0708 | 0.0271 | 212.4 | 1 | 2018-08-10 | 2018-09-21 | 2018-08-23 |  | 2 | 2
| PWN00025-H | new | 9000 | 9000 | 6.9686 | 330 | 4 | 31.2727 | 5 | A06021-0016 | 0.0708 | 0.0271 | 637.2 | 2.5 | 2018-09-10 | 2018-09-24 | 2018-10-01 |  |  | 5
| PWN00040-H | new | 9000 | 9000 | 6.9686 | 330 | 4 | 31.2727 | 5 | A06021-0016 | 0.0708 | 0.0271 | 637.2 | 2.5 | 2018-09-20 | 2018-09-27 | 2018-10-08
| PWN25030-H | new | 12000 | 12000 | 9.2914 | 330 | 4 | 40.3636 | 6 | A06021-0016 | 0.0708 | 0.0271 | 849.6 | 3 | 2018-09-20 | 2018-10-02 | 2018-10-12
| PWN25033-H | new | 12000 | 12000 | 9.2914 | 330 | 4 | 40.3636 | 6 | A06021-0016 | 0.0708 | 0.0271 | 849.6 | 3 | 2018-09-20 | 2018-10-05 | 2018-10-12
| PWN25060-H | new | 3000 | 3000 | 2.3229 | 330 | 4 | 13.0909 | 2 | A06021-0016 | 0.0708 | 0.0271 | 212.4 | 1 | 2018-09-20 | 2018-10-10 | 2018-10-12
| PWN25029-H | 620298 | 24000 | 24000 | 18.5829 | 330 | 4 | 76.7273 | 11 | A06021-0016 | 0.0708 | 0.0271 | 1699.2 | 5.5 | 2018-10-05 | 2018-10-11 | 2018-10-25
| PWN25045-H | new | 3000 | 3000 | 2.3229 | 330 | 4 | 13.0909 | 2 | A06021-0016 | 0.0708 | 0.0271 | 212.4 | 1 | 2018-10-05 | 2018-10-19 | 2018-10-25
2018-10-22
2018-10-22
59
[13 empty] | 12 S&O |  | SHIFTS |  | SHIFTS
| THIS MONTH |  |  | Total Shifts Needed |  |  |  |  | 645 |  |  |  | APRIL |  | 1901-04-24 |  | 1901-04-24
| NEXT MONTH |  |  | Total Shifts Scheduled |  |  |  |  | 27 |  |  |  | MAY |  | 1901-07-05 |  | 1901-07-05
|  |  |  | Staff Needed |  |  |  |  | 13.5
Color Codes
New Part
Material in House
Material 1 week
Material 2 weeks
Material partial in house
Hard Orders
Needs Reviewed
Gross & Scrap Verified- in BOM
Cycle time Verified
Vefication that BOM matches P/N Secondary schedule Only
L2 | 0027-15-C |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02031-0032 | 0.4987 | 0.27685 | 0 |  |  |  | FF1
L2 | 0027-13-C |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02061-71115 | 0.6721 | 0.3802 | 0 |  |  |  | FF1
L2 | 0027-17-C |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02061-71115 | 0.6721 | 0.4678 | 0 |  |  |  | FF1
L2 | 0012-85-C(1/2) | Ganesh |  | 0 | 0 | 231 | 16 | 16 | 2 | A02031-0032 | 0.4344 | 0.3033 | 0 |  |  |  | FF1
L3/L2 | 0043-33-C |  |  | 0 | 0 | 203 | 50 | 50 | 7 | A02031-0060 | 1.6401 | 0.369 | 0
L3 | 0043-34-C |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02031-0040 | 0.8971 | 0.41719 | 0 |  |  |  | FF2
L2 | 0010-92-C-P(1/2) | Ganesh |  | 0 | 0 | 270 | 32 | 32 | 4 | A02031-0040 | 1.0081 | 0.585 | 0 |  |  |  | FF2
L2 | 0014-01-C-P(1/2) |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02031-0040 | 0.6038 | 0.2566 | 0 |  |  |  | FF2
L2 | 0045-30-C(1/2) | Ganesh |  | 0 | 0 | 231 | 32 | 32 | 4 | A02031-0040 | 0.6344 | 0.252 | 0 |  |  |  | FF2
L2 | 0017-89-C-P(1/2) |  |  | 0 | 0 | 270 | 32 | 32 | 4 | A02031-0040 | 0.7289 | 0.292 | 0 |  |  |  | FF2
S2 | 104114-4 |  |  | 0 | 0 | 324 | 24 | 24 | 3 | A02032-0022 | 0.2031 | 0.067 | 0 |  | F37 | collet | F37
S2 | 104114-3 |  |  | 0 | 0 | 324 | 24 | 24 | 3 | A02032-0022 | 0.2031 | 0.06844 | 0 |  | F37 | collet | F37
S2 | 104114-2 |  |  | 0 | 0 | 324 | 24 | 24 | 3 | A02032-0022 | 0.1753 | 0.05394 | 0 |  | F37 | collet | F37
S2 | 104114-1 |  |  | 0 | 0 | 360 | 24 | 24 | 3 | A02032-0022 | 0.1741 | 0.06519 | 0 |  | F37 | collet | F37
S3 | 106148-2 |  |  | 0 | 0 | 324 | 24 | 24 | 3 | A02032-0022 | 0.1753 | 0.05236 | 0 |  | F37 | collet
L2 | 106-70-2 |  |  | 0 | 0 | 191 | 32 | 32 | 4 | A08031-0124 | 0.2383 | 0.054 | 0 |  | F88
L2 | 106-103-2 |  |  | 0 | 0 | 191 | 32 | 32 | 4 | A08031-0124 | 0.2167 | 0.072 | 0 |  | F88
L2 | 106-118-2 |  |  | 0 | 0 | 203 | 32 | 32 | 4 | A08031-0124 | 0.2423 | 0.06956 | 0 |  | F88 | 1900-04-09
L2 | 106-129-2 |  |  | 0 | 0 | 203 | 32 | 32 | 4 | A08031-0124 | 0.225 | 0.07162 | 0 |  | F88
L2 | 134-132-2 |  |  | 0 | 0 | 249 | 50 | 50 | 7 | A08031-0185 | 0.2528 | 0.15305 | 0 |  | F88
L4 | 106238-1-10 |  |  | 0 | 0 | 162 | 50 | 32 | 4 | A06232-0024 | 0.1717 | 0.06025 | 0
L2 | 143001-01-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.6672 | 0.325 | 0
L2 | 143002-01-C |  |  | 0 | 0 | 191 | 32 | 32 | 4 | A01132-0040 | 1.1029 | 0.0472 | 0
L2 | 143003-02-C |  |  | 0 | 0 | 137 | 32 | 32 | 4 | A01132-0052 | 2.2217 | 1.008 | 0
L2 | 143123-1-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.5156 | 0.287 | 0
L2 | 143124-1-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.5101 | 0.265 | 0
L2 | 143125-1-C |  |  | 0 | 0 | 240 | 32 | 32 | 4 | A01132-0040 | 0.8862 | 0.43505 | 0
L2 | 143126-2-C |  |  | 0 | 0 | 154 | 24 | 24 | 3 | A01132-0052 | 1.7789 | 0.909 | 0
L2 | 143171-1-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.5156 | 0.2897 | 0
L2 | 143172-1-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.5127 | 0.431 | 0
L2 | 143173-1-C |  |  | 0 | 0 | 240 | 32 | 32 | 4 | A01132-0040 | 0.8862 | 0.42805 | 0
L2 | 143341-01-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.5156 | 0.2897 | 0
L2 | 143342-1-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.5101 | 0.277 | 0
L2 | 143356-01-C |  |  | 0 | 0 | 154 | 24 | 24 | 3 | A01132-0052 | 1.7506 | 1.066 | 0
L2 | 143358-01-C |  |  | 0 | 0 | 154 | 8 | 8 | 1 | A01132-0052 | 1.7506 | 1.072 | 0
L3 | 21256A |  |  | 0 | 0 | 191 | 16 | 16 | 2 | A06132-0024 | 0.4099 | 0.2 | 0 |  |  | 2015
L# | 293138-10 |  |  | 0 | 0 | 295 | 32 | 32 | 4 | A02032-0044 | 1.0319 | 0.49315 | 0 |  |  | 2015
L3 | 293546-10 |  |  | 0 | 0 | 295 | 4 | 4 | 1 | A02032-0044 | 1.0319 | 0.4274 | 0 |  |  | 2015
L2 | 301782-1-C |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01132-0034 | 0.5186 | 0.281 | 0
L2 | 301868-1-C | new part |  | 0 | 0 | 249 | 8 | 8 | 1 | A01132-0034 | 0.5101 | 0.2653 | 0 |  |  | 2016
L3 | 419996 |  |  | 0 | 0 | 463 | 32 | 32 | 4 | A02031-7877 | 0.2485 | 0.0925 | 0
L5 | 428062(2/3) |  |  | 0 | 0 | 313 | 0 | 0 | 0 | 427926 | 0.4769 | 0.241 | 0 |  |  | 180
L5 | 428435(2/3) |  |  | 0 | 0 | 313 | 0 | 0 | 0 | 428436 | 0.4606 | 0.7365 | 0
L3 | 5010165-C |  |  | 0 | 0 | 381 | 32 | 32 | 4 | A02032-0044 | 0.5205 | 0.2466 | 0
L4 | 60-13011-C |  |  | 0 | 0 | 110 | 32 | 32 | 4 | A06432-8017 | 0.1602 | 0.0541 | 0
L4 | 60-13055-C |  |  | 0 | 0 | 278 | 32 | 32 | 4 | A01132-0032 | 0.8237 | 0.8154 | 0
| 678557001-C |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A06022-0018 | 0.1551 | 0.07 | 0
L3 | 80008836-C |  |  | 0 | 0 | 297 | 32 | 32 | 4 | A02032-0028 | 0.6031 | 0.3566 | 0
S6 Only | A3942-5 |  |  | 0 | 0 | 216 | 32 | 32 | 4 | A06201-0016 | 0.0485 | 0.013 | 0
A4/L2 | ACM01-10 |  |  | 0 | 0 | 324 | 48 | 48 | 6 | A02002-0028 | 0.5801 | 0.5105 | 0 | purchased
L3 | AP2501 |  |  | 0 | 0 | 405 | 32 | 32 | 4 | A02032-0026 | 0.2897 | 0.1037 | 0 | QBE | F3 |  | F3
L2 | AP2502 | Run with AP2504 |  | 0 | 0 | 531 | 32 | 32 | 4 | A02032-0026 | 0.2971 | 0.08226 | 0
L2 | AP2503 |  |  | 0 | 0 | 360 | 32 | 32 | 4 | A02032-0026 | 0.3004 | 0.12558 | 0 |  |  | 2015
L2 | AP2504 | Run with AP2502 |  | 0 | 0 | 360 | 32 | 32 | 4 | A02032-0026 | 0.298 | 0.12558 | 0 |  |  | 2018
L3 | AP3801 |  |  | 0 | 0 | 405 | 32 | 32 | 4 | A02032-0026 | 0.293 | 0.084 | 0 | QBE | F3 |  | F3
L3 | AP3802 | new part |  | 0 | 0 | 432 | 32 | 32 | 4 | A02032-0026 | 0.3004 | 0.0938 | 0 |  |  | 2016 | run with C3838B22
L3 | AP5001 |  |  | 0 | 0 | 360 | 32 | 32 | 4 | A02032-0032 | 0.4727 | 0.151 | 0 | QBE | F7 | 150 | run with IC50001
L3 | AP5002 | new part |  | 0 | 0 | 405 | 32 | 32 | 4 | A02032-0032 | 0.4948 | 0.1547 | 0 |  |  | 2016
L3 | AP5003 | new part |  | 0 | 0 | 405 | 32 | 32 | 4 | A02032-0032 | 0.4889 | 0.1586 | 0 |  |  | 2016
L3 | IC50001 |  |  | 0 | 0 | 360 | 16 | 16 | 2 | A02032-0032 | 0.6113 | 0.24115 | 0 | QBE | F7 |  | run with AP5001
L4 | B38B38002 |  |  | 0 | 0 | 117 | 32 | 32 | 4 | A06131-0018 | 0.1639 | 0.0415 | 0
L1 | C3150B74 |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A01032-0028 | 0.3943 | 0.144 | 0
L3 | C3838B22 |  |  | 0 | 0 | 324 | 16 | 16 | 2 | A02032-0026 | 0.3518 | 0.0957 | 0 |  | F3 |  | run with AP3801
L1 | C3850B21 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0028 | 0.523 |  | 0
L1 | C3850B22 |  |  | 0 | 0 | 324 | 8 | 8 | 1 | A02032-0028 | 0.5341 |  | 0
L1 | C3850B71 |  |  | 0 | 0 | 231 | 8 | 8 | 1 | A01032-0028 | 0.4908 |  | 0 |  | F2 |  | F2
L1 | C3850B72-5 |  |  | 0 | 0 | 231 | 4 | 4 | 1 | A01032-0028 | 0.4908 |  | 0 |  | F2 |  | F2
L1 | C3850B72-P |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A01032-0028 | 0.4908 |  | 0 |  | F2 |  | F2
L1 | C5050001 |  |  | 0 | 0 | 324 | 16 | 16 | 2 | A02032-0028 | 0.6412 |  | 0
L1 | C5050001-00 | 2015 |  | 0 | 0 | 324 | 1 | 1 | 0 | A02032-0028 | 0.6412 |  | 0
L1 | C5050001-10 |  |  | 4 | 0 | 270 | 32 | 32.0148 | 4 | A02032-0028 | 0.6412 |  | 2.5648 |  | F1 |  | F1
L1 | C5050071 |  |  | 16 | 0 | 231 | 32 | 32.0693 | 4 | A01032-0028 | 0.5891 |  | 9.4256 |  | F1 |  | F1
L1 | C5050071-10 |  |  | 0 | 0 | 231 | 16 | 16 | 2 | A01032-0028 | 0.5891 |  | 0 |  | F1 | 216 | F1
L1 | C5050072 |  |  | 8 | 0 | 231 | 16 | 16.0346 | 2 | A01032-0028 | 0.5891 |  | 4.7128 |  | F1 |  | F1
L1 | C5050B2L1 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0028 | 0 |  | 0
L1 | C5050B2L1-10 |  |  | 0 | 0 | 324 | 4 | 4 | 1 | A02032-0028 | 0 |  | 0
L1 | C5050B2L2 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0028 | 0.5297 |  | 0
L1 | C5050B2L2-10 |  |  | 0 | 0 | 324 | 4 | 4 | 1 | A02032-0028 | 0.5297 |  | 0
L1 | C5050B2L6-00 |  |  | 0 | 0 | 324 | 4 | 4 | 1 | A02032-0028 | 0.6259 |  | 0
L1 | C5050B21 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0028 | 0.4746 |  | 0
L1 | C5050B7L1 |  |  | 0 | 0 | 231 | 4 | 4 | 1 | A01032-0028 | 0.4867 |  | 0 |  | F6 |  | F6
L1 | C5050B7L2 |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A01032-0028 | 0.4867 |  | 0 |  | F6 |  | F6
L2 | C7575001 | new part |  | 0 | 0 | 231 | 0 | 0 | 0 | A02002-0036 | 1.3159 |  | 0 |  | F6 | 2015
L1 | C7575B22 |  |  | 0 | 0 | 231 | 16 | 16 | 2 | A02032-0036 | 1.0878 |  | 0 |  | F6 | 2017
L1 | S5650B72 |  |  | 0 | 0 | 259 | 32 | 32 | 4 | A01032-0028 | 0.4019 |  | 0 |  | F6 | 2014
| CJ1801 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0028 | 0.4163 |  | 0
S3 | CJ3873 |  |  | 0 | 0 | 243 | 32 | 32 | 4 | A01032-0028 | 0.4905 |  | 0
S3 | CJ3804 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0028 | 0.5143 |  | 0
L3 | CY10021 |  |  | 0 | 0 | 405 | 32 | 32 | 4 | A02031-0032 | 0.3103 |  | 0 |  | F43
L3 | CY10025 |  |  | 0 | 0 | 360 | 16 | 16 | 2 | A09031-0032 | 0.1012 |  | 0 |  | F43
L3 | CY10035 |  |  | 0 | 0 | 250 | 32 | 32 | 4 | A06201-0032 | 0.2953 |  | 0 |  | F43 | 2018
L3 | CY10030 |  |  | 0 | 0 | 270 | 32 | 32 | 4 | A09331-0032 | 0.1012 |  | 0 |  | F43
S3 | CY10101 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02031-7986 | 0.1872 | 0.03326 | 0
L4 | CY10114 |  |  | 0 | 0 | 463 | 32 | 32 | 4 | A02031-71085 | 0.2245 | 0.0728 | 0 |  | F43
L4 | CY10114-M |  |  | 0 | 0 | 463 | 32 | 32 | 4 | A02031-71085 | 0.2245 | 0.0728 | 0 |  | F43
L4 | CY10120 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02031-0038 | 0.4387 |  | 0 |  | F44 | 2016
L3 | CY10201-0 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02031-0038 | 0.4387 |  | 0 |  | F43
L3 | CY10220 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A09331-0038 | 0.1405 |  | 0 |  | F43
L3 | CY10604-0 | Obsolete |  | 0 | 0 | 309 | 32 | 32 | 4 | A02032-0040 | 0.536 |  | 0 |  | F43
L3 | CY10620 |  |  | 0 | 0 | 309 | 32 | 32 | 4 | A02032-0040 | 0.527 |  | 0 |  | F43
L3 | CY11601-0 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02031-0038 | 0.439 |  | 0 |  | F43
L3 | CY11601-10 |  |  | 0 | 0 | 324 | 4 | 4 | 1 | A02031-0038 | 0.4355 |  | 0 |  | F43
L3 | CY11602-0 |  |  | 0 | 0 | 324 | 16 | 16 | 2 | A02031-0038 | 0.435 |  | 0 |  | F43
L3 | CY11701 |  |  | 0 | 0 | 295 | 32 | 32 | 4 | A09031-0038 | 0.1837 |  | 0 |  | F43
L3 | CY11702 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A19131-0038 | 0.1839 |  | 0 |  | F43
L3 | CY11711 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A09331-0038 | 0.1837 |  | 0 |  | F43
L3 | CY11901-0 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02031-0038 | 0.4357 |  | 0 |  | F43
L3 | CY13501 | Gasco 6262 |  | 0 | 0 | 324 | 32 | 32 | 4 | A09331-0038 | 0.1405 |  | 0 |  | F43 | 2017
L3 | CY14001 |  |  | No BOM | #VALUE!
L3 | CY12201 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0040 | 0.5434 |  | 0 |  | F43
L3/L4 | CY12401 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A09031-0038 | 0.143 |  | 0 |  | F43 | 2014
L4 | CY20001 | new part |  | 0 | 0 | 360 | 32 | 32 | 4 | A09031-0038 | 0.143 |  | 0 |  | F43 | 2016
L3/L4 | CY20020 | New |  | 0 | 0 | 324 | 0 | 0 | 0 | A09031-0038 | 0.145 |  | 0 |  | F43 | 2016
L3/L4 | CY20030 | New |  | 0 | 0 | 324 | 0 | 0 | 0 | A09031-0038 | 0.145 |  | 0 |  | F43 | 2016
L3 | CY30001 | New Part |  | 0 | 0 | 180 | 32 | 32 | 4 | A06101-0040 | 0.4625 |  | 0 |  | F43 | 2016
L3 | CY30009 |  |  | 0 | 0 | 295 | 32 | 32 | 4 | A06131-0038 | 0.54 |  | 0 |  | F43 | 2015
L3 | CY30010 |  |  | 0 | 0 | 180 | 32 | 32 | 4 | A06131-0038 | 0.4174 |  | 0 |  | F43 | 2016
L3 | CY30015 | new part |  | 0 | 0 | 231 | 32 | 32 | 4 | A06131-0038 | 0.54 |  | 0 |  | F43 | 2016
L2 | CY90020 | new part |  | 0 | 0 | 155 | 32 | 32 | 4 | A02002-0024 | 0.2102 |  | 0 |  |  | 2016
L2 | CY90030 | new part |  | 0 | 0 | 385 | 32 | 32 | 4 | A02032-0024 | 0.1811 |  | 0 |  |  | 2016
L3 | DM2203 | Ganesh |  | 0 | 0 | 231 | 32 | 32 | 4 | A02001-0036 | 0.6871 | 0.166 | 0 |  |  | 2015
S3 | EB2550 | NOT STND |  | 0 | 0 | 360 | 24 | 24 | 3 | A02032-0028 | 0.3664 | 0.091 | 0 |  | F4
L4 | EB2550 | STND |  | 0 | 0 | 432 | 24 | 24 | 3 | A02032-0028 | 0.3706 | 0.091 | 0 |  | F4
S3 | EB2552 | NOT STND |  | 0 | 0 | 360 | 24 | 4 | 1 | A02032-0028 | 0.3693 |  | 0 |  | F4
L4 | EB2552 | STND |  | 0 | 0 | 432 | 24 | 4 | 1 | A02032-0028 | 0.3736 |  | 0 |  | F4
S3 | EB2553 | NOT STND |  | 0 | 0 | 331 | 24 | 4 | 1 | A02032-0028 | 0.2981 |  | 0 |  | F4 | 2014
L4 | EB2553 | STND |  | 0 | 0 | 498 | 24 | 4 | 1 | A02032-0028 | 0.3023 |  | 0 |  | F4 | 2014
S3 | EB2555 |  |  | 0 | 0 | 360 | 24 | 24 | 3 | A09332-0028 | 0.1204 | 0.03 | 0 |  |  | 2017
S3 | EC3850 | NOT STND |  | 0 | 0 | 463 | 24 | 4 | 1 | A02032-0028 | 0.3636 |  | 0 |  | F4
L4 | EC3850 | STND |  | 0 | 0 | 463 | 24 | 4 | 1 | A02032-0028 | 0.3678 |  | 0 |  | F4
S3 | EC3851 |  |  | 0 | 0 | 312 | 24 | 24 | 3 | A01032-0028 | 0.336 |  | 0
S3 | EC5051 |  |  | 0 | 0 | 405 | 32 | 32 | 4 | A02032-0028 | 0.3841 |  | 0 |  | F21 |  | F21
L3 | EC5053 | STND |  | 0 | 0 | 405 | 32 | 32 | 4 | A02032-0028 | 0.3047 |  | 0 |  | F21 |  | F21
S3 | EC5053 | NOT STND |  | 0 | 0 | 405 | 32 | 32 | 4 | A02032-0028 | 0.3005 |  | 0 |  | F21 |  | F21
S3 | EC5050 | NOT STND |  | 0 | 0
S3 | EC5054 |  |  | 0 | 0 | 405 | 8 | 8 | 1 | A02032-0028 | 0.3713 |  | 0 |  | F21 |  | F21
L3 | EC5055 | obsolete |  | 0 | 0 | 295 | 32 | 32 | 4 | A02032-0028 | 0.3713 |  | 0 |  | F21 |  | F21
S3 | EC5055(1/2) | obsolete |  | 0 | 0 | 295 | 24 | 24 | 3 | A02032-0028 | 0.3636 |  | 0 |  | F21 |  | F21
S4,5,6 | FSN5030 |  |  | 0 | 0 | 360 | 24 | 24 | 3.2 | A06132-0018 | 0.0832 |  | 0
S4,5,6 | FSN5040 |  |  | 0 | 0 | 360 | 24 | 24 | 3.2 | A06132-0018 | 0.0832 |  | 0
S4,5,6 | FSN5050 |  |  | 0 | 0 | 360 | 24 | 24 | 3.2 | A06132-0018 | 0.0832 |  | 0
S4,5,6 | FSN5060 |  |  | 0 | 0 | 360 | 24 | 24 | 3.2 | A06132-0018 | 0.0832 |  | 0
S4,5,6 | FSN8030 |  |  | 0 | 0 | 360 | 24 | 24 | 3.2 | A06132-0018 | 0.0832 |  | 0
S4,5,6 | FSN9540 |  |  | 0 | 0 | 360 | 24 | 24 | 3.2 | A06132-0018 | 0.0816 |  | 0
L2 | FS12 |  |  | 0 | 0 | 382 | 32 | 32 | 4 | A01005-0024 | 0.206 |  | 0 |  |  | 2016
S2 | FS22-10 | new part |  | 0 | 0 | 477 | 24 | 24 | 3 | A01005-0020 | 0.1507 |  | 0 | collet loading |  | 2016
L3 | FT10870 |  |  | 0 | 0 | 240 | 32 | 32 | 4 | A01032-0032 | 0.402 |  | 0 | QBE
L3/L4 | FT11801 |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A02071-0032 | 0.6238 |  | 0 |  | F109 | 2014
L3/L4 | FT11901 |  |  | 0 | 0 | 249 | 16 | 16 | 2 | A02071-0032 | 0.5896 |  | 0 |  | F109 | 2014
L3 | FT12570 |  |  | 0 | 0 | 249 | 32 | 32 | 4 | A01032-0032 | 0.3975 |  | 0 | QBE | F5 |  | F5
L3 | FT13070 | OMSI |  | 0 | 0 | 240 | 32 | 32 | 4 | A01032-0032 | 0.9513 |  | 0 | QBE | F5 |  | F5
S4 | FT13801 |  |  | 0 | 0 | 405 | 24 | 24 | 3 | A02002-0020 | 0.0926 | 0.0349 | 0
L1 | IC75001 |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02032-0038 | 1.0431 |  | 0 |  | F57 | 2017
L1 | IF5050B24(1/2) |  |  | 0 | 0 | 216 | 32 | 32 | 4 | A02032-0032 | 0.8102 |  | 0 |  | F27
L1 | IF5050B26(1/2) |  |  | 0 | 0 | 216 | 32 | 32 | 4 | A02032-0032 | 0.8102 |  | 0 |  | F27 | 2018
L1 | IF6275B25 |  |  | 0 | 0 | 240 | 32 | 32 | 4 | A02032-0038 | 1.1343 |  | 0 |  | F27 | 2016
L1 | IF6275B26 |  |  | 0 | 0 | 240 | 32 | 32 | 4 | A02032-0038 | 1.1343 |  | 0 |  | F27 | 2018
L1 | IF7575B22 |  |  | 0 | 0 | 216 | 32 | 32 | 4 | A02032-0040 | 1.32 |  | 0 |  | F27
L1 | IF7575B27 |  |  | 0 | 0 | 216 | 32 | 32 | 4 | A02032-0040 | 1.32 |  | 0 |  | F27 | 2018
L1 | IF7575B24 |  |  | 0 | 0 | 216 | 8 | 8 | 1 | A02032-0040 | 1.32 |  | 0 |  | F27 | 2016
S3 | M1212002 |  |  | 0 | 0 | 360 | 16 | 16 | 2 | A02032-0022 | 0.1773 | 0.04135 | 0 |  | F4
L3 | M30091 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02002-0032 | 0.5856 |  | 0 |  |  | 2016
L4 | M31071 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0032 | 0.472 |  | 0 |  |  | 2015
L4 | M3800B24 |  |  | 0 | 0 | 324 | 32 | 32 | 4 | A02032-0028 | 0.3792 |  | 0 | QBE | F7 |  | new
S3 | MPC20002-10 |  |  | 0 | 0 | 432 | 32 | 32 | 4 | A09231-0024 | 0.0499 |  | 0 | cnc
S3 | ND3801 |  |  | 0 | 0 | 463 | 24 | 24 | 3 | A02032-0018 | 0.1453 |  | 0
S6 | NL2503 | Backup for Acme |  | 0 | 0 | 543 | 16 | 16 | 2 | A02002-0018 | 0.077 |  | 0
L1 | P5050001 |  |  | 0 | 0 | 270 | 32 | 32 | 4 | A02032-0032 | 0.8639 |  | 0 |  | F58
L1 | P5050001-00 |  |  | 0 | 0 | 270 | 4 | 4 | 1 | A02032-0032 | 0.8639 |  | 0 |  | F58
L1 | P5050B21 |  |  | 8 | 0 | 270 | 32 | 32.0296 | 4 | A02032-0032 | 0.7324 |  | 5.8592 |  | F57
L1 | P5050B21-10 |  |  | 4 | 0 | 324 | 4 | 4.0123 | 1 | A02032-0032 | 0.7324 |  | 2.9296 |  | F57
L1 | P5050B24 |  |  | 4 | 0 | 291 | 4 | 4.0137 | 1 | A02032-0032 | 0.7324 |  | 2.9296 |  | F57
L1 | P5050B25 |  |  | 32 | 0 | 270 | 4 | 4.1185 | 1 | A02032-0032 | 0.7324 |  | 23.4368 |  | F57
L1 | P5075001 | new part |  | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0038 | 1.4125 |  | 0
L1 | P5075001-00 | new part |  | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0038 | 1.4125 |  | 0
L1 | P5075001-10 | new part |  | 0 | 0 | 231 | 0 | 0 | 0 | A02032-0038 | 1.4125 |  | 0
L1 | P7575B21 |  |  | 16 | 0 | 231 | 32 | 32.0693 | 4 | A02032-0038 | 1.1499 |  | 18.3984 |  | F48
L1 | P7575B21-00 |  |  | 16 | 0 | 231 | 32 | 32.0693 | 4 | A02032-0038 | 1.1499 |  | 18.3984 |  | F48
L1 | P7575B31 |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02032-0038 | 1.1499 |  | 0 |  | F48
L1 | P7575B25 |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02032-0038 | 1.1499 |  | 0 |  | F48 | 2017
L1 | P7575B71 |  |  | 16 | 0 | 216 | 16 | 16.0741 | 2 | A01032-0038 | 1.0628 |  | 17.0048 |  | F48
L1 | P7575B71-00 |  |  | 8 | 0 | 216 | 8 | 8.037 | 1 | A01032-0038 | 1.0628 |  | 8.5024 |  | F48
L1 | P5075001 |  |  | 0 | 0 | 180 | 8 | 8 | 1 | A02032-0038 | 1.4137 |  | 0 |  | F48 | 2015
L1 | P7575001 |  |  | 32 | 0 | 231 | 32 | 32.1385 | 4 | A02032-0038 | 1.4125 |  | 45.2 |  | F48
L1 | P7575001-10 |  |  | 4 | 0 | 180 | 4 | 4.0222 | 1 | A02032-0038 | 1.4137 |  | 5.6548
L1 | P7575030 |  |  | 8 | 0 | 231 | 8 | 8.0346 | 1 | A02032-0038 | 1.4125 |  | 11.3 |  | F48
L1 | P7575002 |  |  | 0 | 0 | 231 | 8 | 8 | 1 | A02032-0038 | 1.4137 |  | 0 |  | F48
L1 | PPV10001 |  |  | 0 | 0 | 270 | 32 | 32 | 4 | A02032-0036 | 1.1831 |  | 0 |  |  | 2015
S4,S6 | PWN1016 |  |  | 0 | 0 | 360 | 24 | 24 | 4 | A06032-0014 | 0.0305 |  | 0
S4,5,6 | PWN00100-B | NON STND |  | 0 | 0 | 432 | 16 | 16 | 2 | A02001-0016 | 0.0778 | 0.0449 | 0
S4,5,6 | PWN00400-B | NON STND |  | 0 | 0 | 432 | 16 | 16 | 2 | A02001-0016 | 0.0778 | 0.0449 | 0
S5 | PWN00100-L |  |  | 0 | 0 | 432 | 16 | 16 | 2 | A02001-0016 | 0.0778 |  | 0
S5 | PWN00400-L |  |  | 0 | 0 | 432 | 16 | 16 | 2 | A02001-0016 | 0.0778 |  | 0
S4,5,6 | PWNXXXXX-B |  |  | 0 | 0 | 432 | 4 | 4 | 1 | A02031-0016 | 0.0775 |  | 0 |  |  | 750
S4,5,6 | PWNXXXXX-H |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06021-0016 | 0.0708 | 0.0271 | 0 |  |  | 750
S4,5,6 | PWNXXXXX-HT |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06021-0016 | 0.0708 | 0.0271 | 0 |  |  | 750
S4,5,6 | PWNXXXXX-HS-10 |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06021-0016 | 0.0708 |  | 0
S4,5,6 | PWNXXXXX-BC |  |  | 0 | 0 | 432 | 24 | 24 | 4 | A02031-0018 | 0.0942 |  | 0
S6 | PWN16040-H |  |  | 0 | 0 | 259 | 24 | 24 | 4 | A06032-0018 | 0.0817 |  | 0
S6 | PWN16040BSP-H |  |  | 0 | 0 | 259 | 24 | 24 | 4 | A06032-0018 | 0.0817 |  | 0
S6 | PWN17015-H |  |  | 0 | 0 | 405 | 24 | 24 | 4 | A06032-0014 | 0.0312 |  | 0
S6 | PWN17020-H |  |  | 0 | 0 | 405 | 24 | 24 | 4 | A06032-0014 | 0.0312 |  | 0
S6 | PWN17022-H |  |  | 0 | 0 | 360 | 24 | 24 | 3.2 | A06032-0014 | 0.0312 |  | 0
S4 | PWN17027-H |  |  | 0 | 0 | 405 | 24 | 24 | 3.2 | A06032-0014 | 0.0312 |  | 0
S6 | PWN18011-B |  |  | 0 | 0 | 720 | 24 | 24 | 4 | A02032-0012 | 0.0167 |  | 0
S6 | PWN18015-H |  |  | 0 | 0 | 499 | 8 | 8 | 2 | A06032-0012 | 0.0156 |  | 0
S6 | PWN18016-H |  |  | 0 | 0 | 499 | 8 | 8 | 2 | A06032-0012 | 0.0156 |  | 0
S4/S6 | PWN2007B-B |  |  | 0 | 0 | 421 | 6 | 6 | 1 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2007D-B |  |  | 0 | 0 | 421 | 24 | 24 | 4 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2007C-H |  |  | 0 | 0 | 421 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S4/S6 | PWN2007E-B |  |  | 0 | 0 | 421 | 4 | 4 | 1 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2008B-B |  |  | 0 | 0 | 421 | 4 | 4 | 1 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2008C-H |  |  | 0 | 0 | 420 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S4/S6 | PWN2008D-B |  |  | 0 | 0 | 470 | 24 | 24 | 4 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2009A-B |  |  | 0 | 0 | 470 | 24 | 24 | 4 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2009B-B |  |  | 0 | 0 | 470 | 24 | 24 | 4 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2009B-H |  |  | 0 | 0 | 470 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S4/S6 | PWN2009C-B |  |  | 0 | 0 | 470 | 24 | 24 | 4 | A02061-0012 | 0.031 |  | 0
S4/S6 | PWN2088-H |  |  | 0 | 0 | 470 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S5 | PWN2007A-H |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06061-0012 | 0.0343 |  | 0
S5 | PWN2007C-B |  |  | 0 | 0 | 470 | 4 | 4 | 1 | A02061-0012 | 0.031 | 0.01642 | 0
S5 | PWN2007B-H |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06061-0012 | 0.0343 |  | 0
S5 | PWN2007-H |  |  | 0 | 0 | 421 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S5 | PWN2008A-B |  |  | 0 | 0 | 420 | 4 | 4 | 1 | A02061-0012 | 0.0312 |  | 0
S5 | PWN2008A-H |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06061-0012 | 0.0343 |  | 0
S5 | PWN2008-H |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S5 | PWN2008C-B |  |  | 0 | 0 | 470 | 4 | 4 | 1 | A02061-0012 | 0.031 |  | 0
S5 | PWN2009A-H |  |  | 0 | 0 | 331 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S5 | PWN2009-B |  |  | 0 | 0 | 470 | 4 | 4 | 1 | A02061-0012 | 0.031 | 0.01642 | 0
S5 | PWN2009-H |  |  | 0 | 0 | 330 | 4 | 4 | 1 | A06061-0012 | 0.029 |  | 0
S5 | PWN2010 |  |  | 0 | 0 | 470 | 4 | 4 | 1 | A02061-0012 | 0.031 |  | 0
S3 | PWN2018 | STND |  | 0 | 0 | 540 | 32 | 32 | 5 | A02032-0028 | 0.2412 |  | 0
L4 | PWN2018 | NON STND |  | 0 | 0 | 540 | 32 | 32 | 5 | A02032-0028 | 0.2454 |  | 0
L1 | PWN2019 |  |  | 0 | 0 | 405 | 32 | 32 | 5 | A02032-0024 | 0.197 |  | 0 |  | QBE
L3 | PWN2004 |  |  | 0 | 0 | 348 | 32 | 32 | 5 | A02032-0022 | 0.2599 | 0.1376 | 0
L3 | PWN2024 |  |  | 0 | 0 | 324 | 32 | 32 | 5 | A09032-0022 | 0.0848 | 0.0449 | 0 |  |  | 100 | never run in busy season
S3 | PWN2027-B |  |  | 0 | 0 | 463 | 4 | 4 | 1 | A02061-0012 | 0.031 | 0.01642 | 0
L3/L1 | PWN2076 |  |  | 0 | 0 | 381 | 32 | 32 | 5 | A02032-0024 | 0.2095 |  | 0
L3/L1 | PWN2083 | new part |  | 0 | 0 | 381 | 32 | 32 | 5 | A02032-0024 | 0.2095 |  | 0 |  |  | 2014
S3 | PWN2078 | STND |  | 0 | 0 | 540 | 32 | 32 | 5 | A02032-0028 | 0.239 | 0.11194 | 0
L4 | PWN2078 | NON STND |  | 0 | 0 | 540 | 32 | 32 | 5 | A02032-0028 | 0.2432 | 0.11194 | 0 |  |  | 2014
L1/L3 | PWN2079 |  |  | 0 | 0 | 405 | 32 | 32 | 5 | A02032-0024 | 0.197 | 0.07402 | 0 |  |  | 2014
S3 | PWN4003-B |  |  | 0 | 0 | 341 | 24 | 24 | 4 | A02032-0016 | 0.1545 |  | 0
S4/S6 | PWN400X |  |  | 0 | 0 | 648 | 4 | 4 | 1 | A02061-0008 | 0.0087 |  | 0 | TEMP MATERIAL CODE
S6 | PWN60040-0EA | 2015 |  | 0 | 0 | 259 | 24 | 24 | 4 | A06032-0018 | 0.0817 |  | 0
S5 | PWN65400 |  |  | 0 | 0 | 505 | 24 | 24 | 4 | A02001-0016 | 0.0778 | 0.032 | 0
S3 | PWN65400-A |  |  | 0 | 0 | 476 | 16 | 16 | 3 | A09301-0016 | 0.0254 | 0.0103 | 0
L2 | RCF001 |  |  | 0 | 0 | 300 | 32 | 32 | 5 | A02001-0032 | 0.4923 | 0.2683 | 0 |  |  | 2018
L2 | RCF002 |  |  | 0 | 0 | 360 | 32 | 32 | 5 | A02001-0032 | 0.301 | 0.088 | 0 |  |  | 2017
L2 | RCF003 |  |  | 0 | 0 | 360 | 32 | 32 | 5 | A02001-0026 | 0.2082 | 0.0287 | 0 |  |  | 2018
L2 | RCF201 |  |  | 0 | 0 | 240 | 32 | 32 | 5 | A02001-0032 | 0.5034 | 0.24 | 0 |  |  | 2018
L2 | RCF202 |  |  | 0 | 0 | 300 | 32 | 32 | 5 | A02031-7944 | 0.486 | 0.156 | 0 |  |  | 2018
L2 | RCF303 |  |  | 0 | 0 | 240 | 32 | 32 | 5 | A06201-0024 | 0.1363 | 0.028 | 0 |  |  | 2018
L2 | RCF402 |  |  | 0 | 0 | 240 | 32 | 32 | 5 | A02031-0035 | 0.3278 | 0.14 | 0 |  |  | 2018
L2 | RDF001 |  |  | 0 | 0 | 300 | 32 | 32 | 5 | A02031-0032 | 0.5542 | 0.284 | 0 |  |  | 2018
L2 | RDF901 |  |  | 0 | 0 | 216 | 32 | 32 | 5 | A02001-0040 | 0.8882 | 0.49 | 0 |  |  | 2018
L2 | RDF002 |  |  | 0 | 0 | 216 | 32 | 32 | 5 | A02001-0056 | 1.065 | 0.36 | 0 |  |  | 2018
L2 | RSC1001 |  |  | 0 | 0 | 540 | 32 | 32 | 5 | A09032-0036 | 0.1802 | 0.103 | 0 |  |  | 2014
L2 | RSC1003 |  |  | 0 | 0 | 540 | 32 | 32 | 5 | A09032-0036 | 0.1044 |  | 0 |  |  | 2014
L2 | RSC1002 |  |  | 0 | 0 | 270 | 32 | 32 | 5 | A09032-0036 | 0.2535 |  | 0 |  | F8 | 2014
L2 | RSC1004 |  |  | 0 | 0 | 270 | 32 | 32 | 5 | A02032-0036 | 0.6979 | 0.1891 | 0 |  | F8 | 2014
L2 | RSC1005 |  |  | 0 | 0 | 324 | 16 | 16 | 3 | A09511-0016 | 0.0973 |  | 0 |  |  | 2014
S3 | RSC1006 |  |  | 0 | 0 | 810 | 24 | 24 | 4 | A09002-0020 | 0.0328 |  | 0 |  |  | 2014
S3/S5 | RSC1016 |  |  | 0 | 0 | 341 | 24 | 24 | 4 | A02031-0016 | 0.1077 |  | 0
L3 | S68S14001-L | Tooling |  | 0 | 0 | 261 | 32 | 32 | 4 | A06132-0024 | 0.2136 |  | 0
S1 | SA1201 |  |  | 0 | 0 | 498 | 24 | 24 | 3 | A02022-0022 | 0.235 |  | 0
S1 | SA2501 |  |  | 0 | 0 | 498 | 24 | 24 | 3 | A02022-0022 | 0.235 |  | 0
S2 | SA2509 |  |  | 0 | 0 | 432 | 24 | 24 | 3 | A02031-0018 | 0.133 |  | 0
S2 | SA3801 |  |  | 0 | 0 | 498 | 0 | 0 | 0 | A02022-0022 | 0.235 |  | 0
L3 | SF1601 |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02042-0028 | 0.4999 | 0.1607 | 0 |  | F3 | 2017
L3 | SF5001 |  |  | 0 | 0 | 231 | 32 | 32 | 4 | A02042-0028 | 0.4999 | 0.1891 | 0 |  | F3 | 2015
L3 | SF5002 |  |  | 0 | 0 | 231 | 4 | 4 | 1 | A02042-0028 | 0.4999 | 0.188 | 0 |  | F3 | 2015
L3 | SF5051 | Moved from CNC |  | 0 | 0 | 231 | 4 | 4 | 1 | A02042-0028 | 0.4999 | 0.188 | 0 |  | F3 | 2018
L3 | SN5001 | new part |  | 0 | 0 | 231 | 8 | 8 | 1 | A02042-0028 | 0.5319 | 0.188 | 0 |  | F3 | 2016
S1 | SP1201-1 |  |  | 0 | 0 | 810 | 8 | 8 | 1 | A02022-0018 | 0.1102 |  | 0
S1 | SP2501 |  |  | 0 | 0 | 810 | 24 | 24 | 3 | A02022-0018 | 0.1197 |  | 0
S1/S2 | SP2502 |  |  | 0 | 0 | 810 | 24 | 24 | 3 | A02022-0018 | 0.1197 |  | 0
S1/S2 | SP2505 |  |  | 0 | 0 | 810 | 16 | 16 | 2 | A02022-0018 | 0.1197 |  | 0
S1 | SP2506 | new part |  | 0 | 0 | 810 | 4 | 4 | 1 | A02022-0018 | 0.1197 |  | 0 |  |  |  | runs w/ SP2501 only
S2 | SP2509 |  |  | 0 | 0 | 810 | 24 | 24 | 3 | A02001-0013 | 0.0532 |  | 0
S1/S2 | SP2550 |  |  | 0 | 0 | 810 | 8 | 8 | 1 | A02022-0018 | 0.1197 |  | 0
S3 | SP3806 | NONSTND |  | 0 | 0 | 432 | 4 | 4 | 1 | A02032-0028 | 0.3052 | 0.1193 | 0 |  |  |  | runs w/ SP5063 only
S3 | SP5055 | NON STND |  | 0 | 0 | 432 | 32 | 32 | 4 | A02032-0028 | 0.3001 | 0.1283 | 0 |  | F13 |  | F13
S3 | SP5056 | NON STND |  | 0 | 0 | 390 | 32 | 32 | 4 | A02032-0028 | 0.3235 | 0.1286 | 0 |  | F13 |  | F13
S3 | SP5057 | NON STND |  | 0 | 0 | 405 | 8 | 8 | 1 | A02032-0028 | 0.2708 | 0.098 | 0 |  | F13 |  | F13
S3 | SP5063 | NON STND |  | 0 | 0 | 432 | 8 | 8 | 1 | A02032-0028 | 0.3052 | 0.12364 | 0 |  | F13 |  | F13
L4 | SP3806 | STND |  | 0 | 0 | 432 | 4 | 4 | 1 | A02032-0028 | 0.3095 | 0.1193 | 0 |  |  |  | runs w/ SP5063 only
L4 | SP5055 | STND |  | 0 | 0 | 432 | 32 | 32 | 4 | A02032-0028 | 0.3043 | 0.1283 | 0
L4 | SP5056 | STND |  | 0 | 0 | 390 | 32 | 32 | 4 | A02032-0028 | 0.3235 | 0.1286 | 0 |  | F13 |  | F13
L4 | SP5057 | STND |  | 0 | 0 | 432 | 8 | 8 | 1 | A02032-0028 | 0.275 | 0.098 | 0 |  | F13 |  | F13
L4 | SP5060 |  |  | 0 | 0 | 381 | 16 | 16 | 2 | A02032-0032 | 0.3768 | 0.12364 | 0 |  | F13 |  | F13
L4 | SP5062 |  |  | 0 | 0 | 432 | 16 | 16 | 2 | A02032-0030 | 0.3284 | 0.1478 | 0 |  | F13 |  | F13
L4 | SP5063 | STND |  | 0 | 0 | 432 | 8 | 8 | 1 | A02032-0028 | 0.3095 | 0.1236 | 0 |  | F13 |  | F13
L4 | SP5066 | new part |  | 0 | 0 | 432 | 4 | 4 | 1 | A02032-0028 | 0.3095 | 0.1272 | 0 |  | F13 |  | runs w/ SP5055 only
S6 | SR2501 |  |  | 0 | 0 | 450 | 24 | 24 | 3 | A02002-0020 | 0.2199 | 0.08886 | 0
L3 | ST1601-10 |  |  | 0 | 0 | 432 | 32 | 32 | 4 | A02032-8019 | 0.2555 |  | 0
S3 | ST1960-C |  |  | 0 | 0 | 463 | 24 | 24 | 3 | A02032-0022 | 0.1796 |  | 0
S1 | ST1A01 |  |  | 0 | 0 | 498 | 8 | 8 | 1 | A02022-0022 | 0.2143 |  | 0
S1 | ST2A01B |  |  | 0 | 0 | 540 | 8 | 8 | 1 | A02022-0022 | 0.2143 |  | 0
S1 | ST2A01F |  |  | 0 | 0 | 498 | 24 | 24 | 3 | A02022-0022 | 0.2143 |  | 0
S1 | ST2A01G |  |  | 0 | 0 | 498 | 8 | 8 | 1 | A02022-0022 | 0.2143 |  | 0
S2 | ST2A02 |  |  | 0 | 0 | 498 | 24 | 24 | 3 | A02031-0018 | 0.1347 |  | 0
S1 | ST3A01 |  |  | 0 | 0 | 498 | 8 | 8 | 1 | A02022-0022 | 0.2143 |  | 0
S1 | ST3A01B |  |  | 0 | 0 | 405 | 8 | 8 | 1 | A02022-0022 | 0.2143 |  | 0
S3 | TC0211 |  |  | 0 | 0 | 405 | 24 | 24 | 3 | A02031-0020 | 0.17 |  | 0 |  | F133
S3 | TC0216 |  |  | 0 | 0 | 405 | 24 | 24 | 3 | A02031-0020 | 0.1928 |  | 0 |  | F133
S3 | TC0217 |  |  | 0 | 0 |  |  | 24 |  | A02031-0020 | 0.1642 |  | 0 |  | F133
L3 | TC1280 |  |  | 0 | 0 | 240 | 32 | 32 | 4 | A02032-0032 | 0.7615 | 0.442 | 0 |  |  | 2017
L4 | TC1609 |  |  | 0 | 0 | 463 | 32 | 32 | 4 | A02032-0026 | 0.4415 |  | 0 |  | F25 |  | F25
L4 | TC1610 |  |  | 0 | 0 | 384 | 32 | 32 | 4 | A02032-0026 | 0.4396 |  | 0 |  | F25 |  | F25
S6 | TRV2523 |  |  | 0 | 0 | 450 | 24 | 24 | 3 | A09002-0020 | 0.0575 |  | 0
L1/L2/L4 | VC10071 |  |  | 0 | 0 | 154 | 16 | 16 | 2 | A01032-0038 | 1.6531 | 0.6606 | 0 |  |  | 2016
Formulas:
DATE = WORKDAY([DATE, row above],ROUNDUP([DAYS, row above],0))
DATE = WORKDAY([DATE, row below],ROUNDUP([DAYS, row below],0))
Note on K18: Rob Douglas: Hold for release at Corey
Note on B28: Rob Douglas: S5650-0NA
Note on G28: Ken Mcguire: tell Cindy, this is the new rate 8/24
Note on K28: Rob Douglas: Hold for release at Corey
Note on B35: Rob Douglas: Same as P7575B25 Different tap location
Note on B37: Rob Douglas: same as P7575B21 Different tap location
Note on B47: Rob Douglas: Same as IF5050B26 with stamp Rob Douglas: Reference IF5050B24-10
Note on B48: Rob Douglas: Same as IF5050B24 without stamp
Note on B49: Rob Douglas: Same as IF6275B26 with Stamp
Note on K49: Rob Douglas: 10k 9/12
Note on B50: Rob Douglas: Same as IF6275B25 without stamp
Note on B51: Rob Douglas: Same as IF7575B27 with stamp
Note on B52: Rob Douglas: Same as IF7575B22 without stamp
Note on C55: Rob Douglas: review closer to run time, usage is off pace for 2018
Note on D55: Rob Douglas: Review closer to run time
Note on E55: Rob Douglas: Review closer to run time
Note on C56: Chelsea Garrison: Make PO for OP Cleaning
Note on K57: Rob Douglas: 8/31
Note on K63: Rob Douglas: 8100# on hand 8/24
Note on K64: Rob Douglas: 8/31
Note on K76: Rob Douglas: 5k 9/7
Note on R79: Rob Douglas: was 10/1
Note on B80: SH: want to run this is slow time- never in busy season when scheduled a quantiy must be picked that will satisfy this condition
Note on K80: Rob Douglas: 8/31 Thyssen-Krupp
Note on B81: SH: must be round corner
Note on B82: SH: SH: must be round corner SH: NEEDS A15 OR A16 - PICKOFF BACK CHAMFER TO AVOID DEBURR OP
Note on B83: SH: must be round corner
Note on B84: SH: round corner only
Note on B85: SH: round corner only
Note on C85: Amanda Wadley: Review quote sheet as parts run - monitoring material
Note on B98: Rob Douglas: Gasco Rob Douglas: CY135-AX1TXG
Note on B101: Rob Douglas: CY102-AA
Note on B103: Rob Douglas: Same as CY30009 with a different thread
Note on B104: Rob Douglas: Same as CY30015 with a different thread
Note on B111: Rob Douglas: Praxair CY145-AP3XXP 30K per quarter usage of -P
Note on B114: Rob Douglas: CY106-LD
Note on K131: Rob Douglas: 4k on hand 9/6
Note on K132: Rob Douglas: 10k 8/31
Note on H133: SH: 3 hour setup within family
Note on B156: Rob Douglas: EB2550-4XA
Note on K156: Rob Douglas: 8/17 Sapa (Hydro Extrusions)
Note on B157: Rob Douglas: EB2550-1AA Reference Rob Douglas: EB2550-4AA also
Note on C157: Amanda Wadley: Review quote sheet as parts run - monitoring material
Note on L157: Chelsea Garrison: EDIT IF GOING ON S3 SCRAP: -0.27540
Note on B158: Rob Douglas: Run with EB2550
Note on K168: Rob Douglas: 1k on hand 8/24 Rob Douglas: 5K 9/12
Note on L172: Amanda Wadley: need to edit bom if going on a small hydro scrap -.0455
Note on R179: Rob Douglas: was 9/15
Note on R203: Rob Douglas: was 9/10
Note on B235: Rob Douglas: Similarto RCF001
Note on C245: Amanda Wadley: ON MATERIAL WATCH - MAKE SURE PART RUNS AS QUOTE SHEET IS SETUP
Note on C254: Chelsea Garrison: Make PO for cleaning
Note on K254: Rob Douglas: 10k mill minimum 8 week lead time
Note on B258: SH: run a minimum of 4 releases at a time per Ken… setup is a bogger.
Note on B260: Rob Douglas: Same as 301868-1-C Different Plating
Note on C262: awadley: 25 cp's in PR
Note on C268: awadley: 8 -CP'S in PR
Note on G271: SH: 3000 safety on no dash
Note on G272: SH: 808 safety on no dash
Note on B274: Rob Douglas: Same as 143124-1-C Different Plating
Note on K279: SH: get a bar of brass for setups
Note on B285: SH: round corner only
Note on B286: SH: SH: must be round corner SH: NEEDS A15 OR A16 - PICKOFF BACK CHAMFER TO AVOID DEBURR OP
Note on B287: SH: must be round corner
Note on B288: SH: must be round corner
Note on B289: SH: round corner only
Note on B290: SH: SH: must be round corner SH: NEEDS A15 OR A16 - PICKOFF BACK CHAMFER TO AVOID DEBURR OP
Note on B291: SH: round corner only
Note on C291: Amanda Wadley: Review quote sheet as parts run - monitoring material
Note on B292: Rob Douglas: Same as WP5008 Different Stock
Note on C292: Amanda Wadley: Review quote sheet as parts run - monitoring material
Note on B293: SH: must be round corner
Note on H297: awadley: IM is wrong
Note on K324: SH: stocking item central need lead time sometimes
Note on B326: Rob Douglas: Praxair CY145-AP3XXP 30K per quarter usage of -P
Note on C327: Chelsea Garrison: Make PO for OP-Cleaning
Note on B330: Rob Douglas: Reference 30213REVC
Note on B331: Rob Douglas: CY102-AA
Note on C338: awadley: NEED FINISHED WEIGHT
Note on K338: SH: stocking item central need lead time sometimes
Note on K345: SH: stocking item central need lead time sometimes
Note on B350: Rob Douglas: Same as CY30015 with a different thread
Note on C350: Chelsea Garrison: Make PO for OP cleaning
Note on B352: Rob Douglas: Same as CY30009 with a different thread
Note on B356: Rob Douglas: EB2550-1AA Reference Rob Douglas: EB2550-4AA also
Note on C356: Amanda Wadley: Review quote sheet as parts run - monitoring material
Note on L356: Chelsea Garrison: EDIT IF GOING ON S3 SCRAP: -0.27540
Note on B357: Rob Douglas: EB2550-1AA Reference Rob Douglas: EB2550-4AA also
Note on C357: Amanda Wadley: Review quote sheet as parts run - monitoring material
Note on L358: awadley: EDIT BOM IF GOING ON A SMALL HYDRO. SCRAP -.2800
Note on B360: Rob Douglas: Check With Dan Lammers Before Running
Note on L360: Amanda Wadley: IF GOING ON SMALL HYDRO SCRAP -.1458
Note on B361: Rob Douglas: Check with Dan Lammers Before Running
Note on B362: Rob Douglas: EB2550-4XA
Note on L363: awadley: EDIT BOM IF GOING ON A SM HYDRO. SCRAP -.2205
Note on L368: Stephanie Smith: If going on the small Hydromat scrap is -.2018
Note on K379: SH: material gets arrow stamped before running
Note on C382: Amanda Wadley: Review quote sheet as parts run - monitoring material
Note on Q390: Rob Douglas: Eliminated 2nd op Drill/Tap (Inverted Flair)
Note on Q394: Rob Douglas: Eliminated 2nd op Drill/Tap (Inverted Flair)
Note on B395: Rob Douglas: Run with EB2550
Note on B398: Rob Douglas: Reference M38N-0ACN
Note on L401: Stephanie Smith: IF RUNNING ON THE SMALL HYDRO CHANGE SCRAP TO -.0511
Note on H415: awadley: IM IS WRONG
Note on H416: awadley: IM IS WRONG
Note on L424: Amanda Wadley: EDIT BOM IF GOING ON A SMALL HYDRO SCRAP -.0420
Note on L425: Amanda Wadley: EDIT BOM IF GOING ON A SMALL HYDRO SCRAP -.0433
Note on L467: awadley: EDIT BOM IF GOING ON A LRG HYDRO. SCRAP -.1333
Note on B470: SH: want to run this is slow time- never in busy season when scheduled a quantiy must be picked that will satisfy this condition
Note on K470: SH: material has 6 week lead time - Tristar
Note on L475: Amanda Wadley: EDIT BOM IF GOING ON A LARGE HYDRO SCRAP -.1312
Note on L480: Amanda Wadley: need to edit bom if going on a small hydro scrap -.0455
Note on L481: awadley: NEED TO EDIT BOM SCRAP -.0151 awadley: AND EDIT MATERIAL CODE TO PULL HYDRO MATERIAL
Note on K486: Rob Douglas: 5k mill minimum
Note on C492: Chelsea Garrison: Make PO for OP Cleaning
Note on C493: Chelsea Garrison: Make PO for OP Cleaning
Note on C494: Chelsea Garrison: Make PO for OP Cleaning
Note on K494: Ken Mcguire: confirming with Steve S. 11/10
Note on K496: Ken Mcguire: purchased from Tri-star metals
Note on C497: Chelsea Garrison: Make PO for OP Cleaning
Note on B499: Ken Mcguire: review tooling, we will be short
Note on C502: Amanda Wadley: "Review quote sheet as parts run-monitoring material"
Note on C514: Amanda Wadley: "Review quote sheet as parts run-monitoring material"
Note on L516: Amanda Wadley: IF RUNNING ON A SMALL HYDRO EDIT BOM: SCRAP -.1859
Note on L517: Amanda Wadley: EDIT BOM IF GOING ON A SMALL HYDRO SCRAP -.1718
Note on L519: awadley: NEED TO EDIT BOM IF GOING ON A SMALL HYDRO SCRAP -.1728
Note on L520: awadley: EDIT BOM IF GOING ON SM HYDRO SCRAP -.1816
Note on B528: Rob Douglas: Option Make from SP5055 Requires Secondary Cross Hole
Note on C536: Amanda Wadley: "Review quote sheet as parts run-monitoring material"

## Material Bar Weights
427926 | ALUMINUM | 41.71 | Saw Wgt .4021 / L5 Wgt .2438
A01001-0016 | 1/2 | 8.02
A01001-0034 | 1-1/16 | 36.2 | NOTE: 6 ft threaded rod from McMaster Carr
A01001-0046 | 1-3/8" RND STEEL | 66.26
A01001-0048 | 1-1/2 | 72.14
A01002-0020 | 5/8 | 13.81
A01002-0024 | 3/4 | 19.89
A01002-0028 | 0.875 | 27.07
A01002-0032 | 1 | 35.35
A01002-0038 | 1-3/16 | 49.86
A01002-0040 | 1-1/4 | 55.24
A01002-0042 | 1-5/16 | 60.9
A01005-0016 | 1/2 | 8.02
A01005-0016 | 0.5 | 8.84
A01005-0020 | 5/8 | 13.81
A01005-0024 | 3/4 | 19.89
A01032-0016 | 1/2 | 8.84
A01032-0028 | 7/8 | 27.07
A01032-0038 | 1-3/16 | 49.86
A01101-0026 | 13/16 | 21.17
A01101-0030 | 15/16 | 28.18
A01101-0034 | 1-1/16 | 36.2
A01101-0042 | 1-5/16 | 55.23
A01102-0026 | 13/16 | 23.34
A01102-0030 | 15/16 | 31.07
A01102-0034 | 1-1/16 | 39.91
A01102-0040 | 1-1/4 | 55.24
A01102-0044 | 1-3/8 | 66.84
A01102-0046 | 1-7/16 | 73.01
A01102-0052 | 1-5/8 | 93.36
A01102-0056 | 1-3/4 | 108.27
A01102-0060 | 1-7/8 | 124.29
A01102-0064 | 2 | 141.42
A01132-0032 | 1 | 35.35
A01132-0034 | 1-1/16 | 39.91
A01132-0040 | 1-1/4 | 55.24
A01132-0052 | 1-5/8 | 93.36
A01132-0064 | 2 | 141.42
A01301-0088 | 2.75 ground | 243
A01301-0112 | 3-1/2 8620 Steel | 392.52
A01301-0160 | 5 | 801.84
A01401-0006 | 3/16 | 4
A01461-7194 |  | 1.2 | Need Verification
A01461-73154 |  | 1.6 | Need Verification
A01701-0020 |  | 2.094 | Need Verification
A01701-0022 |  | 2.72 | Need Verification
A01701-0024 | 3/4 | 3.352
A01701-0040 | 1 1/4 Virgin PFTE | 13.8
A02001-0006 | 3/16 | 1.22
A02001-0008 | 1/4 | 2.17
A02001-0010 | 5/16 | 3.39
A02001-0012 | 3/8 | 4.88
A02001-0013 | 13/32 | 5.73
A02001-0014 | 7/16 | 6.65
A02001-0016 | 1/2 | 8.68
A02071-0016 | 1/2 | 8.68
A02001-0005 | 5/32" Rnd Brass | 0.8484
A02001-0018 | 9/16 | 10.99
A02071-0018 | 9/16 | 10.99
A02001-0020 | 5/8 | 13.56
A02071-0020 | 5/8 | 13.56
A02001-0022 | 11/16 | 16.41
A02071-0022 | 11/16 | 16.41
A02001-0024 | 3/4 | 19.53
A02071-0024 | 3/4 | 19.53
A02001-0026 | 13/16 | 22.95
A02071-0026 | 13/16 | 22.95
A02001-0028 | 7/8 | 26.58
A02071-0028 | 7/8 | 26.58
A02071-0030 | 15/16 | 30.52
A02001-0032 | 1 | 34.72
A02071-0032 | 1 | 34.72
A02001-0034 | 1-1/16 | 39.2
A02071-0034 | 1-1/16 | 39.2
A02001-0036 | 1-1/8 | 43.94
A02071-0036 | 1-1/8 | 43.94
A02001-0038 | 1-3/16 | 49
A02071-0038 | 1-3/16 | 49
A02031-0038 | 1-3/16 | 49
A02001-0040 | 1-1/4 | 54.25
A02031-0040 | 1-1/4 | 54.25
A02071-0040 | 1-1/4 | 54.25
A02001-0042 | 1-5/16 | 59.81
A02071-0042 | 1-5/16 | 59.81
A02001-0044 | 1-3/8 | 65.64
A02071-0044 | 1-3/8 | 65.64
A02001-0046 | 1-7/16 | 71.75
A02071-0046 | 1-7/16 | 71.75
A02001-0048 | 1-1/2 | 78.12
A02071-0048 | 1-1/2 | 78.12
A02001-0050 | 1-9/16 | 84.77
A02071-0052 | 1-5/8 | 91.68
A02001-0056 | 1-3/4 | 106.33
A02071-0056 | 1-3/4 | 106.33
A02091-0056 | 1-3/4 | 106.33
A02001-0058 | 1-13/16 | 114.06
A02001-0060 | 1-7/8 | 122.07
A02031-0060 | 1-7/8 | 122.07
A02071-0060 | 1-7/8 | 122.07
A02001-0064 | 2 | 138.88
A02071-0064 | 2 | 138.88
A02001-0068 | 2-1/8 | 156.79
A02071-0068 | 2-1/8 | 156.79
A02001-0072 | 2-1/4 | 175.8
A02071-0072 | 2-1/4 | 175.8
A02001-0076 | 2-3/8 | 195.85
A02071-0076 | 2-3/8 | 195.85
A02001-0080 | 2-1/2 | 217.01
A02071-0080 | 2-1/2 | 217.01
A02001-0088 | 2-3/4 | 262.58
A02071-0088 | 2-3/4 | 262.58
A02001-0096 | 3 | 312.49
A02071-0096 | 3 | 312.49
A02001-0112 | 3-1/2 | 425.33
A02071-0112 | 3-1/2 | 425.33
A02001-0128 | 4 | 555.53
A02071-0128 | 4 | 555.53
A02001-0144 | 4-1/2 X 8ft | 469
A02071-0144 | 4-1/2 X 8ft | 469
A02001-0152 | 4-3/4 X 8ft | 524.64
A02071-0152 | 4-3/4 X 8ft | 524.64
A02071-0176 | 5-1/2 | 700.24
A02002-0010 | 5/16 | 3.74
A02002-0012 | 3/8 | 5.38
A02002-0014 | 7/16 | 7.33
A02002-0016 | 1/2 | 9.57
A02002-0018 | 9/16 | 12.11
A02002-0020 | 5/8 | 14.96
A02002-0022 | 11/16 | 18.1
A03002-0022 | 11/16 | 18.1
A02002-0024 | 3/4 | 21.54
A02002-0026 | 13/16 | 25.27
A02002-0028 | 7/8 | 29.31
A03002-0028 | 7/8 | 29.31
A02002-0030 | 15/16 | 33.65
A02002-0032 | 1 | 38.29
A02002-0034 | 1-1/16 | 43.22
A02002-0036 | 1-1/8 | 48.45
A02002-0038 | 1-3/16 | 54.03
A02002-0040 | 1-1/4 | 59.82
A02002-0042 | 1-5/16 | 65.95
A02002-0044 | 1-3/8 | 72.38
A02002-0048 | 1-1/2 | 86.14
A02002-0052 | 1-5/8 | 101.1
A02002-0054 | 1-11/16 | 109
A02002-0056 | 1-3/4 | 117.25
A02042-0056 | 1-3/4 | 117.25
A02002-0060 | 1-7/8 | 134.6
A02002-0064 | 2 | 153.14
A02002-0068 | 2-1/8 | 172.88
A02002-0072 | 2-1/4 | 193.82
A02002-0080 | 2-1/2 | 239.3
A02003-0020 | 0.625 | 17.27
A02005-0022 | 11/16 | 18.1
A02006-0005 | 5/32 | 0.23
A02016-0036 | 1-1/8 | 34.128
A02022-0018 | 9/16 | 12.11
A02022-0022 | 11/16 | 18.1
A02031-0012 | 3/8 | 4.88
A02031-0016 | 1/2 | 8.68
A02031-0018 | 9/16 | 10.99
A02031-00198 | 19.8/32 | 13.29
A02031-0020 | 5/8 | 13.56
A02031-0032 | 1" | 34.72
A02031-71085 | 1.085 | 40.87
A02031-7877 | .877 | 26.7
A02031-7986 | 0.986 | 33.76
A02032-0016 | 1/2 | 9.57
A02032-0018 | 9/16 | 12.11
A02032-0022 | 11/16 | 18.1
A02032-0024 | 3/4 | 21.54
A02032-0026 | 13/16 | 25.27
A02032-0028 | 7/8 | 29.31
A02032-0030 | 15/16 | 33.65
A02032-0032 | 1 | 38.29
A02032-0036 | 1-1/8 | 48.45
A02032-0038 | 1-3/16 | 54.03
A02032-0040 | 1-1/4 | 59.82
A02032-0044 | 1-3/8 | 72.38
A02042-0028 | 7/8 | 29.31
A02042-0034 | 1-1/16 | 43.22
A02042-0046 | 1-7/16 | 79.11
A02042-0052 | 1-5/8 | 101.1
A02061-0008 | 1/4 | 2.17
A02061-0012 | 3/8 | 4.63
A02061-71115 | 1.115 -ground | 43.94
A02072-0024 | 3/4 | 21.54
A03001-0012 | 3/8 Lead free | 4.88
A03001-0016 | 1/2 | 8.68
A03001-0016 | 0.5 | 8.68
A03001-0020 | 5/8 Lead -Free | 13.56
A03001-0024 | 3/4 | 19.53
A03001-0028 | 7/8 | 26.58
A03001-0036 | 1-3/16" Lead Free | 48.96
A03002-0026 | 13/16 | 25.27
A04001-0028 | 7/8 | 26.58
A05501-0028 | 7/8" Rnd Black Delrin | 3.71
A06001-0004 | 1/8 | 0.5004
A06001-0010 | 5/16 | 3.13
A06021-0012 | 3/8 | 4.55
A06021-0016 | 1/2 | 8.1
A06032-0014 | 7/16 | 6.84
A06101-00035 | 7/64" Rnd 303 Stainless | 3.5
A06101-0005 | 5/32 | 0.81
A06101-0008 | 1/4" 303 Stainless steel | 2.06
A06101-0010 | 5/16" | 3.23
A06101-0012 | 3/8 | 4.65
A06101-0013 | 13/32" 303 Stainless | 5.29
A06101-0016 | 1/2" 303 Stainless | 8.01
A06101-0018 | 9/16 | 10.45
A06101-0020 | 5/8" 303 Stainless | 12.52
A06101-0024 | 3/4 | 18.02
A06101-0034 | 1-1/16" 303 Stainless Steel | 37.29
A06101-0036 | 1-1/8" 303 Stainless Steel | 40.56
A06101-0038 | 1-3/16" Rnd 303 Stainless | 46.59
A06101-0040 | 1-1/4 Rnd 303 Stainless | 50.08
A06101-0042 | 1-5/16" Rnd 303 Stainless | 55.2
A06101-0044 | 1-3/8 | 62.46
A06101-0072 | 2-1/4 | 167.24
A06102-0024 | 3/4 | 20.49
A06102-0032 | 1" | 35.33
A06131-0018 | 9/16 | 10.45
A06131-0038 | 1 3/16" 303 Stainless Steel | 45.23
A06132-0018 | 9/16 | 11.53
A06132-0024 | 3/4 | 20.49
A06135-0024 | 3/4 | 20.49
A06153-0016 | 0.5 | 10.52
A06201-0003 | 3/32 | 0.29
A06201-0006 | 3/16 | 1.16
A06201-0008 | 1/4 | 2.06
A06201-0010 | 5/16 | 3.23
A06201-0012 | 3/8 | 4.65
A06201-0014 | 7/16 | 6.763
A06201-0016 | 1/2 | 8.26
A06201-0018 | 9/16 | 10.14
A06201-0020 | 0.625 | 12.9
A06201-0024 | 3/4 | 18.58
A06201-0032 | 1 | 32.04
A06201-0026 | 13/16 | 21.81
A06201-0028 | 7/8 | 25.29
A06201-0044 | 1-3/8" | 60.59
A06201-0048 | 1-1/2" | 72.1
A06201-0050 | 1-9/16 | 78.24
A06201-0060 | 1-7/8 | 112.7
A06201-0064 | 2" | 128.2
A06201-0072 | 2-1/4 | 162.2
A06201-0080 | 2-1/2 | 200.3
A06201-0096 | 3" | 288.4
A06201-0112 | 3-1/2 | 392.5
A06202-0010 | 5/16 | 3.56
A06202-0012 | 3/8 | 5.12
A06202-0014 | 7/16 | 6.97
A06202-0016 | 1/2 | 9.11
A06202-0024 | 3/4 | 20.49
A06202-0026 | 13/16 | 24.05
A06202-0028 | 7/8 | 27.89
A06202-0032 | 1 | 36.43
A06202-0036 | 1-1/8 | 44.72
A06202-0040 | 1-1/4 | 55.21
A06202-0044 | 1-3/8 | 66.8
A06202-0048 | 1-1/2" Hex 316 Stainless | 79.5
A06202-0056 | 1-3/4 | 108.5
A06202-0080 | 2-1/2 | 165
A06232-0024 | 3/4" 316 Stainless Steel | 20.49
A06261-0006 | 3/16 | 1.16
A06403-0032 | 1" | 40.8
A06501-0048 | 1-1/2 304 Stainless | 72.1
A06501-0088 | 2-3/4 304 Stainless | 242.3
A06501-0096 | 3" | 288.4
A06501-0112 | 3-1/2 304 Stainless | 392.5
A06501-0128 | 4' Rnd 304 | 512.8
A06502-0020 | 5/8" 304 | 13.8
A06432-8017 | 17mm | 15.99
A08031-0124 | .750 1144 Med Carbon | 18.04
A08031-0185 | .560 1144 Med Carbon | 10.05
A09001-0012 | 3/8 | 1.59
A09001-0016 | 0.5 | 2.83
A09001-0020 | 5/8 | 4.42
A09001-0024 | 3/4 | 6.234
A09001-0028 | 0.875 | 8.485
A19101-0028 | 0.875 | 8.485
A09001-0056 | 1-3/4 | 34.67
A09002-0014 | 7/16 | 2.39
A09002-0020 | 5/8 | 4.88
A09031-0032 | 1 | 11.32
A09031-0038 | 1-3/16 | 15.98
A09032-0036 | 1-1/8" Hex 6262 Alum | 15.8
A09201-0010 | 5/16 | 1.11
A09201-0012 | 0.375 | 1.59
A09201-0020 | 5/8" 2011 ALUM. RND | 4.42
A09511-0016 | 0.5 | 2.31
A11001-0048 | 1-1/2 | 72.17
A19101-0008 | 1/4 | 0.71
A19101-0012 | 3/8 | 1.59
A19101-0016 | 1/2 | 2.83
A19101-0020 | 5/8 | 4.42
A19101-0022 | 11/16 | 5.35
A19101-0032 | 1" | 11.32
A19101-0036 | 1-1/8 | 14.03
A19101-0050 | 1-9/16 | 27.06
A19102-0014 | 0.875 | 2.39
A19102-0056 | 1-3/4 | 38.23
A19132-0022 | 11/16 | 5.9
A06202-0022 | 0.6875 | 16.7
A01001-0073 | 2-5/16 | 171.4
A06101-7314 | .314 Ground 303 | 3.56
A06501-0060 | 1-7/8 316 | 112.7
A19101-0060 | 1-7/8" Rnd 6061 | 38.96
A06201-0036 | 1-1/8" Rnd 316 S.S. | 40.56
A06201-0054 | 1-11/16" Rnd 316 S.S | 91.5
A06201-0052 | 1-5/8" Rnd 316 S.S. | 84.62
A01216-6021 | 1/4 X 1/2 1018 | 5.1
A02032-0020 | 15/16 | 33.65
A19101-0042 | 1-5/16" Rnd 6061 | 19.09
A19101-0044 | 1-3/8 rnd 6061 | 1.746
A03002-0038 | 1-3/16" Hex LF | 54.03
A06501-0160 | 5" Rnd 304L | 801
A06001-0040 | 1-1/4" Rnd 416 | 50.08
A06461-0008 | .2505 Rnd 304 SS | 2.06
A06401-0010 | .2505 Rnd 304 SS | 3.23
A06202-0020 | 5/8 Hex 316 | 13.8