## Master
Control Devices LLC Work Order Production Record
[6 empty] | Machine No. |  | D1 |  | Acme / Davenport Only | [7 empty] | Setup Allowed Hrs. |  |  | 8
[6 empty] | Rev Letter |  | B |  | Wgt/Bar | 5.73 | Total Bars |  | 490.8144 |  |  |  | Setup Actual Hrs. |  |  | 3
Part No. | SP2513 |  |  |  |  | Planned Pcs/Hr |  | 516 |  | Bars/Load | 5 | Total Loads |  | 98.1629 |  |  |  | Setup % |  |  | 266.7%
Order No. | 321158 |  |  |  |  | Remaining Loads |  | 23.1629 |  | Wgt/Pc | 0.0373 | Pcs/Bar |  | 153.6193
Order Qty | 75000 | [8 empty] | Matr. # | A02001-0013
Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Loads | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes
|  | beginning balance | [5 empty] | 0 | 75000
2014-02-10 | rr | 3119 | 2 | 3 | 2 | 1536.193 | 7.5 | 1536.193 | 73463.807 | 1032 | 1536.193 | 148.9% |  | 2758144 |  | 2.5 | 1 | 0 | wait FAIR
2014-02-11 | rr | 3119 | 8 | 0 | 7 | 5376.6756 | 8 | 6912.8686 | 68087.1314 | 4128 | 5376.6756 | 130.2% |  | 2758144 |  | 0 | 0 | 0
2014-02-12 | rr | 3119 | 8 | 0 | 7 | 5376.6756 | 8 | 12289.5442 | 62710.4558 | 4128 | 5376.6756 | 130.2% |  | 2758144 |  | 0 | 0 | 0
2014-02-13 | rr | 3119 | 6.6 | 0 | 6 | 4608.5791 | 7.6 | 16898.1233 | 58101.8767 | 3405.6 | 4608.5791 | 135.3% |  | 2758144 |  | 1 | 4 | 0 | meeting
2014-02-14 | rr | 3119 | 8 | 0 | 7 | 5376.6756 | 8 | 22274.7989 | 52725.2011 | 4128 | 5376.6756 | 130.2% |  | 2758144 |  | 0 | 0 | 0
2014-02-15 | rr | 3119 | 6 | 0 | 5 | 3840.4826 | 6 | 26115.2815 | 48884.7185 | 3096 | 3840.4826 | 124% |  | 2758144 |  | 0 | 0 | 0
2014-02-17 | rr | 3119 | 8 | 0 | 7 | 5376.6756 | 8 | 31491.9571 | 43508.0429 | 4128 | 5376.6756 | 130.2% |  | 2758144/2758782 |  | 0 | 0 | 0
2014-02-17 | mb | 3658 | 8 | 0 | 7 | 5376.6756 | 8 | 36868.6327 | 38131.3673 | 4128 | 5376.6756 | 130.2% |  | 2758782 |  | 0 | 0 | 0
2014-02-18 | rr | 3119 | 1.5 | 0 | 1 | 768.0965 | 1.5 | 37636.7292 | 37363.2708 | 774 | 768.0965 | 99.24% |  | 2758728 |  | 0 | 0 | 0 | 6.5 hrs on D6 (Disassembly0
2014-02-18 | mb | 3658 | 8 | 0 | 6 | 4608.5791 | 8 | 42245.3083 | 32754.6917 | 4128 | 4608.5791 | 111.6% |  | 2758782 |  | 0 | 0 | 0
2014-02-20 | rr | 3119 | 8 | 0 | 7 | 5376.6756 | 8 | 47621.9839 | 27378.0161 | 4128 | 5376.6756 | 130.2% |  | 2758782 |  | 0 | 0 | 0
2014-02-21 | rr | 3119 | 8 | 0 | 7 | 5376.6756 | 8 | 52998.6595 | 22001.3405 | 4128 | 5376.6756 | 130.2% |  | 2758782/2758743 |  | 0 | 0 | 0
2014-02-24 | RR | 3119 | 7 | 0 | 6 | 4608.5791 | 7 | 57607.2386 | 17392.7614 | 3612 | 4608.5791 | 127.6% |  | 2758743 |  | 0 | 0 | 0 | S/U PR7602
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0! | [6 empty] | JOB PULLED
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
[6 empty] | 0 | 0 | 57607.2386 | 17392.7614 | 0 | 0 | #DIV/0!
|  |  | 87.1 | 3 | 75 | 57607.2386 | 90.6 | [8 empty] | 3.5 |  | 0 | Page 1
Barstock Efficiency |  |  | Actual Efficiency |  |  |  | Down Time Codes |  |  | Total Hours | First Part Inspection Record
Total Planned Pcs |  | 44943.6 | Total Counted Pcs |  |  | 57587 | 1 | Maintenance |  | 2.5 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes
[7 empty] | 2 | Tooling |  | 0
BarStock Efficiency |  | 128.2% | Actual Efficiency |  |  | 128.1% | 3 | Setup Idle |  | 0 | 2014-02-10 |  | 12:15 |  | YES | ok |  | DH
[7 empty] | 4 | Other |  | 1
Total Barstock Pcs |  | 57607.2386