## Master
Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record
[6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME | [7 empty] | Setup Allowed Hrs. |  |  | 24 | [6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 24 | [6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 24 | [6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 24
[6 empty] | Rev Letter |  | A |  | Wgt/Bar | 122.07 | Total Bars |  | 18 |  |  |  | Setup Actual Hrs. |  |  | 31.5 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 122.07 | Total Bars |  | 18 |  |  |  | Setup Actual Hrs. |  |  | 31.5 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 122.07 | Total Bars |  | 18 |  |  |  | Setup Actual Hrs. |  |  | 31.5 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 122.07 | Total Bars |  | 18 |  |  |  | Setup Actual Hrs. |  |  | 31.5
Part No. | S20S20003-10 |  |  |  |  | Planned Pcs/Hr |  | 217 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 76.19% | Part No. | S20S20003-10 |  |  |  |  | Planned Pcs/Hr |  | 217 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 76.19% | Part No. | S20S20003-10 |  |  |  |  | Planned Pcs/Hr |  | 217 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 76.19% | Part No. | S20S20003-10 |  |  |  |  | Planned Pcs/Hr |  | 217 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 76.19%
|  |  |  | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions
Order No. | 369340 |  |  |  |  | Standard |  | 13.2 |  | Wgt/Pc | 1.7693 | Pcs/Bar |  | 68.9934 | [7 empty] | Order No. | 369340 |  |  |  |  | Standard |  | 13.2 |  | Wgt/Pc | 1.7693 | Pcs/Bar |  | 68.9934 | [7 empty] | Order No. | 369340 |  |  |  |  | Standard |  | 13.2 |  | Wgt/Pc | 1.7693 | Pcs/Bar |  | 68.9934 | [7 empty] | Order No. | 369340 |  |  |  |  | Standard |  | 13.2 |  | Wgt/Pc | 1.7693 | Pcs/Bar |  | 68.9934
|  |  |  | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified
Order Qty | 900 |  |  |  |  | Actual |  |  |  | Component |  | A02001-0060 | [9 empty] | Order Qty | 900 |  |  |  |  | Actual |  |  |  | Component |  | A02001-0060 | [9 empty] | Order Qty | 900 |  |  |  |  | Actual |  |  |  | Component |  | A02001-0060 | [9 empty] | Order Qty | 900 |  |  |  |  | Actual |  |  |  | Component |  | A02001-0060
1081
Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes
|  | Beginning Balance | [5 empty] | 0 | 900 | [12 empty] | Carried over from previous sheet |  |  | 11 | 31.5 | 956 | 2.3094 | 21.5 | 956 | -56 | 2387 | [5 empty] | 10.5 |  | 0 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 11 | 31.5 | 956 | 2.3094 | 21.5 | 956 | -56 | 2387 | [5 empty] | 10.5 |  | 0 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 11 | 31.5 | 956 | 2.3094 | 21.5 | 956 | -56 | 2387 | [5 empty] | 10.5 |  | 0 | Balance brought forward
??? | EB |  | 0 | 3 | 0 | 0 | 3 | 0 | 900 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
2015-05-11 | JS | 27954 | 0 | 6 | 0 | 0 | 9 | 0 | 900 | 0 | 0 |  |  |  |  | 3 | 3 | 0 | Working on A6 | [10 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
2015-05-11 | EB | 28297 | 0 | 6.5 | 0 | 0 | 8 | 0 | 900 | 0 | 0 |  |  |  |  | 1.5 | 3 | 0 | [11 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
2015-05-12 | JS | 27954 | 0 | 6 | 0 | 0 | 9 | 0 | 900 | 0 | 0 |  |  |  |  | 3 | 3 | 0 | Wrk on A6 | [10 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
2015-05-12 | EB | 28297 | 0 | 6 | 0 | 0 | 8 | 0 | 900 | 0 | 0 |  |  |  |  | 2 | 4 | 0 | Fair | [10 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
2015-05-13 | JS | 27954 | 3 | 4 | 408 | 0.9856 | 7 | 408 | 492 | 651 | 408 | 62.67% |  |  |  | 0 | 0 | 0 | 1st art/moved to A15 | [10 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
2015-05-13 | EB | 28297 | 7 | 0 | 430 | 1.0387 | 8 | 838 | 62 | 1519 | 430 | 28.31% |  |  |  | 1 | 2 | 0 | Conveyer prob/mach run on 5 spindle | [10 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
2015-05-14 | JS | 27954 | 1 | 0 | 118 | 0.28505 | 1 | 956 | -56 | 217 | 118 | 54.38% |  |  |  | 0 | 0 | 0 | JOB OUT | [10 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [7 empty] | NO PARTS AT THE MACH-AW | [10 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
[8 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0 | [18 empty] | 956 | -56 | 0 | 0
|  |  | 11 | 31.5 | 956 | 2.3094 | 21.5 | 956 | -56 | 2387 | [5 empty] | 10.5 |  | 0 | Page 1 | [5 empty] | 11 | 31.5 | 956 | 2.3094 | 21.5 | 956 | -56 | 2387 | [5 empty] | 10.5 |  | 0 | Page 2 | [5 empty] | 11 | 31.5 | 956 | 2.3094 | 21.5 | 956 | -56 | 2387 | [5 empty] | 10.5 |  | 0 | Page 3 | [5 empty] | 11 | 31.5 | 956 | 2.3094 | 21.5 | 956 | -56 | 2387 | [5 empty] | 10.5 |  | 0 | Page 4
Efficiency |  |  | Final Part and Material Calculation |  |  |  | Total Down Time on Page Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record
Total Planned Pcs |  | 2387 | Total Counted Pcs |  |  | 920 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 2387 | Total Counted Pcs |  |  | 920 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 2387 | Total Counted Pcs |  |  | 920 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 2387 | Total Counted Pcs |  |  | 920 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes
Efficiency |  | 40.05% | Total Scrap Pcs |  |  | 0 | 2 | Tooling |  | 1 | [11 empty] | Efficiency |  | 40.05% | Total Scrap Pcs |  |  | 0 | 2 | Tooling |  | 1 | [11 empty] | Efficiency |  | 40.05% | Total Scrap Pcs |  |  | 0 | 2 | Tooling |  | 1 | [11 empty] | Efficiency |  | 40.05% | Total Scrap Pcs |  |  | 0 | 2 | Tooling |  | 1
Machine Count (PCS) |  | 956 | Estimated Short Parts |  |  | 36 | 3 | Setup Idle |  | 7.5 | [11 empty] | Machine Count (PCS) |  | 956 | Estimated Short Parts |  |  | 36 | 3 | Setup Idle |  | 7.5 | [11 empty] | Machine Count (PCS) |  | 956 | Estimated Short Parts |  |  | 36 | 3 | Setup Idle |  | 7.5 | [11 empty] | Machine Count (PCS) |  | 956 | Estimated Short Parts |  |  | 36 | 3 | Setup Idle |  | 7.5
|  |  | Difference in Parts |  |  | 0 | 4 | Other |  | 2 | [14 empty] | Difference in Parts |  |  | 0 | 4 | Other |  | 2 | [14 empty] | Difference in Parts |  |  | 0 | 4 | Other |  | 2 | [14 empty] | Difference in Parts |  |  | 0 | 4 | Other |  | 2
|  |  | Material Difference LBS. |  |  | 0 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | 0 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | 0 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | 0 | 5 | Alternate - Tooling/ Units/ S/U |  | 0