## Master
Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record
[6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 16 | [6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 16 | [6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 16 | [6 empty] | Machine No. |  | A14 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 16
[6 empty] | Rev Letter |  | C |  | Wgt/Bar | 49.86 | Total Bars |  | 156 |  |  |  | Setup Actual Hrs. |  |  | 31.5 | [6 empty] | Rev Letter |  | C |  | Wgt/Bar | 49.86 | Total Bars |  | 156 |  |  |  | Setup Actual Hrs. |  |  | 31.5 | [6 empty] | Rev Letter |  | C |  | Wgt/Bar | 49.86 | Total Bars |  | 156 |  |  |  | Setup Actual Hrs. |  |  | 31.5 | [6 empty] | Rev Letter |  | C |  | Wgt/Bar | 49.86 | Total Bars |  | 156 |  |  |  | Setup Actual Hrs. |  |  | 31.5
Part No. | VC10071-20 |  |  |  |  | Planned Pcs/Hr |  | 100 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 50.79% | Part No. | VC10071-20 |  |  |  |  | Planned Pcs/Hr |  | 100 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 50.79% | Part No. | VC10071-20 |  |  |  |  | Planned Pcs/Hr |  | 100 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 50.79% | Part No. | VC10071-20 |  |  |  |  | Planned Pcs/Hr |  | 100 |  | Bars per Load | 6 | Remaing Bars |  | -6 |  |  |  | Setup % |  |  | 50.79%
|  |  |  | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions
Order No. | 353832 |  |  |  |  | Standard 2" |  | 27.8 |  | Wgt/Pc | 1.6951 | Pcs/Bar |  | 29.4142 |  | ACT reviewed 1/2 @ 33.2 - operator to speed up per RD // ACT reviewed 1/5 @ 28 - 100 pcs/hr | [5 empty] | Order No. | 353832 |  |  |  |  | Standard |  | 27.8 |  | Wgt/Pc | 1.6951 | Pcs/Bar |  | 29.4142 |  | ACT reviewed 1/2 @ 33.2 - operator to speed up per RD // ACT reviewed 1/5 @ 28 - 100 pcs/hr | [5 empty] | Order No. | 353832 |  |  |  |  | Standard |  | 27.8 |  | Wgt/Pc | 1.6951 | Pcs/Bar |  | 29.4142 |  | ACT reviewed 1/2 @ 33.2 - operator to speed up per RD // ACT reviewed 1/5 @ 28 - 100 pcs/hr | [5 empty] | Order No. | 353832 |  |  |  |  | Standard |  | 27.8 |  | Wgt/Pc | 1.6951 | Pcs/Bar |  | 29.4142 |  | ACT reviewed 1/2 @ 33.2 - operator to speed up per RD // ACT reviewed 1/5 @ 28 - 100 pcs/hr
|  |  |  | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified
Order Qty | 4500 |  |  |  |  | Actual |  | 28 | RD | Component |  | A01002-0038 | [9 empty] | Order Qty | 4500 |  |  |  |  | Actual |  | 28 | RD | Component |  | A01002-0038 | [9 empty] | Order Qty | 4500 |  |  |  |  | Actual |  | 28 | RD | Component |  | A01002-0038 | [9 empty] | Order Qty | 4500 |  |  |  |  | Actual |  | 28 | RD | Component |  | A01002-0038
1081
Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes
|  | Beginning Balance | [5 empty] | 0 | 4500 | [12 empty] | Carried over from previous sheet |  |  | 52.5 | 31.5 | 4581 | 25.9569 | 66 | 4581 | -81 | 5250 | [5 empty] | 13.5 |  | 27 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 52.5 | 31.5 | 4581 | 25.9569 | 66 | 4581 | -81 | 5250 | [5 empty] | 13.5 |  | 27 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 52.5 | 31.5 | 4581 | 25.9569 | 66 | 4581 | -81 | 5250 | [5 empty] | 13.5 |  | 27 | Balance brought forward
2014-12-26 | DH/JS | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 4500 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2014-12-29 | JT | 27815 | 0 | 5 | 0 | 0 | 10 | 0 | 4500 | 0 | 0 |  |  |  |  | 5 | 3 | 0 | Wrkd on A12/13 / 3rd machine | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2014-12-30 | JT | 27815 | 0 | 8 | 0 | 0 | 8 | 0 | 4500 | 0 | 0 |  |  | 498443 |  | 0 | 0 | 7 | 11/Maint/wrk on oil filters | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2014-12-31 | JT | 27815 | 0 | 10 | 0 | 0 | 10 | 0 | 4500 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-02 | JT | 27815 | 5.5 | 0.5 | 528 | 2.9918 | 10 | 528 | 3972 | 550 | 528 | 96% |  | 498443 |  | 4 | 4 | 20 | 19/Fair | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-05 | JT | 27815 | 10 | 0 | 720 | 4.0797 | 10 | 1248 | 3252 | 1000 | 720 | 72% |  | 498443 |  | 0 | 0 | 0 | Wrkng on A13 | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-05 | SB | 3657 | 8 | 0 | 655 | 3.7114 | 8 | 1903 | 2597 | 800 | 655 | 81.88% |  | 498443 |  | 0 | 0 | 0 | Deburr 8sp parts/one machine | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-06 | JT | 27815 | 9 | 0 | 912 | 5.1676 | 10 | 2815 | 1685 | 900 | 912 | 101.3% |  | 499109 |  | 1 | 4 | 0 | Wrkng on A13 | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-07 | JT | 27815 | 2 | 0 | 199 | 1.1276 | 2 | 3014 | 1486 | 200 | 199 | 99.5% |  |  |  | 0 | 0 | 0 | Mvd to A15 | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-07 | JS | 27954 | 7 | 0 | 803 | 4.55 | 7 | 3817 | 683 | 700 | 803 | 114.7% |  | 499109 |  | 0 | 0 | 0 | Mvd from A6 | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-07 | SB | 3657 | 4.5 | 0 | 230 | 1.3032 | 4.5 | 4047 | 453 | 450 | 230 | 51.11% |  | 499109 |  | 0 | 0 | 0 | Mvd to A5/mach crashed | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
2015-01-08 | JT | 27815 | 6.5 | 0 | 534 | 3.0258 | 10 | 4581 | -81 | 650 | 534 | 82.15% |  | 499109 |  | 3.5 | 2 | 0 | Fix wreck/3rd mach | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [7 empty] | JOB OUT | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [7 empty] | No parts @ mach per RD | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [7 empty] | 1/30 cc/terrence 37 pieces less | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [7 empty] | changed from 4715 to 4678. | [10 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
[8 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0 | [18 empty] | 4581 | -81 | 0 | 0
|  |  | 52.5 | 31.5 | 4581 | 25.9569 | 66 | 4581 | -81 | 5250 | [5 empty] | 13.5 |  | 27 | Page 1 | [5 empty] | 52.5 | 31.5 | 4581 | 25.9569 | 66 | 4581 | -81 | 5250 | [5 empty] | 13.5 |  | 27 | Page 2 | [5 empty] | 52.5 | 31.5 | 4581 | 25.9569 | 66 | 4581 | -81 | 5250 | [5 empty] | 13.5 |  | 27 | Page 3 | [5 empty] | 52.5 | 31.5 | 4581 | 25.9569 | 66 | 4581 | -81 | 5250 | [5 empty] | 13.5 |  | 27 | Page 4
Efficiency |  |  | Final Part and Material Calculation |  |  |  | Total Down Time on Page Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record
Total Planned Pcs |  | 5250 | Total Counted Pcs |  |  | 4678 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 5250 | Total Counted Pcs |  |  | 4678 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 5250 | Total Counted Pcs |  |  | 4678 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 5250 | Total Counted Pcs |  |  | 4678 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes
Efficiency |  | 87.26% | Total Scrap Pcs |  |  | 27 | 2 | Tooling |  | 3.5 | [11 empty] | Efficiency |  | 87.26% | Total Scrap Pcs |  |  | 27 | 2 | Tooling |  | 3.5 | [11 empty] | Efficiency |  | 87.26% | Total Scrap Pcs |  |  | 27 | 2 | Tooling |  | 3.5 | [11 empty] | Efficiency |  | 87.26% | Total Scrap Pcs |  |  | 27 | 2 | Tooling |  | 3.5
Machine Count (PCS) |  | 4581 | Estimated Short Parts |  |  | 312 | 3 | Setup Idle |  | 5 | [11 empty] | Machine Count (PCS) |  | 4581 | Estimated Short Parts |  |  | 312 | 3 | Setup Idle |  | 5 | [11 empty] | Machine Count (PCS) |  | 4581 | Estimated Short Parts |  |  | 312 | 3 | Setup Idle |  | 5 | [11 empty] | Machine Count (PCS) |  | 4581 | Estimated Short Parts |  |  | 312 | 3 | Setup Idle |  | 5
|  |  | Difference in Parts |  |  | 436 | 4 | Other |  | 5 | [14 empty] | Difference in Parts |  |  | 436 | 4 | Other |  | 5 | [14 empty] | Difference in Parts |  |  | 436 | 4 | Other |  | 5 | [14 empty] | Difference in Parts |  |  | 436 | 4 | Other |  | 5
|  |  | Material Difference LBS. |  |  | -739.0636 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -739.0636 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -739.0636 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -739.0636 | 5 | Alternate - Tooling/ Units/ S/U |  | 0