## Master
Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record
[6 empty] | Machine No. |  | L3 |  | HYDROMAT / ACME | [7 empty] | Setup Allowed Hrs. |  |  | 32 | [6 empty] | Machine No. |  | L3 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 32 | [6 empty] | Machine No. |  | L3 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 32 | [6 empty] | Machine No. |  | L3 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 32
[6 empty] | Rev Letter |  | A |  | Wgt/Bar | 29.31 | Total Bars |  | 21 |  |  |  | Setup Actual Hrs. |  |  | 82.4 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 29.31 | Total Bars |  | 21 |  |  |  | Setup Actual Hrs. |  |  | 82.4 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 29.31 | Total Bars |  | 21 |  |  |  | Setup Actual Hrs. |  |  | 82.4 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 29.31 | Total Bars |  | 21 |  |  |  | Setup Actual Hrs. |  |  | 82.4
Part No. | EC5053 |  |  |  |  | Planned Pcs/Hr |  | 405 |  | Bars per Load | 1 | Remaing Bars |  | -5 |  |  |  | Setup % |  |  | 38.83% | Part No. | EC5053 |  |  |  |  | Planned Pcs/Hr |  | 405 |  | Bars per Load | 1 | Remaing Bars |  | -5 |  |  |  | Setup % |  |  | 38.83% | Part No. | EC5053 |  |  |  |  | Planned Pcs/Hr |  | 405 |  | Bars per Load | 1 | Remaing Bars |  | -5 |  |  |  | Setup % |  |  | 38.83% | Part No. | EC5053 |  |  |  |  | Planned Pcs/Hr |  | 405 |  | Bars per Load | 1 | Remaing Bars |  | -5 |  |  |  | Setup % |  |  | 38.83%
|  |  |  | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions
Order No. | 345971 |  |  |  |  | Standard L3 |  | 8 |  | Wgt/Pc | 0.3047 | Pcs/Bar |  | 96.193 | [7 empty] | Order No. | 345971 |  |  |  |  | Standard |  | 8 |  | Wgt/Pc | 0.3047 | Pcs/Bar |  | 96.193 | [7 empty] | Order No. | 345971 |  |  |  |  | Standard |  | 8 |  | Wgt/Pc | 0.3047 | Pcs/Bar |  | 96.193 | [7 empty] | Order No. | 345971 |  |  |  |  | Standard |  | 8 |  | Wgt/Pc | 0.3047 | Pcs/Bar |  | 96.193
|  |  |  | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified
Order Qty | 2000 |  |  |  |  | Actual |  |  |  | Component |  | A02032-0028 | [9 empty] | Order Qty | 2000 |  |  |  |  | Actual |  |  |  | Component |  | A02032-0028 | [9 empty] | Order Qty | 2000 |  |  |  |  | Actual |  |  |  | Component |  | A02032-0028 | [9 empty] | Order Qty | 2000 |  |  |  |  | Actual |  |  |  | Component |  | A02032-0028
1081
Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes
|  | Beginning Balance | [5 empty] | 0 | 2000 | [12 empty] | Carried over from previous sheet |  |  | 7.6 | 82.4 | 2425 | 25.2097 | 17.6 | 2425 | -425 | 3078 | [5 empty] | 13.1 |  | 73 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 7.6 | 82.4 | 2425 | 25.2097 | 17.6 | 2425 | -425 | 3078 | [5 empty] | 13.1 |  | 73 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 7.6 | 82.4 | 2425 | 25.2097 | 17.6 | 2425 | -425 | 3078 | [5 empty] | 13.1 |  | 73 | Balance brought forward
2014-09-03 | DR/BW | [6 empty] | 0 | 2000 | 0 | 0 |  |  |  |  | 3.1 | 3 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-04 | TED | 28140 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  | N/A |  | 0 | 0 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-04 | DR/BW |  | 0 | 4 | 0 | 0 | 7.6 | 0 | 2000 | -1.7986e-13 | 0 | 0% |  |  |  | 3.6 | 3 | 0 | Wrkd on L2 | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-05 | TG | 28140 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-05 | TG | 28140 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 1 on 1 per JD | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-06 | BEN W | 27927 | 0 | 6 | 0 | 0 | 6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-06 | SP | 3504 | 0 | 6.6 | 0 | 0 | 6.6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-08 | TG | 28140 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  | N/A |  | 0 | 0 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-08 | TG | 28140 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 1 on 1 per JD | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-08 | BM/MF |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | Trainee/trainer | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-08 | DR | 28073 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-09 | TG | 28140 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-09 | TG | 28140 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 1 on 1 per JD | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-09 | BM/MF |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | Trainee/trainer | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-09 | DR | 28073 | 2.6 | 5 | 425 | 4.4182 | 7.6 | 425 | 1575 | 1053 | 425 | 40.36% |  | 424573H |  | 0 | 0 | 35 | 11 | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-10 | TG | 28140 | 5 | 0 | 2000 | 20.7915 | 7.6 | 2425 | -425 | 2025 | 2000 | 98.77% |  | 424573H |  | 2.6 | 2 | 0 | St10/5 | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-10 | BM/MF |  | 0 | 0 | 0 | 0 | 3.8 | 2425 | -425 | 0 | 0 |  |  |  |  | 3.8 | 2 | 0 | Collets/tooling/wrk on L2/training | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [7 empty] | JOB OUT | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [7 empty] | No parts @ mach per MR | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
2014-09-10 | BM/MF | [6 empty] | 2425 | -425 | 0 | 0 | [6 empty] | 38 | Q10 | [10 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
[8 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0 | [18 empty] | 2425 | -425 | 0 | 0
|  |  | 7.6 | 82.4 | 2425 | 25.2097 | 17.6 | 2425 | -425 | 3078 | [5 empty] | 13.1 |  | 73 | Page 1 | [5 empty] | 7.6 | 82.4 | 2425 | 25.2097 | 17.6 | 2425 | -425 | 3078 | [5 empty] | 13.1 |  | 73 | Page 2 | [5 empty] | 7.6 | 82.4 | 2425 | 25.2097 | 17.6 | 2425 | -425 | 3078 | [5 empty] | 13.1 |  | 73 | Page 3 | [5 empty] | 7.6 | 82.4 | 2425 | 25.2097 | 17.6 | 2425 | -425 | 3078 | [5 empty] | 13.1 |  | 73 | Page 4
Efficiency |  |  | Final Part and Material Calculation |  |  |  | Total Down Time on Page Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record
Total Planned Pcs |  | 3078 | Total Counted Pcs |  |  | 2487 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 3078 | Total Counted Pcs |  |  | 2487 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 3078 | Total Counted Pcs |  |  | 2487 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 3078 | Total Counted Pcs |  |  | 2487 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes
Efficiency |  | 78.78% | Total Scrap Pcs |  |  | 73 | 2 | Tooling |  | 6.4 | [11 empty] | Efficiency |  | 78.78% | Total Scrap Pcs |  |  | 73 | 2 | Tooling |  | 6.4 | [11 empty] | Efficiency |  | 78.78% | Total Scrap Pcs |  |  | 73 | 2 | Tooling |  | 6.4 | [11 empty] | Efficiency |  | 78.78% | Total Scrap Pcs |  |  | 73 | 2 | Tooling |  | 6.4
Machine Count (PCS) |  | 2425 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 6.7 | 2014-09-09 |  | 19:40 |  | YES | OK |  | VG |  |  |  | Machine Count (PCS) |  | 2425 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 6.7 | 2014-09-09 |  | 19:40 |  | YES | OK |  | VG |  |  |  | Machine Count (PCS) |  | 2425 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 6.7 | 2014-09-09 |  | 19:40 |  | YES | OK |  | VG |  |  |  | Machine Count (PCS) |  | 2425 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 6.7 | 2014-09-09 |  | 19:40 |  | YES | OK |  | VG
|  |  | Difference in Parts |  |  | 135 | 4 | Other |  | 0 | [14 empty] | Difference in Parts |  |  | 135 | 4 | Other |  | 0 | [14 empty] | Difference in Parts |  |  | 135 | 4 | Other |  | 0 | [14 empty] | Difference in Parts |  |  | 135 | 4 | Other |  | 0
|  |  | Material Difference LBS. |  |  | -41.1345 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -41.1345 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -41.1345 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -41.1345 | 5 | Alternate - Tooling/ Units/ S/U |  | 0