## Master
Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record | [21 empty] | Control Devices LLC Work Order Production Record
[6 empty] | Machine No. |  | L2 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 64 | [6 empty] | Machine No. |  | L2 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 64 | [6 empty] | Machine No. |  | L2 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 64 | [6 empty] | Machine No. |  | L2 |  | HYDROMAT / ACME / 2ND OPS | [7 empty] | Setup Allowed Hrs. |  |  | 64
[6 empty] | Rev Letter |  | A |  | Wgt/Bar | 18.04 | Total Bars |  | 188 |  |  |  | Setup Actual Hrs. |  |  | 53.1 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 18.04 | Total Bars |  | 188 |  |  |  | Setup Actual Hrs. |  |  | 53.1 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 18.04 | Total Bars |  | 188 |  |  |  | Setup Actual Hrs. |  |  | 53.1 | [6 empty] | Rev Letter |  | A |  | Wgt/Bar | 18.04 | Total Bars |  | 188 |  |  |  | Setup Actual Hrs. |  |  | 53.1
Part No. | 106-129-2 |  |  |  |  | Planned Pcs/Hr |  | 205 |  | Bars per Load | 1 | Remaing Bars |  | 8 |  |  |  | Setup % |  |  | 120.5% | Part No. | 106-129-2 |  |  |  |  | Planned Pcs/Hr |  | 205 |  | Bars per Load | 1 | Remaing Bars |  | 8 |  |  |  | Setup % |  |  | 120.5% | Part No. | 106-129-2 |  |  |  |  | Planned Pcs/Hr |  | 205 |  | Bars per Load | 1 | Remaing Bars |  | 8 |  |  |  | Setup % |  |  | 120.5% | Part No. | 106-129-2 |  |  |  |  | Planned Pcs/Hr |  | 205 |  | Bars per Load | 1 | Remaing Bars |  | 8 |  |  |  | Setup % |  |  | 120.5%
|  |  |  | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions | [9 empty] | ADDED W/O # |  | CYCLE TIMES | [9 empty] | Special Notes / Instructions
Order No. | 365961 |  |  |  |  | Standard L2 |  | 16 |  | Wgt/Pc | 0.225 | Pcs/Bar |  | 80.1778 |  | ACT reviewed at 15.8/205pcs per hr | [5 empty] | Order No. | 365961 |  |  |  |  | Standard |  | 16 |  | Wgt/Pc | 0.225 | Pcs/Bar |  | 80.1778 |  | ACT reviewed at 15.8/205pcs per hr | [5 empty] | Order No. | 365961 |  |  |  |  | Standard |  | 16 |  | Wgt/Pc | 0.225 | Pcs/Bar |  | 80.1778 |  | ACT reviewed at 15.8/205pcs per hr | [5 empty] | Order No. | 365961 |  |  |  |  | Standard |  | 16 |  | Wgt/Pc | 0.225 | Pcs/Bar |  | 80.1778 |  | ACT reviewed at 15.8/205pcs per hr
|  |  |  | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified | [16 empty] | QTY CHANGE INLS/DATE |  |  |  |  | Verified
Order Qty | 15000 |  |  |  |  | Actual |  | 15.8 | AW | Component |  | A08031-0124 | [9 empty] | Order Qty | 15000 |  |  |  |  | Actual |  | 15.8 | AW | Component |  | A08031-0124 | [9 empty] | Order Qty | 15000 |  |  |  |  | Actual |  | 15.8 | AW | Component |  | A08031-0124 | [9 empty] | Order Qty | 15000 |  |  |  |  | Actual |  | 15.8 | AW | Component |  | A08031-0124
1081
Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Loads Today | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes |  |  | Date | Emp. Name | Clock # | Prod. Hours | Setup Hours | Total Pcs | Pieces Today (bars) | Planned Hours | Cum. Total | Balance Due Pcs | Plan Pcs/Day | Actual Pcs/Day | % Mach. Efficiency |  | Material Heat Lot No. |  | Mach Down Time | CODE | Scrap Pcs. | Notes
|  | Beginning Balance | [5 empty] | 0 | 15000 | [12 empty] | Carried over from previous sheet |  |  | 64.5 | 53.1 | 14390 | 179.4762 | 90.3 | 14390 | 610 | 13222.5 | [5 empty] | 25.8 |  | 245 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 80.2 | 53.1 | 17950 | 223.8775 | 106 | 17950 | -2950 | 16441 | [5 empty] | 25.8 |  | 245 | Balance brought forward |  |  | Carried over from previous sheet |  |  | 80.2 | 53.1 | 17950 | 223.8775 | 106 | 17950 | -2950 | 16441 | [5 empty] | 25.8 |  | 245 | Balance brought forward
2015-07-10 | SP | 3504 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 0 | 0 | 0 |  |  |  | 2015-07-24 | DT | 3205 | 7.6 | 0 | 1700 | 21.2029 | 7.6 | 16090 | -1090 | 1558 | 1700 | 109.1% |  | 20382960 |  | 0 | 0 | 0 | Changed sta.11 inserts at 11am | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-10 | DT | 3205 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 0 | 0 | 0 |  |  |  | 2015-07-24 | DR/BW |  | 7.6 | 0 | 1740 | 21.7018 | 7.6 | 17830 | -2830 | 1558 | 1740 | 111.7% |  | 20382960 |  | 0 | 0 | 0 | [11 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-11 | SP | 3504 | 0 | 6.6 | 0 | 0 | 6.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 0 | 0 | 0 |  |  |  | 2015-07-25 | DR/BW | 28073 | 0.5 | 0 | 120 | 1.4967 | 0.5 | 17950 | -2950 | 102.5 | 120 | 117.1% |  |  |  | 0 | 0 | 0 | JOB OUT | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-13 | SP | 3504 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 0 | 0 | 0 | [11 empty] | 17950 | -2950 | 0 | 0 | [7 empty] | NO PARTS AT MACH-AW | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-13 | DT | 3205 | 0 | 1 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 6.6 | 4 | 0 | Quotes/layouts/work on L1 | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-14 | DT | 3205 | 0 | 3 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 4.6 | 4 | 0 | Quotes and layouts | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-15 | SP | 3504 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 0 | 0 | 0 | [11 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-15 | DT | 3205 | 0 | 2 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  | N/A |  | 5.6 | 4 | 0 | Waiting on Maint. | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-16 | DR | 28073 | 0 | 7.6 | 0 | 0 | 7.6 | 0 | 15000 | 0 | 0 |  |  |  |  | 0 | 0 | 63 | 11 | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-17 | DT | 3205 | 4 | 2.5 | 800 | 9.9778 | 7.6 | 800 | 14200 | 820 | 800 | 97.56% |  | 20382960 |  | 1.1 | 4 | 0 | Fair/prob w/cutter/sta.13 | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-17 | DR | 28073 | 4.6 | 0 | 1010 | 12.597 | 7.6 | 1810 | 13190 | 943 | 1010 | 107.1% |  |  |  | 3 | 2 | 88 | 19 dwn at start/re-clocking mill | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-20 | DT | 3205 | 7.6 | 0 | 1685 | 21.0158 | 7.6 | 3495 | 11505 | 1558 | 1685 | 108.2% |  | 20382960 |  | 0 | 0 | 60 | H13, end mill mark | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-20 | DR | 28073 | 7 | 0 | 1600 | 19.9557 | 7.6 | 5095 | 9905 | 1435 | 1600 | 111.5% |  |  |  | 0.6 | 2 | 0 | [11 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-21 | DT | 3205 | 6 | 0 | 1350 | 16.8376 | 7.1 | 6445 | 8555 | 1230 | 1350 | 109.8% |  | 20382960 |  | 1.1 | 2 | 0 | End mill sta.10 | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-21 | DT | 3205 | 0 | 0 | 0 | 0 | 0.5 | 6445 | 8555 | 0 | 0 |  |  |  |  | 0.5 | 4 | 0 | Meeting | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-21 | DM/DR |  | 7.1 | 0 | 1660 | 20.704 | 7.6 | 8105 | 6895 | 1455.5 | 1660 | 114.1% |  | 20382960 |  | 0.5 | 4 | 0 | Meeting | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-22 | DT | 3205 | 7.6 | 0 | 1750 | 21.8265 | 7.6 | 9855 | 5145 | 1558 | 1750 | 112.3% |  | 20382960 |  | 0 | 0 | 0 | Changed sta.11 insert | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-22 | BW | 27927 | 7.6 | 0 | 1625 | 20.2675 | 7.6 | 11480 | 3520 | 1558 | 1625 | 104.3% |  |  |  | 0 | 0 | 0 | Changed st.4 reamer | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-23 | DT | 3205 | 6.4 | 0 | 1540 | 19.2073 | 7.6 | 13020 | 1980 | 1312 | 1540 | 117.4% |  | 20382960 |  | 1.2 | 4 | 0 | Lunch | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
2015-07-23 | BW/DR |  | 6.6 | 0 | 1370 | 17.087 | 7.6 | 14390 | 610 | 1353 | 1370 | 101.3% |  | 20382960 |  | 1 | 4 | 34 | B4 Drill/reamer/lunch | [10 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
[8 empty] | 14390 | 610 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
[8 empty] | 14390 | 610 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
[8 empty] | 14390 | 610 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
[8 empty] | 14390 | 610 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
[8 empty] | 14390 | 610 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
[8 empty] | 14390 | 610 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0 | [18 empty] | 17950 | -2950 | 0 | 0
|  |  | 64.5 | 53.1 | 14390 | 179.4762 | 90.3 | 14390 | 610 | 13222.5 | [5 empty] | 25.8 |  | 245 | Page 1 | [5 empty] | 80.2 | 53.1 | 17950 | 223.8775 | 106 | 17950 | -2950 | 16441 | [5 empty] | 25.8 |  | 245 | Page 2 | [5 empty] | 80.2 | 53.1 | 17950 | 223.8775 | 106 | 17950 | -2950 | 16441 | [5 empty] | 25.8 |  | 245 | Page 3 | [5 empty] | 80.2 | 53.1 | 17950 | 223.8775 | 106 | 17950 | -2950 | 16441 | [5 empty] | 25.8 |  | 245 | Page 4
Efficiency |  |  | Final Part and Material Calculation |  |  |  | Total Down Time on Page Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record | [10 empty] | Efficiency |  |  | Final Part and Material Calculation |  |  |  | Down Time Code Description Hours |  |  |  | First Part Inspection Record
Total Planned Pcs |  | 16441 | Total Counted Pcs |  |  | 17850 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 16441 | Total Counted Pcs |  |  | 17850 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 16441 | Total Counted Pcs |  |  | 17850 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes |  | Total Planned Pcs |  | 16441 | Total Counted Pcs |  |  | 17850 | 1 | Maintenance |  | 0 | Date Part Submitted |  | Time Of Day |  | Approved Yes / No | Material Check |  | Inspector |  | Notes
Efficiency |  | 109.2% | Total Scrap Pcs |  |  | 245 | 2 | Tooling |  | 4.7 | [11 empty] | Efficiency |  | 109.2% | Total Scrap Pcs |  |  | 245 | 2 | Tooling |  | 4.7 | [11 empty] | Efficiency |  | 109.2% | Total Scrap Pcs |  |  | 245 | 2 | Tooling |  | 4.7 | [11 empty] | Efficiency |  | 109.2% | Total Scrap Pcs |  |  | 245 | 2 | Tooling |  | 4.7
Machine Count (PCS) |  | 17950 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 0 | 2015-07-17 |  | 930am |  | yes | ok | [5 empty] | Machine Count (PCS) |  | 17950 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 0 | 2015-07-17 |  | 930am |  | yes | ok | [5 empty] | Machine Count (PCS) |  | 17950 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 0 | 2015-07-17 |  | 930am |  | yes | ok | [5 empty] | Machine Count (PCS) |  | 17950 | Estimated Short Parts |  |  | 0 | 3 | Setup Idle |  | 0 | 2015-07-17 |  | 930am |  | yes | ok
|  |  | Difference in Parts |  |  | 145 | 4 | Other |  | 21.1 | [14 empty] | Difference in Parts |  |  | 145 | 4 | Other |  | 21.1 | [14 empty] | Difference in Parts |  |  | 145 | 4 | Other |  | 21.1 | [14 empty] | Difference in Parts |  |  | 145 | 4 | Other |  | 21.1
|  |  | Material Difference LBS. |  |  | -32.625 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -32.625 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -32.625 | 5 | Alternate - Tooling/ Units/ S/U |  | 0 | [14 empty] | Material Difference LBS. |  |  | -32.625 | 5 | Alternate - Tooling/ Units/ S/U |  | 0